## Sheet1
Phase | Area of Focus | Activity | Sub-Activity | Responsibility | Deleverable | Timeline
Phase One | Special Olympics policies, procedures and processes | Review of existing National policies, procecdures and processes | Review of existing National policies | BBF |  | Within 3 months | BBF Costs
|  | Survey/Focus group on best practices and implementation at state level | Pick-up policy/Travel policy | Both |  |  | Current staff | 160000
|  |  | Handling medical concerns | Both |  |  | New staff | 210000
|  |  | On-site Tracking and Identification - attendance, records available | Both |  |  | FirstPic staff | 100000
|  |  | Internal claims reporting policy | Both |  |  | SOI staff | 250000
|  |  | Develop Safe Sport Act policies and procedures | Both |  |  | SoC contract | 100000
|  |  | Training policy for staff and volunteers | Both |  |  | Marketing | 40000
|  | Recommendations made |  | BBF | SOPI Action Plan |  | Technology | 100000
|  | Update internal governing documents and trainings aroud topics identified by BBF Action Plan |  | SOI |  |  |  | 960000
|  | Distribute new best practices and policies to U.S. state and global Special Olympic affiates |  | SOI |  | Within 6-12 months
| Online case management system | Work with technology team to identify or create a space for tracking internal claims reported from the field |  |  |  | Within 12 months
Work with SOI staff to create a system by which internal claims are assigned to SOI staff member
Develop the investigative procedure that internal claims must go through in order to be cleared
| Training Development and Delivery (Staff and volunteers) | Review of existing SOI trainings for staff and volunteers | Inrease emphasis on preventative rather than just reactive safety training policies |  |  | Within 12 months
Integrate protective behaviors training with Risk Management and Insurance Task Force
|  | Decide on training delivery (online or in-person) |  | Both
|  | Decide if adapting existing SOI online training or adapting Stewards of Children | Either way, online trainings will require specific content for different state contexts to be addressed in different versions of the training video
Develop pocket cards stating the mandatory reporting requirements for each state
|  | Ensure compliance of all trainings with Safe Sport Act requirements | Does the Safe Sport Act require mandatory reporters to report to both the Federal agency and the state agency if the person is also a mandatory reporter under State Law
Ensure consistent international training and protection standards that take into account cultural differences
Phase Two | Developing an improved system for screening volunteers | Develop and update volunteer recruiting process
Option of national database for volunteer screening (possibly work with NCMEC?)
| Training and materials development and delivery for parents and athletes | Develop trainings for parents
Develop content for parents
Develop trainings for atheles
Develop content athletes
|  | Identify a delivery mechanism for these materials | Online, at SO events (table, emails), app