1	Intended System Design (ISD)	2

1.1	Intended General Design	2

1.1.1	Hardware	4

1.1.1.1	Cabling	5

1.1.1.2	Power/Grounding Connections	5

1.1.1.3	Installation	6

1.1.2	Software	8

1.1.2.1	NFE	8

1.2	Intended Specific Design Diagrams	9

1.2.1	ISD HQ Brunssum,  Main Site	9

1.2.2	ISD HQ Brunssum,  NIC Site	10

1.2.3	ISD HQ Ramstein, Main Site	11

1.2.4	ISD HQ Heidelberg,  Main Site	12

1.2.5	ISD HQ Heidelberg,  ISK Site	13

1.3	Intended Specific Design Diagrams (expanded)	14

# Intended System Design (ISD)

## Intended General Design

The purchaser has determined in his IFB, which is the basis for this proposal, in a very detailed manner the hardware, software and services expected to be delivered/performed for this project for the purpose to have fully functional extensions to the Bi-SC Core Capabilities to the Public Access domains installed in several HQs within Europe.

These predetermined functionalities and required hard- and software specifications as well as required quantities thereof have to be taken as facts and leave no alternatives for a typical overall system design.

The intended system design as required in the course of this proposal is limited to the physical layout and configuration of the system components for an operational site under consideration of the predetermined and in the course of this project procured hard- and software.

All activities of management, control, quality assurance, Integrated Logistic Support, Configuration Management and Test & Evaluation are precisely defined in the Project Implementation Plan (PIP), which is included in this proposal in a draft version in Volume B. For the performance of this contract, the PIP will be finalized and adapted to the actual situation by Serco and discussed and approved by the purchaser shortly after CA.

The Project Manager, and in case of his absence the Deputy Project Manager, are full time positions and they will be active throughout the project from contract award, pre-installation, test, installation on site, and finally throughout the FSA. Positions such as QA and Test Manager are part time positions of personnel assigned to this task for specific periods of time with some upfront planning work and then execution around the time periods of FAT, SIT, PSA and FSA.

This Technical Proposal demonstrates how we intend to successfully “extend the ACE ACCIS Core Capacity to the MIS”. Our proposal breaks down the ACE ACCIS Core Capability extension work into 7 main phases (plus a three-year warranty support period, extendable to a five-year warranty) to correspond with the major requirements outlined in the SOW. PSA and FSA are time oriented administrative phases. There is some overlap between the phases.

A high-level summary schedule is shown in the Time Schedule attached to the draft PIP in Volume B, Annex B to this proposal.

We have broken down the project into the following phases:

- Final System Design

- Installation and Integration

- Factory Acceptance Test (FAT)

- System Integration Test (SIT)

- Documentation, Training

- Provisional System Acceptance (PSA)

- Final System Acceptance (FSA)

Highlighting the major milestones of phase 1 of the project:

Final System Design

- Last System Requirements Review: 		EDC + 15 working days

- Last System Design Review: 			Last SRR + 20 working days

- Project Implementation Plan:

  - Section 1 (final)				10 days after EDC

  - Section 2 (final QAP)				10 days after EDC

  - Section 3 (final ILSP)				20 days after EDC

  - Section 4 (final CMP)				20 days after EDC

  - Section 5 (final TEP)				5 days before first SDR

The SAN installation is a specialized task and will be subcontracted. The system chosen is a HP Solution. The SAN installation will take place by an individual or a small team early in the project prior to the FAT site by site. Some of the other installation team members will assist with any concept or integration issues after the initial installation.

Besides our own technicians, we will only be working with those subcontractors and vendors that have high level knowledge of those special tasks they are working on. ManTech, Hansen & Gieraths and BetaTech performed magnificently during the projects we had been working on in the past. This is why we have decided on a partnership with the companies mentioned.

### Hardware

The Intended System Design is based on Hewlett Packard (HP) servers, printer and scanners and CISCO switches and routers to fulfil the NATO requirements. The 5 sheets of the attached drawings show the specific Intended System Design concept for each of the 5 sites, including the 3 Headquarter sites; individual pieces of equipment are labelled on the diagram. A much more in depth listing and description of the equipment being provided is found in the completed Annex B to the Attachment 4 (SOW) of the IFB (Node Architecture) which is attached to this Volume A as Annex E-2 and in the Manufacturer data Sheets provided in Annex D.

The hardware for each system consists basically of

- blade servers, switches, storage systems and LAN components installed in 19“ rack(s). Detailed information about the selected racks is found in Annex D-1.6.9 of this Volume A.

- Workstations with monitors, Laptops with Docking Stations and peripherals (B/W printer, Colour printer, Scanner) distributed inside each individual site based on an installation plan TBD.

The equipment has been selected upon the “Minimum Required Baseline” as specified in the SOW.

#### Cabling

Signal Cabling between rack mounted components and the distributed equipment is performed by use of the specified cable types.

The cabling team will be staffed with high experienced specialists that have been working on cabling tasks for several years. They will strictly work in a way that the final system design document will be mirrored on each site. After finishing the cabling work at a site, and after finishing the FAT, we will deliver the components to the locations. On site the team will be quick working for assuring a SIT as soon as possible. The experienced experts are going to continue their work during the life cycle of the whole project. In a way of blue printing the experience we will be making at the sites, the next project milestones will be reached in time.

#### Power/Grounding Connections

The racks are centrally and the distributed equipment individually connected to the infrastructure power outlets available on site. It is assumed that sufficient quantity and quality of power outlets are available on each site.

The equipment rack(s) will have power distribution strips with sockets in sufficient quantity to provide power to each individual piece of equipment installed.

A centralized UPS is foreseen for site Heidelberg (Main Site). This UPS will be installed and connected to infrastructure power and will then provide uninterrupted mains power to the system for the duration determined in case of mains power failure.

Grounding/Earthing of the equipment rack(s) and the UPS will be established directly to the facility grounding system. The distributed equipment is grounded via the regular power connector grounding pin.

#### Installation

Based on the depicted task timing, the server/LAN installers may continue to be used as part of the following system admin/desktop installation team after they complete the server installation. This would be very useful from our point of view so that there are better trained, more experienced installation team members for a longer period of time, and thus there would be an increased efficiency and the carried over technicians could perform user and LAN integration throughout the installation period.

Following the completion of the user equipment, a subset of the installation team will stay in place for the customer support. The team needs a mix of Server/LAN and user equipment expertise. They will be used for customer support, punch list work, and support until the 3 months period is complete.

Following successful completion of systems integration there will be a three year warranty period.

We suggest a site by site approach in the project, starting with JFC Brunssum (Main Site).

- Brunssum Main Site has been selected by Serco as the first site to be installed, because it is geographically the closest to the Serco facility in Bonn and in case there are problems arising they can be solved in the most time effective manner and can be taken to avoid such problems on the following sites. Immediately after PSA the 3 months system support commences.

- Brunssum NIC Site
Deliveries for Brunssum NIC Site will be sent to Brunssum Main Site, until the NIC Site buildings are completed

- The second site will be CC-Air HQ Ramstein
The sequence of activities is identical to the ones described for Brunssum Main Site.

- The third site will be CC Land HQ Heidelberg Main Site
The sequence of activities is identical to the ones described for Brunssum Main Site.
Additional to the above, in Heidelberg Main Site a centralized UPS will be installed for the system.

- The forth site will be CC Land HQ Heidelberg ISK
The sequence of activities is identical to the ones described for Brunssum Main Site.

Our project team will install and configure all the components required for each site.

The first milestone to be reached for each site will be the FAT at the Serco facility. We are going to test all components on a high level manner. We will not deliver any hard- or software if it is not tested and accepted by the purchaser. All network and system management programs will be configured, so that the performance fit exactly to each of the sites.

The approach will be performed as required per SOW (65).

Following the physical installation and initial functional tests at the respective site, the system will be undergoing System Integration Test (SIT).

A successful SIT will be followed by Provisional Site Acceptance (PSA).

### Software

In the course of system assembling and testing at Serco and installation and testing on site, the procured software components will be installed, configured and tested accordingly.

Software components will be installed using high level specialists. All software specific items that will take care for a proper performance for each user will be on a state of the art level, so that user problems will be minimized as much as possible. We have selected a site by site approach in order to fulfil any requirement for a single site.

#### NFE

NATO furnished software licenses as specified in the IFB will be integrated also as required by the same team of high level specialists as foreseen for the installation of procured software.

## Intended Specific Design Diagrams

The intended specific design for each individual site is shown on the following diagrams. For better legibility the following diagrams are provided again at the end of this document in an expanded view.

### ISD HQ Brunssum,  Main Site

### ISD HQ Brunssum,  NIC Site

### ISD HQ Ramstein, Main Site

### ISD HQ Heidelberg,  Main Site

### ISD HQ Heidelberg,  ISK Site

## Intended Specific Design Diagrams (expanded)