ANNEXES

PART B1

(CONTRACTUAL AND DELIVERY)

THIS PAGE IS INTENTIONALLY LEFT BLANK

ANNEX B1-1

COMPLETED DELIVERY SCHEDULE

| CLIN | DESCRIPTION | Delivery dates according to the RFQ Weeks from EDC (*) | Delivery Dates proposed by the Bidder Weeks from EDC (*) | Compliance |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Y | N |
| PART I: PRODUCT ACCEPTANCE |  |  |  |  |  |
| 1.00 | Documentation - Project Management Plan (PMP) |  |  |  |  |
| 1.01 | Project Implementation Plan (PIP) | 3 weeks |  |  |  |
| 1.02 | Network Integration Test Procedures and Scenarios | 5 weeks |  |  |  |
| 1.03 | Product Acceptance Test Procedures |  |  |  |  |
| 2.00 | Meetings |  |  |  |  |
| 2.01 | Project Progress Review Meeting (PPRM) including minutes |  |  |  |  |
| 2.02 | Product Profile meetings | 8 weeks |  |  |  |
| 3.00 | Product Acceptance - NCSA Test Site | 9 weeks |  |  |  |
| 3.01 | Physical Installation on the test site |  |  |  |  |
| 3.02 | Product Acceptance Test |  |  |  |  |
| 3.03 | Product Acceptance |  |  |  |  |
| PART II: SOFTWARE PROCUREMENT, INSTALLATION & TRAINING FOR SIX (6) REGIONAL COMMANDS |  |  |  |  |  |
| 4.00 | Software | 10 weeks |  |  |  |
| 4.01 | Software license per seat |  |  |  |  |
| 4.02 | 1-Year Maintenance for 4.01 |  |  |  |  |
| 4.03 | Software license on installation server |  |  |  |  |
| 4.04 | 1-Year Maintenance for 4.03 |  |  |  |  |
| 4.05 | Installation Media CD |  |  |  |  |
| 4.06 | Software Documentation |  |  |  |  |
| 5.00 | Installation - NATO Sites |  |  |  |  |
| 5.01 | Site A: SHAPE, NCSA, NITC, BE (approx. 3966 WS) | 11 weeks |  |  |  |
| 5.01.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 5.01.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 5.01.03 | Network Integration Test |  |  |  |  |
| 5.01.04 | Site Acceptance |  |  |  |  |
| 5.02 | Site B: JFC Naples, IT (approx. 1844 WS) | 12 weeks |  |  |  |
| 5.02.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 5.02.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 5.02.03 | Network Integration Test |  |  |  |  |
| 5.02.04 | Site Acceptance |  |  |  |  |
| 5.03 | Site C: JFC Brunssum, NL (approx. 1535 WS) | 13 weeks |  |  |  |
| 5.03.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 5.03.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 5.03.03 | Network Integration Test |  |  |  |  |
| 5.03.04 | Site Acceptance |  |  |  |  |
| 5.04 | Site D: CC Mar Northwood, UK (approx. 589 WS) | 14 weeks |  |  |  |
| 5.04.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 5.04.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 5.04.03 | Network Integration Test |  |  |  |  |
| 5.04.04 | Site Acceptance |  |  |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION | Delivery dates according to the RFQ Weeks from EDC (*) | Delivery Dates proposed by the Bidder Weeks from EDC (*) | Compliance |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Y | N |
| 5.05 | Site E: JHQ Lisbon, PO (approx. 618 WS) | 15 weeks |  |  |  |
| 5.05.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 5.05.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 5.05.03 | Network Integration Test |  |  |  |  |
| 5.05.04 | Site Acceptance |  |  |  |  |
| 5.06 | Site F: SACT HQ, US (approx. 1132 WS) | 16 weeks |  |  |  |
| 5.06.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 5.06.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 5.06.03 | Network Integration Test |  |  |  |  |
| 5.06.04 | Site Acceptance |  |  |  |  |
| 6.00 | NATO Specific User Information Brochure | 10 weeks |  |  |  |
| 6.01 | NATO-specific User Information Brochure |  |  |  |  |
| 7.00 | Final System Acceptance | 30 weeks |  |  |  |
| 7.01 | FSA conduct, report and meeting |  |  |  |  |
| 8.00 | Help Desk Support |  |  |  |  |
| 8.01 | Help Desk Support | To commence with Site Acceptance of the 1st Site and last for 3 calendar months after last Site Acceptance |  |  |  |
| 8.02 | Help Desk Support | To commence with the Final System Acceptance and last for 12 calendar months |  |  |  |
| 9.00 | Warranty |  |  |  |  |
| 9.01 | 1-year warranty coverage for the CLINS 4 to 5 |  |  |  |  |
| OPTIONS |  |  |  |  |  |
| PART III - OPTIONAL: SOFTWARE PROCUREMENT |  |  |  |  |  |
| 10.00 | Additional licenses + applicable discount scheme (Annex B1-9) |  |  |  |  |
| 10.01 | Software license per seat |  |  |  |  |
| 10.02 | 1-Year Maintenance for 10.01 |  |  |  |  |
| 10.03 | Software license on installation server |  |  |  |  |
| 10.04 | 1-Year Maintenance for 10.03 |  |  |  |  |
| 10.05 | Installation Media CD |  |  |  |  |
| 10.06 | 2nd year Maintenance for 10.01 and 4.01 |  |  |  |  |
| 10.07 | 3rd year Maintenance for 10.01 and 4.01 |  |  |  |  |
| 10.08 | 2nd year Maintenance for 10.03 and 4.03 |  |  |  |  |
| 10.09 | 3rd year Maintenance for 10.03 and 4.03 |  |  |  |  |
| PART IV - OPTIONAL: INSTALLATION & TRAINING FOR NINETEEN (19) REGIONAL COMMANDS |  |  |  |  |  |
| 11.00 | Installation - NATO Sites |  |  |  |  |
| 11.01 | Site G: CC Air Izmir, TU (approx. 1295 WS) |  |  |  |  |
| 11.01.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.01.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.01.03 | Network Integration Test |  |  |  |  |
| 11.01.04 | Site Acceptance |  |  |  |  |
| 11.01.05 | 1st year warranty |  |  |  |  |
| 11.02 | Site H: CC Land Madrid, SP (approx. 462 WS) |  |  |  |  |
| 11.02.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.02.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.02.03 | Network Integration Test |  |  |  |  |
| 11.02.04 | Site Acceptance |  |  |  |  |
| 11.02.05 | 1st year warranty |  |  |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION | Delivery dates according to the RFQ Weeks from EDC (*) | Delivery Dates proposed by the Bidder Weeks from EDC (*) | Compliance |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Y | N |
| 11.03 | Site I: CC Mar Naples, IT (approx. 320 WS) |  |  |  |  |
| 11.03.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.03.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.03.03 | Network Integration Test |  |  |  |  |
| 11.03.04 | Site Acceptance |  |  |  |  |
| 11.03.05 | 1st year warranty |  |  |  |  |
| 11.04 | Site J: CC Air Ramstein, GE (approx. 1145 WS) |  |  |  |  |
| 11.04.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.04.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.04.03 | Network Integration Test |  |  |  |  |
| 11.04.04 | Site Acceptance |  |  |  |  |
| 11.04.05 | 1st year warranty |  |  |  |  |
| 11.05 | Site K: Land Heidelberg , GE(approx. 798 WS) |  |  |  |  |
| 11.05.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.05.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.05.03 | Network Integration Test |  |  |  |  |
| 11.05.04 | Site Acceptance |  |  |  |  |
| 11.05.05 | 1st year warranty |  |  |  |  |
| 11.06 | Site L: Comms Squadron Karup, DE (approx. 79 WS) |  |  |  |  |
| 11.06.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.06.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.06.03 | Network Integration Test |  |  |  |  |
| 11.06.04 | Site Acceptance |  |  |  |  |
| 11.06.05 | 1st year warranty |  |  |  |  |
| 11.07 | Site M: Comms Group Larissa, GR (approx. 213 WS) |  |  |  |  |
| 11.07.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.07.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.07.03 | Network Integration Test |  |  |  |  |
| 11.07.04 | Site Acceptance |  |  |  |  |
| 11.07.05 | 1st year warranty |  |  |  |  |
| 11.08 | Site N: Comms Squadron Verona, IT (approx. 298 WS) |  |  |  |  |
| 11.08.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.08.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.08.03 | Network Integration Test |  |  |  |  |
| 11.08.04 | Site Acceptance |  |  |  |  |
| 11.08.05 | 1st year warranty |  |  |  |  |
| 11.09 | Site O: JWC, NO (approx. 548 WS) |  |  |  |  |
| 11.09.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.09.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.09.03 | Network Integration Test |  |  |  |  |
| 11.09.04 | Site Acceptance |  |  |  |  |
| 11.09.05 | 1st year warranty |  |  |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION | Delivery dates according to the RFQ Weeks from EDC (*) | Delivery Dates proposed by the Bidder Weeks from EDC (*) | Compliance |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Y | N |
| 11.10 | Site P: JFTC PL (approx. 92 WS) |  |  |  |  |
| 11.10.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.10.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.10.03 | Network Integration Test |  |  |  |  |
| 11.10.04 | Site Acceptance |  |  |  |  |
| 11.10.05 | 1st year warranty |  |  |  |  |
| 11.11 | Site R: JALLC, PO (approx. 117 WS) |  |  |  |  |
| 11.11.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.11.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.11.03 | Network Integration Test |  |  |  |  |
| 11.11.04 | Site Acceptance |  |  |  |  |
| 11.11.05 | 1st year warranty |  |  |  |  |
| 11.12 | Site S: NCISS, IT (approx. 118 WS) |  |  |  |  |
| 11.12.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.12.01 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.12.01 | Network Integration Test |  |  |  |  |
| 11.12.01 | Site Acceptance |  |  |  |  |
| 11.12.05 | 1st year warranty |  |  |  |  |
| 11.13 | Site T: NATO School, GE (approx. 78 WS) |  |  |  |  |
| 11.13.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.13.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.13.03 | Network Integration Test |  |  |  |  |
| 11.13.04 | Site Acceptance |  |  |  |  |
| 11.13.05 | 1st year warranty |  |  |  |  |
| 11.14 | Site U: Undersea Research Centre, IT (approx. 385 WS) |  |  |  |  |
| 11.14.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.14.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.14.03 | Network Integration Test |  |  |  |  |
| 11.14.04 | Site Acceptance |  |  |  |  |
| 11.14.05 | 1st year warranty |  |  |  |  |
| 11.15 | Site V: PCC, BE (approx. 60 WS) |  |  |  |  |
| 11.15.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.15.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.15.03 | Network Integration Test |  |  |  |  |
| 11.15.04 | Site Acceptance |  |  |  |  |
| 11.15.05 | 1st year warranty |  |  |  |  |
| 11.16 | Site W: NPC, BE (approx. 245 WS) |  |  |  |  |
| 11.16.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.16.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.16.03 | Network Integration Test |  |  |  |  |
| 11.16.04 | Site Acceptance |  |  |  |  |
| 11.16.05 | 1st year warranty |  |  |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION | Delivery dates according to the RFQ Weeks from EDC (*) | Delivery Dates proposed by the Bidder Weeks from EDC (*) | Compliance |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Y | N |
| 11.17 | Site X: DCM/DCIS Shelters 2NSB Naples, IT (approx. 231 WS) |  |  |  |  |
| 11.17.01 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.17.02 | Network Integration Test |  |  |  |  |
| 11.17.03 | Site Acceptance |  |  |  |  |
| 11.17.04 | 1st year warranty |  |  |  |  |
| 11.18 | Site Y: DCM/DCIS Shelters JFC Brunssum, NL (approx. 231 WS) |  |  |  |  |
| 11.18.01 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.18.02 | Network Integration Test |  |  |  |  |
| 11.18.03 | Site Acceptance |  |  |  |  |
| 11.18.04 | 1st year warranty |  |  |  |  |
| 11.19 | Site Z: NATO Defence Staff College, IT (approx. 174 WS) |  |  |  |  |
| 11.19.01 | Training sessions for users, system admin and INFOSEC |  |  |  |  |
| 11.19.02 | Physical Installation at the network per implementation plan |  |  |  |  |
| 11.19.03 | Network Integration Test |  |  |  |  |
| 11.19.04 | Site Acceptance |  |  |  |  |
| 11.19.05 | 1st year warranty |  |  |  |  |
| PART V – OPTIONAL: ADDITIONAL WARRANTY COVERAGE |  |  |  |  |  |
| 12.00 | Additional warranty coverage for CLINs 4 to 5 (Sites A to F) |  |  |  |  |
| 12.01 | 2nd year warranty |  |  |  |  |
| 12.02 | 3rd year warranty |  |  |  |  |
| 13.00 | Additional warranty coverage for CLINs 11.01 to 11.19 (Sites G to Z) |  |  |  |  |
| 13.01 | Additional warranty coverage for CLIN 11.01 (Site G) |  |  |  |  |
| 13.01.01 | 2nd year warranty |  |  |  |  |
| 13.01.02 | 3rd year warranty |  |  |  |  |
| 13.02 | Additional warranty coverage for CLIN 11.02 (Site H) |  |  |  |  |
| 13.02.01 | 2nd year warranty |  |  |  |  |
| 13.02.02 | 3rd year warranty |  |  |  |  |
| 13.03 | Additional warranty coverage for CLIN 11.03 (Site I) |  |  |  |  |
| 13.03.01 | 2nd year warranty |  |  |  |  |
| 13.03.02 | 3rd year warranty |  |  |  |  |
| 13.04 | Additional warranty coverage for CLIN 11.04 (Site J) |  |  |  |  |
| 13.04.01 | 2nd year warranty |  |  |  |  |
| 13.04.02 | 3rd year warranty |  |  |  |  |
| 13.05 | Additional warranty coverage for CLIN 11.05 (Site K) |  |  |  |  |
| 13.05.01 | 2nd year warranty |  |  |  |  |
| 13.05.02 | 3rd year warranty |  |  |  |  |
| 13.06 | Additional warranty coverage for CLIN 11.06 (Site L) |  |  |  |  |
| 13.06.01 | 2nd year warranty |  |  |  |  |
| 13.06.02 | 3rd year warranty |  |  |  |  |
| 13.07 | Additional warranty coverage for CLIN 11.07 (Site M) |  |  |  |  |
| 13.07.01 | 2nd year warranty |  |  |  |  |
| 13.07.02 | 3rd year warranty |  |  |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION | Delivery dates according to the RFQ Weeks from EDC (*) | Delivery Dates proposed by the Bidder Weeks from EDC (*) | Compliance |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Y | N |
| 13.08 | Additional warranty coverage for CLIN 11.08 (Site N) |  |  |  |  |
| 13.08.01 | 2nd year warranty |  |  |  |  |
| 13.08.02 | 3rd year warranty |  |  |  |  |
| 13.09 | Additional warranty coverage for CLIN 11.09 (Site O) |  |  |  |  |
| 13.09.01 | 2nd year warranty |  |  |  |  |
| 13.09.02 | 3rd year warranty |  |  |  |  |
| 13.10 | Additional warranty coverage for CLIN 11.10 (Site P) |  |  |  |  |
| 13.10.01 | 2nd year warranty |  |  |  |  |
| 13.10.02 | 3rd year warranty |  |  |  |  |
| 13.11 | Additional warranty coverage for CLIN 11.11 (Site R) |  |  |  |  |
| 13.11.01 | 2nd year warranty |  |  |  |  |
| 13.11.02 | 3rd year warranty |  |  |  |  |
| 13.12 | Additional warranty coverage for CLIN 11.12 (Site S) |  |  |  |  |
| 13.12.01 | 2nd year warranty |  |  |  |  |
| 13.12.02 | 3rd year warranty |  |  |  |  |
| 13.13 | Additional warranty coverage for CLIN 11.13 (Site T) |  |  |  |  |
| 13.13.01 | 2nd year warranty |  |  |  |  |
| 13.13.02 | 3rd year warranty |  |  |  |  |
| 13.14 | Additional warranty coverage for CLIN 11.14 (Site U) |  |  |  |  |
| 13.14.01 | 2nd year warranty |  |  |  |  |
| 13.14.02 | 3rd year warranty |  |  |  |  |
| 13.15 | Additional warranty coverage for CLIN 11.15 (Site V) |  |  |  |  |
| 13.15.01 | 2nd year warranty |  |  |  |  |
| 13.15.02 | 3rd year warranty |  |  |  |  |
| 13.16 | Additional warranty coverage for CLIN 11.16 (Site W) |  |  |  |  |
| 13.16.01 | 2nd year warranty |  |  |  |  |
| 13.16.02 | 3rd year warranty |  |  |  |  |
| 13.17 | Additional warranty coverage for CLIN 11.17 (Site X) |  |  |  |  |
| 13.17.01 | 2nd year warranty |  |  |  |  |
| 13.17.02 | 3rd year warranty |  |  |  |  |
| 13.18 | Additional warranty coverage for CLIN 11.18 (Site Y) |  |  |  |  |
| 13.18.01 | 2nd year warranty |  |  |  |  |
| 13.18.02 | 3rd year warranty |  |  |  |  |
| 13.19 | Additional warranty coverage for CLIN 11.19 (Site Z) |  |  |  |  |
| 13.19.01 | 2nd year warranty |  |  |  |  |
| 13.19.02 | 3rd year warranty |  |  |  |  |
|  | * EDC - Effective Date of the Contract |  |  |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

ANNEX B1-2

Comprehension and Acceptance of

CONTRACT SPECIAL AND GENERAL PROVISIONS

The Bidder hereby certifies that he has reviewed the Special Contract Provisions set forth in the Prospective Contract and the NC3O General Provisions from his BOA with NC3A, of this Request For Quotation. The Bidder hereby provides his confirmation that he fully comprehends the rights, obligations and responsibilities of the Contractor as set forth in the Articles and Clauses of the Prospective Contract. The Bidder additionally certifies that the bid submitted by the Bidder is without prejudice, qualification or exception to any of the Terms and Conditions and he will accept and abide by the stated Special and General Provisions if awarded the contract as a result of this Request For Quotation.

| …................................................. Date | …............................................................. Signature of Authorised Representative |
| --- | --- |
|  | …............................................................. Title |
|  | …............................................................. Company |

THIS PAGE IS INTENTIONALLY LEFT BLANK

ANNEX B1-3

CERTIFICATE OF BID VALIDITY

I, the undersigned, as an authorised representative of the firm submitting this bid, do hereby certify that the pricing and all other aspects of our Bid will remain valid for a period of six (6) months from the Bid Closing Date of this Request For Quotation.

| …................................................. Date | …............................................................. Signature of Authorised Representative |
| --- | --- |
|  | …............................................................. Title |
|  | …............................................................. Company |

THIS PAGE IS INTENTIONALLY LEFT BLANK

ANNEX B1-4

CERTIFICATE OF EXCLUSION OF TAXES, DUTIES AND CHARGES

I hereby certify that the prices offered in the price quotation of this bid exclude all taxes, duties and customs charges from which the Purchaser has been exempted by international agreement.

| …................................................. Date | …............................................................. Signature of Authorised Representative |
| --- | --- |
|  | …............................................................. Title |
|  | …............................................................. Company |

THIS PAGE IS INTENTIONALLY LEFT BLANK

ANNEX B1-5

CERTIFICATE OF UNDERSTANDING

I certify that

....................................................................................................................................................................

....................................................................................................................................................................

[Company full name and address]

Company has read and fully understands the requirements of this Request For Quotation (RFQ) and that the bid recognises these requirements in total.

I also certify to the best of my expert knowledge that this bid is within the "state of art" boundaries as they exist at the time of bidding for this project.

| …................................................. Date | …............................................................. Signature of Authorised Representative |
| --- | --- |
|  | …............................................................. Title |
|  | …............................................................. Company |

THIS PAGE IS INTENTIONALLY LEFT BLANK

ANNEX B1-6

VERIFICATION OF EAL 2 CERTIFICATION

The Bidder hereby certifies that the product that is being offered has received Common Criteria Evaluation Assurance Level (EAL) 2 certification or a NATO recognised National COMSEC Authority Equivalent.

| …................................................. Date | …............................................................. Signature of Authorised Representative |
| --- | --- |
|  | …............................................................. Title |
|  | …............................................................. Company |

THIS PAGE IS INTENTIONALLY LEFT BLANK

ANNEX B1-7

LIST OF ALL PROSPECTIVE SUBCONTRACTORS AND MAJOR VENDORS

| Name and Address of Sub-Contractor | Primary Location of Work | Items/Services to be Provided | Estimated Amount of Sub-Contract |
| --- | --- | --- | --- |

THIS PAGE IS INTENTIONALLY LEFT BLANK

ANNEX B1-8

SPECIFICATION COMPLIANCE

| CLIN | DESCRIPTION | Quantity | Specification Compliance |  |
| --- | --- | --- | --- | --- |
|  |  |  | Y | N |
| PART I: PRODUCT ACCEPTANCE |  |  |  |  |
| 1.00 | Documentation - Project Management Plan (PMP) |  |  |  |
| 1.01 | Project Implementation Plan (PIP) | 1 |  |  |
| 1.02 | Network Integration Test Procedures and Scenarios | 7 |  |  |
| 1.03 | Product Acceptance Test Procedures | 1 |  |  |
| 2.00 | Meetings |  |  |  |
| 2.01 | Project Progress Review Meeting (PPRM) including minutes | 3 |  |  |
| 2.02 | Product Profile meetings | 6 |  |  |
| 3.00 | Product Acceptance - NCSA Test Site |  |  |  |
| 3.01 | Physical Installation on the test site | 1 |  |  |
| 3.02 | Product Acceptance Test | 1 |  |  |
| 3.03 | Product Acceptance | 1 |  |  |
| PART II: SOFTWARE PROCUREMENT, INSTALLATION & TRAINING FOR SIX (6) REGIONAL COMMANDS |  |  |  |  |
| 4.00 | Software |  |  |  |
| 4.01 | Software license per seat | 16,705 |  |  |
| 4.02 | 1-Year Maintenance for 4.01 | 16,705 |  |  |
| 4.03 | Software license on installation server | 60 |  |  |
| 4.04 | 1-Year Maintenance for 4.03 | 60 |  |  |
| 4.05 | Installation Media CD | 81 |  |  |
| 4.06 | Software Documentation | 81 |  |  |
| 5.00 | Installation - NATO Sites |  |  |  |
| 5.01 | Site A: SHAPE, NCSA, NITC, BE (approx. 3966 WS) |  |  |  |
| 5.01.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 5.01.02 | Physical Installation at the network per implementation plan | 3 |  |  |
| 5.01.03 | Network Integration Test | 3 |  |  |
| 5.01.04 | Site Acceptance | 1 |  |  |
| 5.02 | Site B: JFC Naples, IT (approx. 1844 WS) |  |  |  |
| 5.02.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 5.02.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 5.02.03 | Network Integration Test | 2 |  |  |
| 5.02.04 | Site Acceptance | 1 |  |  |
| 5.03 | Site C: JFC Brunssum, NL (approx. 1535 WS) |  |  |  |
| 5.03.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 5.03.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 5.03.03 | Network Integration Test | 2 |  |  |
| 5.03.04 | Site Acceptance | 1 |  |  |
| 5.04 | Site D: CC Mar Northwood, UK (approx. 589 WS) |  |  |  |
| 5.04.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 5.04.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 5.04.03 | Network Integration Test | 2 |  |  |
| 5.04.04 | Site Acceptance | 1 |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION | Quantity | Specifications Compliance |  |
| --- | --- | --- | --- | --- |
|  |  |  | Y | N |
| 5.05 | Site E: JHQ Lisbon, PO (approx. 618 WS) |  |  |  |
| 5.05.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 5.05.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 5.05.03 | Network Integration Test | 2 |  |  |
| 5.05.04 | Site Acceptance | 1 |  |  |
| 5.06 | Site F: SACT HQ, US (approx. 1132 WS) |  |  |  |
| 5.06.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 5.06.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 5.06.03 | Network Integration Test | 2 |  |  |
| 5.06.04 | Site Acceptance | 1 |  |  |
| 6.00 | NATO Specific User Information Brochure |  |  |  |
| 6.01 | NATO-specific User Information Brochure | 20 |  |  |
| 7.00 | Final System Acceptance |  |  |  |
| 7.01 | FSA conduct, report and meeting | 1 |  |  |
| 8.00 | HelpDesk Support |  |  |  |
| 8.01 | HelpDesk Support | 1 |  |  |
| 8.02 | Help Desk Support | 1 |  |  |
| 9.00 | Warranty |  |  |  |
| 9.01 | 1-year warranty coverage for the CLINS 4 to 5 | 1 |  |  |
| OPTIONS |  |  |  |  |
| PART III - OPTIONAL: SOFTWARE PROCUREMENT |  |  |  |  |
| 10.00 | Additional licenses + applicable discount scheme (Annex B1-9) |  |  |  |
| 10.01 | Software license per seat | 15,000 |  |  |
| 10.02 | 1-Year Maintenance for 10.01 | 15,000 |  |  |
| 10.03 | Software license on installation server | 40 |  |  |
| 10.04 | 1-Year Maintenance for 10.03 | 40 |  |  |
| 10.05 | Installation Media CD | 40 |  |  |
| 10.06 | 2nd year Maintenance for 10.01 and 4.01 | 16705+15000 |  |  |
| 10.07 | 3rd year Maintenance for 10.01 and 4.01 | 16705+15000 |  |  |
| 10.08 | 2nd year Maintenance for 10.03 and 4.03 | 60+40 |  |  |
| 10.09 | 3rd year Maintenance for 10.03 and 4.03 | 60+40 |  |  |
| PART IV - OPTIONAL: INSTALLATION & TRAINING FOR NINETEEN (19) REGIONAL COMMANDS |  |  |  |  |
| 11.00 | Installation - NATO Sites |  |  |  |
| 11.01 | Site G: CC Air Izmir, TU (approx. 1295 WS) |  |  |  |
| 11.01.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.01.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.01.03 | Network Integration Test | 2 |  |  |
| 11.01.04 | Site Acceptance | 1 |  |  |
| 11.01.05 | 1st year warranty | 1 |  |  |
| 11.02 | Site H: CC Land Madrid, SP (approx. 462 WS) |  |  |  |
| 11.02.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.02.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.02.03 | Network Integration Test | 2 |  |  |
| 11.02.04 | Site Acceptance | 1 |  |  |
| 11.02.05 | 1st year warranty | 1 |  |  |
| 11.03 | Site I: CC Mar Naples, IT (approx. 320 WS) |  |  |  |
| 11.03.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.03.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.03.03 | Network Integration Test | 2 |  |  |
| 11.03.04 | Site Acceptance | 1 |  |  |
| 11.03.05 | 1st year warranty | 1 |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION | Quantity | Specifications Compliance |  |
| --- | --- | --- | --- | --- |
|  |  |  | Y | N |
| 11.04 | Site J: CC Air Ramstein, GE (approx. 1145 WS) |  |  |  |
| 11.04.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.04.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.04.03 | Network Integration Test | 2 |  |  |
| 11.04.04 | Site Acceptance | 1 |  |  |
| 11.04.05 | 1st year warranty | 1 |  |  |
| 11.05 | Site K: Land Heidelberg, GE (approx. 798 WS) |  |  |  |
| 11.05.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.05.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.05.03 | Network Integration Test | 2 |  |  |
| 11.05.04 | Site Acceptance | 1 |  |  |
| 11.05.05 | 1st year warranty | 1 |  |  |
| 11.06 | Site L: Comms Squadron Karup, DE (approx. 79 WS) |  |  |  |
| 11.05.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.05.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.05.03 | Network Integration Test | 2 |  |  |
| 11.05.04 | Site Acceptance | 1 |  |  |
| 11.06.05 | 1st year warranty | 1 |  |  |
| 11.07 | Site M: Comms Group Larissa, GR (approx. 213 WS) |  |  |  |
| 11.07.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.07.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.07.03 | Network Integration Test | 2 |  |  |
| 11.07.04 | Site Acceptance | 1 |  |  |
| 11.07.05 | 1st year warranty | 1 |  |  |
| 11.08 | Site N: Comms Squadron Verona, IT (approx. 298 WS) |  |  |  |
| 11.08.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.08.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.08.03 | Network Integration Test | 2 |  |  |
| 11.08.04 | Site Acceptance | 1 |  |  |
| 11.08.05 | 1st year warranty | 1 |  |  |
| 11.09 | Site O: JWC, NO (approx. 548 WS) |  |  |  |
| 11.09.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.09.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.09.03 | Network Integration Test | 2 |  |  |
| 11.09.04 | Site Acceptance | 1 |  |  |
| 11.09.05 | 1st year warranty | 1 |  |  |
| 11.10 | Site P: JFTC, PL (approx. 92 WS) |  |  |  |
| 11.10.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.10.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.10.03 | Network Integration Test | 2 |  |  |
| 11.10.04 | Site Acceptance | 1 |  |  |
| 11.10.05 | 1st year warranty | 1 |  |  |
| 11.11 | Site R: JALLC, PO (approx. 117 WS) |  |  |  |
| 11.11.01 | Training sessions for users, system admin and INFOSEC | 1 |  |  |
| 11.11.02 | Physical Installation at the network per implementation plan | 2 |  |  |
| 11.11.03 | Network Integration Test | 2 |  |  |
| 11.11.04 | Site Acceptance | 1 |  |  |
| 11.11.05 | 1st year warranty | 1 |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION |  | Quantity |  | Specifications Compliance |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Y |  | N |
| 11.12 |  | Site S: NCISS, IT (approx. 118 WS) |  |  |  |  |  |
| 11.12.01 |  | Training sessions for users, system admin and INFOSEC |  | 1 |  |  |  |
| 11.12.01 |  | Physical Installation at the network per implementation plan |  | 2 |  |  |  |
| 11.12.01 |  | Network Integration Test |  | 2 |  |  |  |
| 11.12.01 |  | Site Acceptance |  | 1 |  |  |  |
| 11.12.05 |  | 1st year warranty |  | 1 |  |  |  |
| 11.13 |  | Site T: NATO School, GE (approx. 78 WS) |  |  |  |  |  |
| 11.13.01 |  | Training sessions for users, system admin and INFOSEC |  | 1 |  |  |  |
| 11.13.02 |  | Physical Installation at the network per implementation plan |  | 2 |  |  |  |
| 11.13.03 |  | Network Integration Test |  | 2 |  |  |  |
| 11.13.04 |  | Site Acceptance |  | 1 |  |  |  |
| 11.13.05 |  | 1st year warranty |  | 1 |  |  |  |
| 11.14 |  | Site U: Undersea Research Centre, IT (approx. 385 WS) |  |  |  |  |  |
| 11.14.01 |  | Training sessions for users, system admin and INFOSEC |  | 1 |  |  |  |
| 11.14.02 |  | Physical Installation at the network per implementation plan |  | 2 |  |  |  |
| 11.14.03 |  | Network Integration Test |  | 2 |  |  |  |
| 11.14.04 |  | Site Acceptance |  | 1 |  |  |  |
| 11.14.05 |  | 1st year warranty |  | 1 |  |  |  |
| 11.15 |  | Site V: PCC, BE (approx. 60 WS) |  |  |  |  |  |
| 11.15.01 |  | Training sessions for users, system admin and INFOSEC |  | 1 |  |  |  |
| 11.15.02 |  | Physical Installation at the network per implementation plan |  | 2 |  |  |  |
| 11.15.03 |  | Network Integration Test |  | 2 |  |  |  |
| 11.15.04 |  | Site Acceptance |  | 1 |  |  |  |
| 11.15.05 |  | 1st year warranty |  | 1 |  |  |  |
| 11.16 |  | Site W: NPC, BE (approx. 245 WS) |  |  |  |  |  |
| 11.16.01 |  | Training sessions for users, system admin and INFOSEC |  | 1 |  |  |  |
| 11.16.02 |  | Physical Installation at the network per implementation plan |  | 2 |  |  |  |
| 11.16.03 |  | Network Integration Test |  | 2 |  |  |  |
| 11.16.04 |  | Site Acceptance |  | 1 |  |  |  |
| 11.16.05 |  | 1st year warranty |  | 1 |  |  |  |
| 11.17 |  | Site X: DCM/DCIS Shelters 2NSB Naples, IT (approx. 231 WS) |  |  |  |  |  |
| 11.17.01 |  | Physical Installation at the network per implementation plan |  | 3 |  |  |  |
| 11.17.02 |  | Network Integration Test |  | 3 |  |  |  |
| 11.17.03 |  | Site Acceptance |  | 1 |  |  |  |
| 11.17.04 |  | 1st year warranty |  | 1 |  |  |  |
| 11.18 |  | Site Y: DCM/DCIS Shelters JFC Brunssum, NL (approx. 231 WS) |  |  |  |  |  |
| 11.18.01 |  | Physical Installation at the network per implementation plan |  | 3 |  |  |  |
| 11.18.02 |  | Network Integration Test |  | 3 |  |  |  |
| 11.18.03 |  | Site Acceptance |  | 1 |  |  |  |
| 11.18.04 |  | 1st year warranty |  | 1 |  |  |  |
| 11.19 |  | Site Z: NATO Defence Staff College, IT (approx. 174 WS) |  |  |  |  |  |
| 11.19.01 |  | Training sessions for users, system admin and INFOSEC |  | 1 |  |  |  |
| 11.19.02 |  | Physical Installation at the network per implementation plan |  | 2 |  |  |  |
| 11.19.03 |  | Network Integration Test |  | 2 |  |  |  |
| 11.19.04 |  | Site Acceptance |  | 1 |  |  |  |
| 11.19.05 |  | 1st year warranty |  | 1 |  |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION |  | Quantity |  | Specifications Compliance |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Y |  | N |
| PART V - OPTIONAL: ADDITIONAL WATRRANTY COVERAGE |  |  |  |  |  |  |  |
| 12.00 |  | Additional warranty coverage for CLINs 4 to 5 (Sites A to F) |  |  |  |  |  |
| 12.01 |  | 2nd year warranty |  |  |  |  |  |
| 12.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.00 |  | Additional warranty coverage for CLINs 11.01 to 11.19 (Sites G to Z) |  |  |  |  |  |
| 13.01 |  | Additional warranty coverage for CLIN 11.01 (Site G) |  |  |  |  |  |
| 13.01.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.01.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.02 |  | Additional warranty coverage for CLIN 11.02 (Site H) |  |  |  |  |  |
| 13.02.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.02.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.03 |  | Additional warranty coverage for CLIN 11.03 (Site I) |  |  |  |  |  |
| 13.03.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.03.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.04 |  | Additional warranty coverage for CLIN 11.04 (Site J) |  |  |  |  |  |
| 13.04.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.04.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.05 |  | Additional warranty coverage for CLIN 11.05 (Site K) |  |  |  |  |  |
| 13.05.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.05.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.06 |  | Additional warranty coverage for CLIN 11.06 (Site L) |  |  |  |  |  |
| 13.06.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.06.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.07 |  | Additional warranty coverage for CLIN 11.07 (Site M) |  |  |  |  |  |
| 13.07.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.07.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.08 |  | Additional warranty coverage for CLIN 11.08 (Site N) |  |  |  |  |  |
| 13.08.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.08.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.09 |  | Additional warranty coverage for CLIN 11.09 (Site O) |  |  |  |  |  |
| 13.09.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.09.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.10 |  | Additional warranty coverage for CLIN 11.10 (Site P) |  |  |  |  |  |
| 13.10.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.10.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.11 |  | Additional warranty coverage for CLIN 11.11 (Site R) |  |  |  |  |  |
| 13.10.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.10.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.12 |  | Additional warranty coverage for CLIN 11.12 (Site S) |  |  |  |  |  |
| 13.10.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.10.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.13 |  | Additional warranty coverage for CLIN 11.13 (Site T) |  |  |  |  |  |
| 13.10.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.10.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.14 |  | Additional warranty coverage for CLIN 11.14 (Site U) |  |  |  |  |  |
| 13.14.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.14.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.15 |  | Additional warranty coverage for CLIN 11.15 (Site V) |  |  |  |  |  |
| 13.15.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.15.02 |  | 3rd year warranty |  |  |  |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

| CLIN | DESCRIPTION |  | Quantity |  | Specifications Compliance |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Y |  | N |
| 13.16 |  | Additional warranty coverage for CLIN 11.16 (Site W) |  |  |  |  |  |
| 13.16.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.16.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.17 |  | Additional warranty coverage for CLIN 11.17 (Site X) |  |  |  |  |  |
| 13.17.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.17.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.18 |  | Additional warranty coverage for CLIN 11.18 (Site Y) |  |  |  |  |  |
| 13.18.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.18.02 |  | 3rd year warranty |  |  |  |  |  |
| 13.19 |  | Additional warranty coverage for CLIN 11.19 (Site Z) |  |  |  |  |  |
| 13.19.01 |  | 2nd year warranty |  |  |  |  |  |
| 13.19.02 |  | 3rd year warranty |  |  |  |  |  |
|  |  | * EDC - Effective Date of the Contract |  |  |  |  |  |

THIS PAGE IS INTENTIONALLY LEFT BLANK

ANNEX B1-9

NC3A INVENTORY ON SOFTWARE ASSETS

PLEASE SEE SEPARATE EXCEL SPREADSHEETS

THIS PAGE IS INTENTIONALLY LEFT BLANK