## Funding Status (hidden)
FUNDING STATUS
21st Space Wing
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
39.13%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
76 SCS
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
4.35%
0 | #VALUE! | #VALUE! | #VALUE!
#REF! | % Expended to date
MAJCOM
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
56.52%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
PMO
Funding | Cost Variance
0 | #VALUE!
#REF! | % Expended to date
TOTALS
Funding | Cost Variance |  | Total Contract Under/Overrun
0 | #REF! |  | #REF!
#REF! | % Expended to date

## Status Report
MONTHLY PROGRAM STATUS REPORT | [5 empty] | As of Period Ending: | 2007-06-29
Program Name: |  | SAR Implementation and Support | [5 empty] | Month Revenue | 130974.18 |  | YTD Revenue |  | 503810.84
Program Manager: |  | Lindy Martin | [5 empty] | Month Costs | 102824.48 |  | YTD Costs |  | 398485.04
Customer: |  | NAMSA | [5 empty] | Month Profit | 27.38% |  | YTD Profit |  | 26.43%
Contract Type: |  | T&M |  | PeopleSoft Contract No.: |  | 23063
Contract Period of Performance: |  |  | 8/16/05 - 09/30/07 |  |  |  |  | CTD Revenue | 1411795 |  | EAC (Act + Frcst) (Sales) |  | 1681514.45
Total Contract Value: |  | 1936755.69 |  | Total Contract Funding: |  | 1936756 |  | CTD Costs | 1232846 |  | CAC (Act + Frcst) (Costs) |  | 1408184.46
[8 empty] | CTD Profit | 14.52%
Contract Period of Performance: |  |  | 8/16/05 - 09/30/07 | [8 empty] | Funding Status: | 0
Total Contract Value: |  | 1936756 |  | Total Contract Funding: |  | 1936756 |  | Remaining Funding: | 524961 |  |  |  | Current | Previous
[8 empty] | % Funding Spent | 72.89% |  |  | Variance at Complete: | 255.2415 | 152.2
Program's Description: |  |  | Contract No. LR-RBG/4600001202
ManTech provides 4 CISCO Technicians (Wade/Manning/Becker/Hemberg) to support SHAPE's Network Control Center.
ACCOMPLISHMENTS (Last 30 Days) | [7 empty] | CONTRACT ACTIVITY
[8 empty] | Risk Memo - | N/A
75% Notification -
[8 empty] | Export Compliance - | N/A
PROGRAM ISSUES & POTENTIAL ISSUES | [7 empty] | ACTION PLANS
|  | N/A | [7 empty] | N/A
INVESTMENT STATUS | [7 empty] | Reviewed by: |  |  |  | Program Mgr
1) | Unbilled Sales: |  | 89953.3 |  | 23K accruals; 78.7K WIP
2) | Receivables +60: |  | 521.32 |  | Discount cleared by Cash Mgmt | [6 empty] | Finance Mgr
3) | Other:
Contracts Mgr

## GRAPHs
MPSR for SAR Implementation and Support
Open Reqs:_________
| 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 |  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01
BAC | 2007-01-01: 1505.57; 2007-02-01: 1735.458; 2007-03-01: 1735.458 | PLAN | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
EAC | 2007-01-01: 1490.949; 2007-02-01: 1595.373; 2007-03-01: 1583.277 | ManTech FTE | 2.77 | 1.95 | 1.36 | 0 | 0 | 0 | 0 | 0
VAC | 14.621 | 140.085 | 152.181 | 0 | 0 | 0 | 0 | 0 |  | *1 subcontractor & 3 ManTech Employees
Funding | 2007-01-01: 1505.57; 2007-02-01: 1735.458; 2007-03-01: 1735.458

## Graph Data
LABOR | (Direct Labor only)
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Cost of Sales |  | 37162.84 | 32317.62 | 22443.37 | 41494.48 | 50015 | 76848 | 26586.53 | 20503.87 | 26586.53 | 26586.53 |  |  | 360544.77
Total Sales |  | 43581.73 | 36749.12 | 38797.34 | 60782.99 | 75716 | 104314 | 49288.2 | 38053.6 | 49288.2 | 43256.85 |  |  | 539828.03
Total Fee |  | 6418.89 | 4431.5 | 16353.97 | 19288.51 | 25701 | 27466 | 22701.67 | 17549.73 | 22701.67 | 16670.32 | 0 | 0 | 179283.26
Total Profit Rate |  | 17.27% | 13.71% | 72.87% | 46.48% | 51.39% | 35.74% | 85.39% | 85.59% | 85.39% | 62.7% | #DIV/0! | #DIV/0! | 49.73%
ODC
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Subcontractor Costs |  | 13745.16 | 25394.07 | 22306.69 | 28571.2 | 22210.13 | 25976.48 | 20475 | 13650 | 20475 | 20475 | 20475 | 20475 | 254228.73
Total Subcontractor Labor Sales |  | 16119.27 | 26067.4 | 22894.92 | 29331.08 | 22796.81 | 26660.18 | 24499.8 | 16333.2 | 24499.8 | 24499.8 | 24499.8 | 24499.8 | 282701.86
Total Travel Sales |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total | Actuals | ETC
Total Revenue |  | 59701 | 62816.52 | 61692.26 | 90114.07 | 98512.81 | 130974.18 | 73788 | 54386.8 | 73788 | 67756.65 | 24499.8 | 24499.8 | 822529.89 | 503810.84 | 269719.45
Total Costs |  | 50908 | 57711.69 | 44750.06 | 70065.68 | 72225.13 | 102824.48 | 47061.53 | 34153.87 | 47061.53 | 47061.53 | 20475 | 20475 | 614773.5 | 398485.04 | 175338.46
Total Profit |  | 8793 | 5104.83 | 16942.2 | 20048.39 | 26287.68 | 28149.7 | 26726.47 | 20232.93 | 26726.47 | 20695.12 | 4024.8 | 4024.8 | 207756.39 | 105325.8 | 94380.99
Total Profit % |  | 17.27% | 8.845% | 37.86% | 28.61% | 36.4% | 27.38% | 56.79% | 59.24% | 56.79% | 43.97% | 19.66% | 19.66% | 33.79% | 26.43% | 53.83%