## Funding Status (hidden)
FUNDING STATUS
21st Space Wing
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
39.13%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
76 SCS
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
4.35%
0 | #VALUE! | #VALUE! | #VALUE!
#REF! | % Expended to date
MAJCOM
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
56.52%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
PMO
Funding | Cost Variance
0 | #VALUE!
#REF! | % Expended to date
TOTALS
Funding | Cost Variance |  | Total Contract Under/Overrun
0 | #REF! |  | #REF!
#REF! | % Expended to date

## Status Report
MONTHLY PROGRAM STATUS REPORT | [5 empty] | As of Period Ending: | 2007-06-29
Program Name: |  | NTM-I | [5 empty] | Month Revenue |  | 354081 |  | YTD Revenue |  | 1875324
Program Manager: |  | Ron Vanleishout | [5 empty] | Month Costs |  | 254494 |  | YTD Costs |  | 1225230
Customer: |  | NAMSA | [5 empty] | Month Profit |  | 39.13% |  | YTD Profit |  | 53.06%
Contract Type: |  | FP |  | PeopleSoft Contract No.: |  | 23539
Contract Period of Performance: |  |  | 10/01/06 - 09/30/09 |  |  |  |  | CTD Revenue |  | 2552092 |  | EAC (Act + Frcst) (Sales) |  | 3324600
Total Contract Value: |  | 12956270 |  | Total Contract Funding: |  | 4106340 |  | CTD Costs |  | 1953426 |  | CAC (Act + Frcst) (Costs) |  | 2603426
Phase III Year 1: | [7 empty] | CTD Profit |  | 30.65%
Contract Period of Performance: |  |  | 02/08/07 - 11/07/07 | [9 empty] | Funding Status: | 0
Total Contract Value: |  | 3324600 |  | Total Contract Funding: |  | 3324600 |  | Remaining Funding: |  | 772508 |  |  |  | Current | Previous
[8 empty] | % Funding Spent |  | 76.76% |  |  | Variance at Complete: | 0 | 0
Program's Description: |  |  | Contract No. 4600001334
ManTech provides full operations and maintenance (O&M) of the NTM-I automated data processing (ADP) systems and communication systems.
ACCOMPLISHMENTS (Last 30 Days) | [7 empty] | CONTRACT ACTIVITY
The project is currently in Phase III, Normal Operations, as of April 2007. | [7 empty] | Prepared correspondence letter and required backup documentation to the Iraq residency department
Four positive SLA Reports have issued and accepted by NAMSA to date . | [7 empty] | in response to the new country visa requirements.
Clint Barnes as of 07/28/07 will be a MCCS Employee, taking on the Project Director Role replacing | [7 empty] | Received revised SOW 1.2.1 to add Camp Dublin as another site in Iraq for ManTech to support. Prepared and
Mr. Guidry. | [7 empty] | submitted the associated pricing.
Mr. Kelley , MCCS President, has received multiple letters from in theater officers complementing | [7 empty] | Received letter from Col. Alan Brown concerning the problems ManTech is having moving in and out of country.
the ManTech NTM-I Teams performance. | [7 empty] | J Kelly submitted response confirming the importance of the issue and informing NATO of our efforts to resolve
the problem.
Employee turnover remains the projects largest incremental expense.
NAMSA has issued a revised SOW for Camp Dublin, which ManTech responded to.
The SOW revisions have since been withdrawn as NAMSA is still establishing the the real
requirements.
[8 empty] | Risk Memo - |  | N/A
[8 empty] | 75% Notification - |  | N/A
[8 empty] | Export Compliance - |  | Yes | DSP73, License # 730000980 - 14 Sets of Body Armor
DSP73, License # 730001752 - 2 Sets of Body Armor for Management Visit
DSP73, License # 730002063 - 20 Gas Masks
DSP5, License #050042365 - 1 set of undeclared body Armor
PROGRAM ISSUES & POTENTIAL ISSUES | [7 empty] | ACTION PLANS
Theater access issues still plague the team. The inability to obtain CAC cards issued by the US is | [8 empty] | Both ManTech and NATO are reaching out to the highest levels of the DOD to obtain a new CAC
biggest challenge of the project. | [8 empty] | card policy which addresses NATO personnel operating in a US controlled environment.
INVESTMENT STATUS | [7 empty] | Reviewed by: |  |  |  |  | Program Mgr
1) | Unbilled Sales: |  | 256449.8 |  | WIP
2) | Receivables +60: |  | 369400 |  | Paid on 7/20/07 | [7 empty] | Finance Mgr
3) | Other:
Contracts Mgr

## GRAPHs
MPSR for NTM-I
Open Reqs:_________
| 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 |  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01
BAC |  | 3324600 | 3324600 | 3324600 | 3324600 | 3324600 |  |  | Budget | 5 | 5 | 6 | 6 | 6 | 6
EAC |  | 3324600 | 3324600 | 3324600 | 3324600 | 3324600 |  |  | Actual | 5 | 5 | 6 | 6.7 | 7.9 | 7.79
VAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding |  | 3324600 | 3324600 | 3324600 | 3324600 | 3324600

## Graph Data
LABOR | (Direct Labor only)
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Cost of Sales |  |  | 218167 | 219814 | 178834 | 231099 | 251281 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 1897195
Total Sales |  |  | 197767 | 362224 | 327021 | 500561 | 349659 | 158000 | 158000 | 158000 | 158000 | 158000 | 158000 | 2685232
Total Fee |  | 0 | -20400 | 142410 | 148187 | 269462 | 98378 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 788037
Total Profit Rate |  | #DIV/0! | -9.351% | 64.79% | 82.86% | 116.6% | 39.15% | 18.8% | 18.8% | 18.8% | 18.8% | 18.8% | 18.8% | 41.54%
ODC
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Subcontractor Costs |  | 2007-02-01: 11721; 2007-03-01: 6468; 2007-04-01: 40708; 2007-05-01: 63925; 2007-06-01: 3213 | 126035
Total Subcontractor Labor Sales |  | 2007-02-01: 13114; 2007-03-01: 7176; 2007-04-01: 42379; 2007-05-01: 71001; 2007-06-01: 4422 | 138092
Total Travel Sales |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total | Actuals | ETC
Total Revenue |  | 0 | 210881 | 369400 | 369400 | 571562 | 354081 | 158000 | 158000 | 158000 | 158000 | 158000 | 158000 | 2823324 | 1875324 | 772508
Total Costs |  | 0 | 229888 | 226282 | 219542 | 295024 | 254494 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 2023230 | 1225230 | 650000
Total Profit |  | 0 | -19007 | 143118 | 149858 | 276538 | 99587 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 800094 | 650094 | 122508
Total Profit % |  | #DIV/0! | -8.268% | 63.25% | 68.26% | 93.73% | 39.13% | 18.8% | 18.8% | 18.8% | 18.8% | 18.8% | 18.8% | 39.55% | 53.06% | 18.85%