## Funding Status (hidden)
FUNDING STATUS
21st Space Wing
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
39.13%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
76 SCS
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
4.35%
0 | #VALUE! | #VALUE! | #VALUE!
#REF! | % Expended to date
MAJCOM
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
56.52%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
PMO
Funding | Cost Variance
0 | #VALUE!
#REF! | % Expended to date
TOTALS
Funding | Cost Variance |  | Total Contract Under/Overrun
0 | #REF! |  | #REF!
#REF! | % Expended to date

## Status Report
MONTHLY PROGRAM STATUS REPORT | [5 empty] | As of Period Ending: | 2007-06-29
Program Name: |  | NTM-I | [5 empty] | Month Revenue | 354081 |  | YTD Revenue |  | 2038221.91
Program Manager: |  | Ron Vanleishout | [5 empty] | Month Costs | 254494 |  | YTD Costs |  | 1523129.01
Customer: |  | NAMSA | [5 empty] | Month Profit | 39.13% |  | YTD Profit |  | 33.82%
Contract Type: |  | FP |  | PeopleSoft Contract No.: |  | 23539
Contract Period of Performance: |  |  | 10/01/06 - 09/30/09 |  |  |  |  | CTD Revenue | 2552092 |  | EAC (Act + Frcst) (Sales) |  | 3500092
Total Contract Value: |  | 13617178 |  | Total Contract Funding: |  | 2628740 |  | CTD Costs | 1953426 |  | CAC (Act + Frcst) (Costs) |  | 2751426
[8 empty] | CTD Profit | 30.65%
Contract Period of Performance: |  |  | 10/01/06 - 09/30/09 | [8 empty] | Funding Status: | -871352
Total Contract Value: |  | 13617178 |  | Total Contract Funding: |  | 2628740 |  | Remaining Funding: | 76648 |  |  |  | Current | Previous
[8 empty] | % Funding Spent | 97.08% |  |  | Variance at Complete: | 10117.086 | 10313.2
Program's Description: |  |  | Contract No. 4600001334
ManTech provides full operations and maintenance (O&M) of the NTM-I automated data processing (ADP) systems and communication systems.
ACCOMPLISHMENTS (Last 30 Days) | [7 empty] | CONTRACT ACTIVITY
Risk Memo -
75% Notification -
Export Compliance -
PROGRAM ISSUES & POTENTIAL ISSUES | [7 empty] | ACTION PLANS
|  | N/A | [7 empty] | N/A
INVESTMENT STATUS | [7 empty] | Reviewed by: |  |  |  | Program Mgr
1) | Unbilled Sales: |  | 256449.8 |  | WIP
2) | Receivables +60: |  | 369400 |  | Paid on 7/20/07 | [6 empty] | Finance Mgr
3) | Other:
Contracts Mgr

## GRAPHs
MPSR for NTM-I
Open Reqs:_________
| 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 |  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01
BAC | 13890178 | 13890178 | 13617178 | 13617178 | 13617178 | 13617178 |  |  | PLAN | 5 | 5 | 6
EAC | 13890178 | 13890178 | 13617178 | 13617178 | 13617178 | 13617178 |  |  | ManTech FTE | 5 | 5 | 6
VAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding | 13890178 | 13890178 | 13617178 | 13617178 | 13617178 | 13617178

## Graph Data
LABOR | (Direct Labor only)
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Cost of Sales |  | 297899.39 | 229887.78 | 226281.65 | 219542.19 | 295024 | 254494 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 2321129.01
Total Sales |  | 162898.23 | 210880.68 | 369400 | 369400 | 571562 | 354081 | 158000 | 158000 | 158000 | 158000 | 158000 | 158000 | 2986221.91
Total Fee |  | -135001.16 | -19007.1 | 143118.35 | 149857.81 | 276538 | 99587 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 665092.9
Total Profit Rate |  | -45.32% | -8.268% | 63.25% | 68.26% | 93.73% | 39.13% | 18.8% | 18.8% | 18.8% | 18.8% | 18.8% | 18.8% | 28.65%
ODC
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Subcontractor Costs | [13 empty] | 0
Total Subcontractor Labor Sales | [13 empty] | 0
Total Travel Sales |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total | Actuals | ETC
Total Revenue |  | 162898.23 | 210880.68 | 369400 | 369400 | 571562 | 354081 | 158000 | 158000 | 158000 | 158000 | 158000 | 158000 | 2986221.91 | 2038221.91 | 948000
Total Costs |  | 297899.39 | 229887.78 | 226281.65 | 219542.19 | 295024 | 254494 | 133000 | 133000 | 133000 | 133000 | 133000 | 133000 | 2321129.01 | 1523129.01 | 798000
Total Profit |  | -135001.16 | -19007.1 | 143118.35 | 149857.81 | 276538 | 99587 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 665092.9 | 515092.9 | 150000
Total Profit % |  | -45.32% | -8.268% | 63.25% | 68.26% | 93.73% | 39.13% | 18.8% | 18.8% | 18.8% | 18.8% | 18.8% | 18.8% | 28.65% | 33.82% | 18.8%