## Funding Status (hidden)
FUNDING STATUS
21st Space Wing
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
39.13%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
76 SCS
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
4.35%
0 | #VALUE! | #VALUE! | #VALUE!
#REF! | % Expended to date
MAJCOM
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
56.52%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
PMO
Funding | Cost Variance
0 | #VALUE!
#REF! | % Expended to date
TOTALS
Funding | Cost Variance |  | Total Contract Under/Overrun
0 | #REF! |  | #REF!
#REF! | % Expended to date

## Status Report
MONTHLY PROGRAM STATUS REPORT | [5 empty] | As of Period Ending: | 2007-06-29
Program Name: |  | Secure VTC | [5 empty] | Month Revenue | 94241.99 |  | YTD Revenue |  | 319882.5
Program Manager: |  | Todd Morgan | [5 empty] | Month Costs | 6720.17 |  | YTD Costs |  | 158856.19
Customer: |  | NC3A-BE | [5 empty] | Month Profit | 1302% |  | YTD Profit |  | 101.4%
Contract Type: |  | FP |  | PeopleSoft Contract No.: |  | 23545
Contract Period of Performance: |  |  | 10/10/06 - 12/31/09 |  |  |  |  | CTD Revenue | 1263716 |  | EAC (Act + Frcst) (Sales) |  | 1583925
Total Contract Value: |  | 1583925.24 |  | Total Contract Funding: |  | 1583925 |  | CTD Costs | 957392 |  |  |  | 1116230
[8 empty] | CTD Profit | 32%
Contract Period of Performance: |  |  | 10/10/06 - 12/31/09 | [8 empty] | Funding Status: | 0
Total Contract Value: |  | 1583925 |  | Total Contract Funding: |  | 1583925 |  | Remaining Funding: | 320209 |  |  |  | Current | Previous
[8 empty] | % Funding Spent | 79.78% |  |  | Variance at Complete: | 0 | 0
Program's Description: |  |  | Contract No. CO-11853-OPL
ManTech provides installation, integration, testing and training of VTC equipment into 8 different locations: Kabul Afghanistan International Airport (KAIA), Deployed Operating Bases (DOBs) at Khandahar Airfield (KAF) and Bagram Airfield (BAF),
and five Regional Commands (RC's) (Mes-A-Sharif, Heart, Salerno, Kabul (KMNB), and Khandahar).
ACCOMPLISHMENTS (Last 30 Days) | [7 empty] | CONTRACT ACTIVITY
Bryan Canaan and his team successfully completed the installation, testing, and theater
wide training to obtain a signed FSA which completes the first 11 CLINS of the contract. | [7 empty] | Submitted updated pricing and conducted fact finding and negotiations for Amd 2 to the contract for the
hardware, installation, and warranty support for two systems in Iraq (NTM-I). Total Value = $324K
The contract has been amended, adding two more systems for NTM-I. These systems are | [7 empty] | Settled two claims associated with transportation delays on previous trips to Afghanistan. Total Value = $90K
currently in transit to IRAQ and NAPLES for preliminary testing. NTM-I personnel will be
performing the on-site installation and testing with support from Colorado Springs.
[8 empty] | Risk Memo - | N/A
[8 empty] | 75% Notification - | N/A
[8 empty] | Export Compliance - | Yes, License #730001597 for five sets of body armor
PROGRAM ISSUES & POTENTIAL ISSUES | [7 empty] | ACTION PLANS
|  | N/A | [7 empty] | N/A
INVESTMENT STATUS | [7 empty] | Reviewed by: |  |  |  | Program Mgr
1) | Unbilled Sales: |  | 3386.99 |  | WIP
2) | Receivables +60: |  | 0 | [8 empty] | Finance Mgr
3) | Other:
Contracts Mgr

## GRAPHs
MPSR for Secure VTC
Open Reqs:_________
| 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 |  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-07 | 2007-07-01 | 2007-08-01
BAC | 1169.474 | 1169.474 | 1169.474 | 1169.474 | 1169.474 | 1583.925 |  |  | Budget | 2 | 2.5 | 0 | 0 | 0 | 0 |  | 0
EAC | 1169.474 | 1169.474 | 1169.474 | 1169.474 | 1169.474 | 1583.925 |  |  | Actual | 2 | 2.75 | 0.275 | 0.15 | 0.25 | 0.25 |  | 0
VAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding | 1169.474 | 1169.474 | 1169.474 | 1169.474 | 1169.474 | 1583.925

## Graph Data
LABOR | (Direct Labor only)
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Cost of Sales |  | 22844.79 | 31800.74 | 3569.28 | 1648.72 | 2885 | 3336.64 | 0 | 0 | 0 | 0 | 0 | 0 | 66085.17
Total Sales |  | 19523.32 | 142821.29 | 0 | 0 | 0 | 90766.68 | 0 | 0 | 0 | 0 | 0 | 0 | 253111.29
Total Fee |  | -3321.47 | 111020.55 | -3569.28 | -1648.72 | -2885 | 87430.04 | 0 | 0 | 0 | 0 | 0 | 0 | 187026.12
Total Profit Rate |  | -14.54% | 349.1% | -100% | -100% | -100% | 2620% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 283%
ODC
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Subcontractor Costs |  | 2007-01-01: 22338.61; 2007-02-01: 33328.3; 2007-03-01: 30782.74; 2007-04-01: 2775.28; 2007-05-01: 162.56; 2007-06-01: 3383.53 | 92771.02
Total Subcontractor Labor Sales |  | 2007-01-01: 25659.68; 2007-02-01: 37636.22; 2007-03-01: 0; 2007-04-01: 0; 2007-05-01: 0; 2007-06-01: 3475.31 | 66771.21
Total Travel Sales |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total | Actuals | ETC
Total Revenue |  | 45183 | 180457.51 | 0 | 0 | 0 | 94241.99 | 0 | 0 | 0 | 0 | 0 | 0 | 319882.5 | 319882.5 | 320209
Total Costs |  | 45183.4 | 65129.04 | 34352.02 | 4424 | 3047.56 | 6720.17 | 0 | 0 | 0 | 0 | 0 | 0 | 158856.19 | 158856.19 | 158838
Total Profit |  | -0.4 | 115328.47 | -34352.02 | -4424 | -3047.56 | 87521.82 | 0 | 0 | 0 | 0 | 0 | 0 | 161026.31 | 161026.31 | 161371
Total Profit % |  | -0.0008853% | 177.1% | -100% | -100% | -100% | 1302% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 101.4% | 101.4% | 101.6%