## Funding Status (hidden)
FUNDING STATUS
21st Space Wing
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
39.13%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
76 SCS
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
4.35%
0 | #VALUE! | #VALUE! | #VALUE!
#REF! | % Expended to date
MAJCOM
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
56.52%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
PMO
Funding | Cost Variance
0 | #VALUE!
#REF! | % Expended to date
TOTALS
Funding | Cost Variance |  | Total Contract Under/Overrun
0 | #REF! |  | #REF!
#REF! | % Expended to date

## Status Report
MONTHLY PROGRAM STATUS REPORT | [5 empty] | As of Period Ending: | 2007-06-29
Program Name: |  | Secure VTC | [5 empty] | Month Revenue | 94242 |  | YTD Revenue |  | 319882.68
Program Manager: |  | Todd Morgan | [5 empty] | Month Costs | 6702 |  | YTD Costs |  | 158838.01
Customer: |  | NC3A-BE | [5 empty] | Month Profit | 1306% |  | YTD Profit |  | 101.4%
Contract Type: |  | FP |  | PeopleSoft Contract No.: |  | 23545
Contract Period of Performance: |  |  | 10/10/06 - 03/31/09 |  |  |  |  | CTD Revenue | 1263716 |  | EAC (Act + Frcst) (Sales) |  | 1263716
Total Contract Value: |  | 1583925.24 |  | Total Contract Funding: |  | 1583925 |  | CTD Costs | 957392 |  | CAC (Act + Frcst) (Costs) |  | 957392
[8 empty] | CTD Profit | 32%
Contract Period of Performance: |  |  | 10/10/06 - 03/31/09 | [8 empty] | Funding Status: | 0
Total Contract Value: |  | 1583925 |  | Total Contract Funding: |  | 1583925 |  | Remaining Funding: | 320209 |  |  |  | Current | Previous
[8 empty] | % Funding Spent | 79.78% |  |  | Variance at Complete: | 320.209 | 0
Program's Description: |  |  | Contract No. CO-11853-OPL
ManTech provides installation, integration, testing and training of VTC equipment into 8 different locations: Kabul Afghanistan International Airport (KAIA), Deployed Operating Bases (DOBs) at Khandahar Airfield (KAF) and Bagram Airfield (BAF),
and five Regional Commands (RC's) (Mes-A-Sharif, Heart, Salerno, Kabul (KMNB), and Khandahar).
ACCOMPLISHMENTS (Last 30 Days) | [7 empty] | CONTRACT ACTIVITY
Risk Memo -
75% Notification -
Export Compliance -
PROGRAM ISSUES & POTENTIAL ISSUES | [7 empty] | ACTION PLANS
|  | N/A | [7 empty] | N/A
INVESTMENT STATUS | [7 empty] | Reviewed by: |  |  |  | Program Mgr
1) | Unbilled Sales: |  | 3386.99 |  | WIP
2) | Receivables +60: |  | 0 | [8 empty] | Finance Mgr
3) | Other:
Contracts Mgr

## GRAPHs
MPSR for Secure VTC
Open Reqs:_________
| 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 |  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-07 | 2007-07-01 | 2007-08-01
BAC | 1169.474 | 1169.474 | 1169.474 | 1169.474 | 1169.474 |  |  |  | PLAN | 2 | 2.5 | 0 |  |  |  |  | 0
EAC | 1169.474 | 1169.474 | 1169.474 | 1169.474 | 1169.474 |  |  |  | ManTech FTE | 2 | 2.75 | 0.275 |  |  |  |  | 0
VAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding | 1169.474 | 1169.474 | 1169.474 | 1169.474 | 1169.474

## Graph Data
LABOR | (Direct Labor only)
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Cost of Sales |  | 45183.39 | 65128.74 | 34351.74 | 4424.14 | 3048 | 6702 | 0 | 0 | 0 | 0 | 0 | 0 | 158838.01
Total Sales |  | 45183.39 | 180457.29 | 0 | 0 | 0 | 94242 | 0 | 0 | 0 | 0 | 0 | 0 | 319882.68
Total Fee |  | 0 | 115328.55 | -34351.74 | -4424.14 | -3048 | 87540 | 0 | 0 | 0 | 0 | 0 | 0 | 161044.67
Total Profit Rate |  | 0% | 177.1% | -100% | -100% | -100% | 1306% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 101.4%
ODC
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Subcontractor Costs |  | 2007-01-01: 0 | 0
Total Subcontractor Labor Sales |  | 2007-01-01: 0 | 0
Total Travel Sales |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total | Actuals | ETC
Total Revenue |  | 45183.39 | 180457.29 | 0 | 0 | 0 | 94242 | 0 | 0 | 0 | 0 | 0 | 0 | 319882.68 | 319882.68
Total Costs |  | 45183.39 | 65128.74 | 34351.74 | 4424.14 | 3048 | 6702 | 0 | 0 | 0 | 0 | 0 | 0 | 158838.01 | 158838.01
Total Profit |  | 0 | 115328.55 | -34351.74 | -4424.14 | -3048 | 87540 | 0 | 0 | 0 | 0 | 0 | 0 | 161044.67 | 161044.67 | 0
Total Profit % |  | 0% | 177.1% | -100% | -100% | -100% | 1306% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 101.4% | 101.4% | #DIV/0!