## Funding Status (hidden)
FUNDING STATUS
21st Space Wing
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
39.13%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
76 SCS
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
4.35%
0 | #VALUE! | #VALUE! | #VALUE!
#REF! | % Expended to date
MAJCOM
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
56.52%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
PMO
Funding | Cost Variance
0 | #VALUE!
#REF! | % Expended to date
TOTALS
Funding | Cost Variance |  | Total Contract Under/Overrun
0 | #REF! |  | #REF!
#REF! | % Expended to date

## Status Report
MONTHLY PROGRAM STATUS REPORT | [5 empty] | As of Period Ending: | 2007-06-29
Program Name: |  | HQ SACT/Joint Analysis & Lessons Learned | [5 empty] | Month Revenue |  | 133181.98 |  | YTD Revenue |  | 837989.24
Program Manager: |  | Lindy Martin | [5 empty] | Month Costs |  | 118576.26 |  | YTD Costs |  | 653934.25
Customer: |  | JALLC | [5 empty] | Month Profit |  | 12.32% |  | YTD Profit |  | 28.15%
Contract Type: |  | T&M |  | PeopleSoft Contract No.: |  | 23657
Contract Period of Performance: |  |  | 01/01/07 - 12/31/07 |  |  |  |  | CTD Revenue |  | 837989 |  | EAC (Act + Frcst) (Sales) |  | 1773509.86
Total Contract Value: |  | 1389899.56 |  | Total Contract Funding: |  | 1389900 |  | CTD Costs |  | 653935 |  | CAC (Act + Frcst) (Costs) |  | 1407437.8
[8 empty] | CTD Profit |  | 28.15%
Contract Period of Performance: |  |  | 01/01/07 - 12/31/07 | [9 empty] | Funding Status: | -383609.86
Total Contract Value: |  | 1389900 |  | Total Contract Funding: |  | 1389900 |  | Remaining Funding: |  | 551911 |  |  |  | Current | Previous
[8 empty] | % Funding Spent |  | 60.29% |  |  | Variance at Complete: | -383.6099 | -399.2
Program's Description: |  |  | Contract No. 4050044
ManTech currently provides 7 specialized Operational Analysts (Moeder/Eden/Ross/Thordsen/Meehan/Hansen/Sosa and 1Contracting Officer (Donahue) to assist NATO’s Joint Analysis Lessons Learned Centre (JALLC).
in Portugal.
ACCOMPLISHMENTS (Last 30 Days) | [7 empty] | CONTRACT ACTIVITY
*We have 7 operational analysts and 1 contracting officer employed at the Joint Analysis and
Lessons Learned Center (JALLC) in Lisbon, Portugal. The JALLC is NATO's premier agency for lessons | [8 empty] | New PO received adding 75 hrs for 4,500 euro for Donahue.
learned and is an entity of one of NATO's two strategic commands, Allied Command Transformation
Submitted TAA Amendment 1 to DDTC for approval. This amendment updated the contract value,
*The ManTech analysts are involved in every ongoing NATO operation and mission: NATO Training Mission Iraq | [8 empty] | employee name change, and updated the statement of work. We have not received an approval yet.
(NTM-I), International Security Assistance Force (ISAF) in Afghanistan, Kosovo Force (KFOR), Operation
ACTIVE ENDEAVOR (OAE) in the Mediterranean Sea, and the African Union Mission in the Sudan (AMIS).
*ISAF is the primary focus of NATO operations at this point and three of our analysts are involved in ISAF
analysis objectives such as C2, Key Leader Training, composite HQs, transfer of authority from the US
coalition to NATO.
*For the other operations, analysis objectives include funding, oversight and technical authority role of SACT,
multinational logistics, task force concept, and intel architecture.
*One analyst is also focused on exercises and training, and he has been addressing reach back, C2, the NATO
Reaction Force (NRF) and an ISAF friendly fire incident. He was also the primary architect for the "train the
trainer" training package on lessons learned delivered to AMIS organizations by a JALLC officer.
*For all analysis objectives, the ManTech analysts are the centers of gravity for drafting analysis reports,
normally 20-40 pages in length. These reports provide the basis for changes to NATO doctrine and procedures,
and also the primary source documents for populating the NATO Lessons Learned Database maintained by the
JALLC (and specifically one of our analysts).
[8 empty] | Risk Memo - |  | N/A
[8 empty] | 75% Notification - |  | N/A
[8 empty] | Export Compliance - |  | Yes, TAA Case No. 1457-06
PROGRAM ISSUES & POTENTIAL ISSUES | [7 empty] | ACTION PLANS
| Joe Moeder is slated to transfer up to the ManTech Brussels office. His Replacement | [9 empty] | N/A
need to be named and position backfills completed.
INVESTMENT STATUS | [7 empty] | Reviewed by: |  |  |  |  | Program Mgr
1) | Unbilled Sales: |  | 196776.35 |  | 45K accruals; 154K WIP
2) | Receivables +60: |  | 0 | [9 empty] | Finance Mgr
3) | Other:
Contracts Mgr

## GRAPHs
MPSR for HQ SACT/Joint Analysis & Lessons Learned
Open Reqs:_________
| 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 |  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01
BAC | 119.538 | 1383.804 | 1383.804 | 1383.804 | 1383.804 | 1383.899 |  |  | Budget | 4 | 4 | 4 | 5 | 5 | 5 | 0 | 0
EAC | 119.538 | 1728.634 | 1775.381 | 1782.991 | 1775.905 | 1773.51 |  |  | Actual | 4.5 | 3.84 | 2.88 | 3.9 | 4.55 | 4.73 | 0 | 0
VAC | 0 | -344.83 | -391.577 | -399.187 | -392.101 | -389.611 | 0 | 0 |  | * 3 Subcontractor & 5 ManTech Employees
Funding | 119.538 | 1383.804 | 1383.804 | 1383.804 | 1383.804 | 1383.899

## Graph Data
LABOR | (Direct Labor only)
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Cost of Sales |  | 49234.23 | 53842.5 | 57350.1 | 55198.24 | 64031 | 84219 | 53000 | 55000 | 53221 | 53221 | 53221 | 53221 | 684759.07
Total Sales |  | 47477.31 | 157326 | 82497.18 | 75146.69 | 79916 | 97919 | 68193 | 68193 | 68193 | 68193 | 68193 | 68193 | 949440.18
Total Fee |  | -1756.92 | 103483.5 | 25147.08 | 19948.45 | 15885 | 13700 | 15193 | 13193 | 14972 | 14972 | 14972 | 14972 | 264681.11
Total Profit Rate |  | -3.568% | 192.2% | 43.85% | 36.14% | 24.81% | 16.27% | 28.67% | 23.99% | 28.13% | 28.13% | 28.13% | 28.13% | 38.65%
ODC
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Subcontractor Costs |  | 0 | 58322.04 | 87730.43 | 67070.89 | 42578.56 | 34357.26 | 54470 | 49041.8 | 47126 | 48600 | 52586 | 62574 | 604456.98
Total Subcontractor Labor Sales |  | 0 | 59856.2 | 90036.47 | 68849.72 | 43701.69 | 35262.98 | 68193 | 60886 | 59263 | 56015 | 65757 | 79862.86 | 687683.92
Total Travel Sales |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total | Actuals | ETC
Total Revenue |  | 47477.31 | 217182.2 | 172533.65 | 143996.41 | 123617.69 | 133181.98 | 136386 | 129079 | 127456 | 124208 | 133950 | 148055.86 | 1637124.1 | 837989.24 | 935520.86
Total Costs |  | 49234.23 | 112164.54 | 145080.53 | 122269.13 | 106609.56 | 118576.26 | 107470 | 104041.8 | 100347 | 101821 | 105807 | 115795 | 1289216.05 | 653934.25 | 753502.8
Total Profit |  | -1756.92 | 105017.66 | 27453.12 | 21727.28 | 17008.13 | 14605.72 | 28916 | 25037.2 | 27109 | 22387 | 28143 | 32260.86 | 347908.05 | 184054.99 | 182018.06
Total Profit % |  | -3.568% | 93.63% | 18.92% | 17.77% | 15.95% | 12.32% | 26.91% | 24.06% | 27.02% | 21.99% | 26.6% | 27.86% | 21.25% | 28.15% | 24.16%