## Funding Status (hidden)
FUNDING STATUS
21st Space Wing
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
39.13%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
76 SCS
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
4.35%
0 | #VALUE! | #VALUE! | #VALUE!
#REF! | % Expended to date
MAJCOM
Funding | Cost Variance | PMO Allocation | Total Under/Overrun
56.52%
0 | #REF! | #VALUE! | #REF!
#REF! | % Expended to date
PMO
Funding | Cost Variance
0 | #VALUE!
#REF! | % Expended to date
TOTALS
Funding | Cost Variance |  | Total Contract Under/Overrun
0 | #REF! |  | #REF!
#REF! | % Expended to date

## Status Report
MONTHLY PROGRAM STATUS REPORT | [5 empty] | As of Period Ending: | 2007-06-29
Program Name: |  | HQ SACT/Joint Analysis & Lessons Learned | [5 empty] | Month Revenue | 133181.98 |  | YTD Revenue |  | 837989.39
Program Manager: |  | Lindy Martin | [5 empty] | Month Costs | 118576.26 |  | YTD Costs |  | 653934.21
Customer: |  | JALLC | [5 empty] | Month Profit | 12.32% |  | YTD Profit |  | 28.15%
Contract Type: |  | T&M |  | PeopleSoft Contract No.: |  | 23657
Contract Period of Performance: |  |  | 01/01/07 - 12/31/07 |  |  |  |  | CTD Revenue | 837989 |  | EAC (Act + Frcst) (Sales) |  | 1772700.66
Total Contract Value: |  | 1389899.56 |  | Total Contract Funding: |  | 1389900 |  | CTD Costs | 653935 |  | CAC (Act + Frcst) (Costs) |  | 1463040
[8 empty] | CTD Profit | 28.15%
Contract Period of Performance: |  |  | 01/01/07 - 12/31/07 | [8 empty] | Funding Status: | -382800.66
Total Contract Value: |  | 1389900 |  | Total Contract Funding: |  | 1389900 |  | Remaining Funding: | 551911 |  |  |  | Current | Previous
[8 empty] | % Funding Spent | 60.29% |  |  | Variance at Complete: | -382.8007 | -399.2
Program's Description: |  |  | Contract No. 4050044
ManTech currently provides 7 specialized Operational Analysts (Moeder/Eden/Ross/Thordsen/Meehan/Hansen/Sosa and 1Contracting Officer (Donahue) to assist NATO’s Joint Analysis Lessons Learned Centre (JALLC).
in Portugal.
ACCOMPLISHMENTS (Last 30 Days) | [7 empty] | CONTRACT ACTIVITY
[8 empty] | Risk Memo - | N/A
[8 empty] | 75% Notification - | N/A
[8 empty] | Export Compliance - | Yes
PROGRAM ISSUES & POTENTIAL ISSUES | [7 empty] | ACTION PLANS
N/A
INVESTMENT STATUS | [7 empty] | Reviewed by: |  |  |  | Program Mgr
1) | Unbilled Sales: |  | 196776.35 |  | 45K accruals; 154K WIP
2) | Receivables +60: |  | 0 | [8 empty] | Finance Mgr
3) | Other:
Contracts Mgr

## GRAPHs
MPSR for HQ SACT/Joint Analysis & Lessons Learned
Open Reqs:_________
| 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 |  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01
BAC | 119.538 | 1383.804 | 1383.804 | 1383.804 | 1383.804 |  |  |  | PLAN | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
EAC | 119.538 | 1728.634 | 1775.381 | 1782.991 | 1775.905 |  |  |  | ManTech FTE | 4.5 | 3.84 | 2.88 | 0 | 0 | 0 | 0 | 0
VAC | 0 | -344.83 | -391.577 | -399.187 | -392.101 | 0 | 0 | 0 |  | * 4 Subcontractor & 4 ManTech Employees
Funding | 119.538 | 1383.804 | 1383.804 | 1383.804 | 1383.804

## Graph Data
LABOR | (Direct Labor only)
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Cost of Sales |  | 49234.23 | 112164.5 | 57350.1 | 55198.24 | 64031 | 84219 | 53000 | 55000 | 53221 | 53221 | 53221 | 53221 | 743081.07
Total Sales |  | 47477.31 | 217182.35 | 82497.18 | 75146.69 | 79916 | 97919 | 68193 | 68193 | 68193 | 68193 | 68193 | 68193 | 1009296.53
Total Fee |  | -1756.92 | 105017.85 | 25147.08 | 19948.45 | 15885 | 13700 | 15193 | 13193 | 14972 | 14972 | 14972 | 14972 | 266215.46
Total Profit Rate |  | -3.568% | 93.63% | 43.85% | 36.14% | 24.81% | 16.27% | 28.67% | 23.99% | 28.13% | 28.13% | 28.13% | 28.13% | 35.83%
ODC
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total
Total Subcontractor Costs |  | 0 | 0 | 87730.43 | 67070.89 | 42578.56 | 34357.26 | 57000 | 43000 | 65000 | 65000 | 65000 | 75000 | 601737.14
Total Subcontractor Labor Sales |  | 0 | 0 | 90036.47 | 68849.72 | 43701.69 | 35262.98 | 59263 | 45462.14 | 68193.22 | 68193.22 | 68193.22 | 79862.86 | 627018.52
Total Travel Sales |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | Grand Total | Actuals | ETC
Total Revenue |  | 47477.31 | 217182.35 | 172533.65 | 143996.41 | 123617.69 | 133181.98 | 127456 | 113655.14 | 136386.22 | 136386.22 | 136386.22 | 148055.86 | 1636315.05 | 837989.39 | 934711.66
Total Costs |  | 49234.23 | 112164.5 | 145080.53 | 122269.13 | 106609.56 | 118576.26 | 110000 | 98000 | 118221 | 118221 | 118221 | 128221 | 1344818.21 | 653934.21 | 809105
Total Profit |  | -1756.92 | 105017.85 | 27453.12 | 21727.28 | 17008.13 | 14605.72 | 17456 | 15655.14 | 18165.22 | 18165.22 | 18165.22 | 19834.86 | 291496.84 | 184055.18 | 125606.66
Total Profit % |  | -3.568% | 93.63% | 18.92% | 17.77% | 15.95% | 12.32% | 15.87% | 15.97% | 15.37% | 15.37% | 15.37% | 15.47% | 17.81% | 28.15% | 15.52%