## Slide 1
Operational Analyst Support to the Joint Analysis & Lessons Learned Centre
Proposal Pre-Release Review
Operating Unit: Global Services/International
October 9, 2009

## Slide 2: Program Description
Program Name: Operational Analyst Support to the Joint Analysis and Lessons Learned Centre
Customer: Allied Command Transformation (ACT) Joint Analysis & Lessons Learned Centre
Contracting Officer and Agency: : Alex F. MacDonald, Senior Buyer
Work Requirements: (Core Services) Provide Operational Analysis & Lessons Learned on NATO operations throughout NATO’s Area of Operations (15K radius of Brussels) Place of Performance: JALLC, Monsanto, Portugal and multiple travel locations throughout NATO countries as required Proposal Due: 29 Oct 2009

## Slide 3: Customer Organization
Contracting/Procurement
Possible Source Selection Committee Members
JALLC, Chief of Staff, Division Chiefs
  - Operations (LTC Nils Windheuser)
  - Lessons Learned & Analysis (LTC Kjetil Larsen)
  - Exercise, Training, and Experimentation Division
  (COL Karlheinz Nickel)
  - Production (LTC Bruce Brunelle
  -BUDFIN (recorder)
  -Admin
JALLC Structure
JALLC, Commander (BGen Hansen-Nord)
• Command Group (COS, Exec, & MA)
• Mission Deliverables:
-- 2 Divisions (Ops & Ex/Tng analysis)
-- 1 Branch (Lessons Learned Db)
• Resources and Support
-- 1 HR Division (matrix arrangement)
-- BUDFIN
-- Admin/Registry/Security/IT

## Slide 4: Program Overview
Solicitation/TO #: NAMSA Collective No.: |  |  | 
Small Business Set-Aside |  Yes  No | GovWin ID: | 5819
Total Value ($M): | $8 Million | INPUT ID: | 
ManTech Value ($M): | $8 Million |  Pwin %: | 89
# of Awards: | 1 |  Pgo %: | 100
Prime or Sub Role: | Prime | Executive Sponsor: | Global Services/International
% Work Share: | 100 | Account Manager: | Lindy Martin
Contract Category: (Basic, IDIQ, Task Order, etc.) | Basic | BD Manager: | Lindy Martin
Contract Type: (TM, FFP, CPAF, etc.) | FFP TM | Capture Manager: | Jody Tieken-Holecek
Lead Type: (New, Re-Compete, Add-On, etc.) | Recompete | Proposal Manager: | Laura Hill
Incumbent: | ManTech | Contract Manager: | Robin Brooks
POP (Years): | 5 | Program Manager | David Ross
Pwin/Pgo Value =  Excellent (61% - 100%)  Good (46% - 60%)  Fair (31% - 45%)  Poor (0% - 30%)

## Slide 5: Acquisition Schedule
Bid Intention | 29 April 2009
Bidders Conference | 7 July 2009
Draft SOW | NA
Questions | NA
Final RFP | 17 August 2009
Proposal Due | 29 October 2009
Public Bid Opening | NA
BAFO | NA
Award | 30 November 2009
Contract Start | 1 January 2010
 = RFP release > 180 days
 = RFP release ≤ 180 days
 = RFP release ≤ 90 days
 = RFP release ≤ 60 days

## Slide 6: Competitive Assessment
Biding Entity + Competitors | Past Performance | Technology Solution | Management Solution | Quality Assurance/ Control | Cost/Price | Small Business Utilization | Numerical Ranking
1. ManTech Technical Services Group |  |  |  |  |  | NA | 1
2. Qinetiq |  |  |  |  |  | NA | 2
3. IABG |  |  |  |  |  | NA | 3
4. ISG – International Solutions Group (US) |  |  |  |  |  | NA | 4
5. |  |  |  |  |  |  | 
6. |  |  |  |  |  |  | 
7. |  |  |  |  |  |  | 
8. |  |  |  |  |  |  | 
Competitive Assessment =  Excellent  Good  Fair  Poor  N/A

## Slide 7: Business Rational – Previous Proposal
Categories | Program Estimate | Program Status | Scoring Criteria
Headcount Growth (Direct Hires Consultants) | 3 4 |  |  Excellent – At least 95% of the bid results in new hire D/L and/or retains existing D/L incumbency  Good – Greater than 50% to 94% of the bid results in new hire D/L and/or retains existing D/L incumbency  Fair – Greater than 35% to 49% of the bid results in new hire D/L and/or retains existing D/L incumbency  Poor – The bid does not result in new hire D/L and/or the retention of existing D/L incumbency
% Gross Profit | 15% |  |  Excellent – Exceeds profits objectives  Good – Meets profit objectives  Fair – Less than .5% below profit objectives  Poor – More than .5% below profit objectives
Annual Revenue | $1.5 (Est) |  |  Excellent – Greater than $15M  Good – Between $5M - $15M  Fair – Greater than $1M and less than $5M  Poor – $1M or less
% ODC and/or Product | 57% (Est) |  |  Excellent – Less than 5% of the total bid  Good – Between 5% and less than 10% of the total bid  Fair – Between 10% and less than 25% of the total bid  Poor – More than 25% of the total bid
Explain upside/down-side of any cash flow implications, financial risks, or problematic funding issues: Program estimates derived from original proposal. These will be revised/updated during the proposal process. Estimated Staffing: TSG – 11; Segovia – 4; Total estimated contract staff – 15.

## Slide 8: Proposal Status Laura Hill, Proposal Manager

## Slide 9: Compliance Matrix
Compliance Requirement | Rating | Compliance Status
1. Administrative Documentation |  | All requirements have been addressed. Red Team has been delayed, so compliance has not been determined.
2. Technical Approach |  | All requirements have been addressed. Red Team has been delayed, so compliance has not been determined.
3. Management Plan for Execution of the Contract |  | All requirements have been addressed. Red Team has been delayed, so compliance has not been determined.
4. Resumes and Personnel Matrices |  | All requirements have been addressed. Red Team has been delayed, so compliance has not been determined.
5. Past Performance |  | All references are relevant. Red Team has been delayed, so compliance has not been determined.
6. Quality Assurance Program and Technology-based Personnel Training |  | All requirements have been addressed. Red Team has been delayed, so compliance has not been determined.

## Slide 10: Status of Win Strategy Elements & Actions
Provide qualified personnel (3 ManTech employees; 4 consultants) | 
Provide quality past performance references | 
Ensure total compliance | 
Not applicable
Win Strategy Elements
Baseline Actions/Metrics

## Slide 11: Risk Assessment & Mitigation
Risks | Risk Level | Mitigation Plan and Action Status
1. JCCC bid issues may impacted our ability to submit JALLC on time |  | Proposal Manager continues to press the JCCC team for results and work on JALLC proposal
2. Need all proposal content in time to submit the bid |  | All requirements have been addressed. Red Team has been delayed, so compliance has not been determined.
3. Price volume may not be completed and approved in time to submit the bid |  | The elements of the price volume have been created. Pricing review and approval is in process.
Risk Level =  Minimal  Moderate  High  Critical

## Slide 12
Priming? Yes  No  |  | 
If priming list all significant subcontractors below: |  | 
Company Name | Contractual Status | Strategic Fit
Sub 1: KFM Technology Resources (US company providing 2 consultants – Robert Meehan and Andrew Eden) | NDA  TA  | 
Sub 2: All Consult (Norway company providing 1 consultant - Staale Hansen) | NDA  TA  | 
Teaming Status
Strategic Fit =  Excellent  Good  Fair  Poor
Note: TAs being finalized for Thales, Cobham Aviation Services and DFS

## Slide 13: Risk Assessment & Mitigation
Risks | Risk Level | Mitigation Plan and Action Status
1. Value Added Tax (VAT) |  | We have mitigated this risk and up to date on tax requirements. As long at we bid as MGSC.
2. ITAR |  | Have Mr. Sime review solicitation. Need to identify Contracts Administrator.
3. Legal |  | We are set up legally to do business in Portugal.
4. Loss of critical personnel by competition poaching |  | Teaming Agreements.
5. Operating Cost increases (labor) |  | Include COLA in bid price or pay employees in Euros.
6. Unable to come up with a PTW scenario – Bid currency? |  | Hold discussion about PTW and develop team to concentrate on pricing. Determine whether to bid in Euros or Dollars.
7. Competition Intelligence |  | Continue to gather intelligence on competition.
8. Proposal Development |  | Secure B&P dollars. Low investment. High ROI.
9. Liquidated Damages Clause – for ea calendar day of delay 0.1% up to 10% of total delivery order price |  | We have been successfully delivering on this contract for 3+ years. Product quality is high with current team.
Risk Level =  Minimal  Moderate  High  Critical

## Slide 14: Financial Considerations (Pricing) Brian Russell, Pricing

## Slide 15: Pricing Summary
Total Program Pricing Summary
 | Total Hours | Total Amount
Subtotal ManTech (Euro) | 27,750 | € 1,937,265
Subtotal ManTech (Dollar) | 27,750 | $ 2,853,726
Subtotal Subcontractor (Euro) | 37,000 | € 3,328,224
Subtotal Subcontractor (Dollar) | 37,000 | $ 4,902,707
Total Firm Fixed Price Euro | 64,750 | € 5,265,489
Total Firm Fixed Price Dollar (Conversion 1.47307) | 64,750 | $ 7,756,433
Profit on Mantech Labor | 14.53% | $ 343,824
Profit on Sub Labor | 10.40% | $ 435,900
Effective Profit % |  | 12.14%

## Slide 16: Price-To-Win Assessment
We formulated our pricing/cost build up
  ManTech has taken into consideration NATO’s current maximum budget for this effort and taken into consideration our current incumbent financial information
  With the precept that we must have the lowest price and be compliant to win
Incumbent Price Analysis | Amount
Current Proposal | € 5,265,489
Previous Proposal (Assuming a cont. 3% esc.) | € 6,138,357
Delta | € (872,868)
Delta % | -16.58%
Contract Ceiling Analysis | Avg. Rate | Hours | Amount
Current Proposal | € 81.32 | 64,750 | € 5,265,489
Contract Ceiling Maximum of 1.5 Million Euro per Year | € 115.83 | 64,750 | € 7,500,000
Delta | € (34.51) |  | € (2,234,512)
Delta % | -42.44% |  | -29.79%
Contract Ceiling Analysis | Avg. Rate | Hours | Amount
Current Proposal | € 81.32 | 64,750 | € 5,265,489
Contract Ceiling Minimum of 750,000 Euro per Year | € 57.92 | 64,750 | € 3,750,000
Delta | € 23.41 |  | € 1,515,489
Delta % | 28.78% |  | 40.41%

## Slide 17: Pricing Methodology/Assumptions
Pricing Methodology/Assumptions:
- Period of Performance: 1 January 2010 to 31 December 2014
- Contract type: Firm Fixed Price/Level of Effort
- ManTech labor includes:
- State Department regulation COLA annually
- $2,000 housing allowance annually-based on previous proposal
- DBA insurance of 1.90% per DoD guidelines (based on Portugal)
- All employees and consultants are current incumbents
- No travel is currently required or has been priced, all employees are current residing at the place of performance in Portugal

## Slide 18: Financial Considerations
Pricing may be quoted in the currency of any NATO member state.
  - Our pricing will be submitted in Euro. ManTech currently pays our consultants on our incumbent program in Euro.
  - The most current currency conversion factor has been applied to ManTech’s employee’s salaries
Invoicing
- Payment for all products and services specified above shall be made within 45 calendar days after receipt of properly supported and acceptable invoices submitted upon completion of delivery.

## Slide 19: Financial Risk
Risk:
-ManTech will be receive payment upon 45 days of completion of a deliverable. However, our consultants will be on a receive payments on a 30 day net basis.
-ManTech will be paid in Euro and will pay our employees in US Dollars. The Euro to US Dollar currency conversion factor has seen a 3.8% fluctuation over the last calendar year.
-The contract type payment terms indicate deliverable type payments, however deliverables are not clearly defined. To mitigate this ManTech will request to receive payments on a monthly basis for all hours worked.
-There is a Liquidated Damages clause in which, “in lieu of actual damage, the Contractor shall pay to HQ SACT as fixed, agreed, liquidated damages for each calendar day of delay, 0.1% of the total delivery order price, less handling, transportation and taxes, to a maximum of 10% of the delivery order price. “

## Slide 20: Recommendations
Approval to release the proposal to NATO ACT