August 2009

| SUNDAY | MONDAY | TUESDAY | WEDNESDAY |  | THURSDAY | FRIDAY |  | SATURDAY |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | 1 |
| 2 | 3 | 4 | 5 |  | 6 | 7 |  | 8 |
| 9 | 10 | 11 | 12 |  | 13 | 14 |  | 15 |
| 16 | 17 | 18 | 19 |  | 20 | 21 |  | 22 |
| 23 | 24 | 25 | 26 Solicitation released |  | 27 Solicitation distributed Team review solicitation KM create templates | 28 11AM EST— Kick-off Meeting KM create templates LH develop shell documents |  | (KM out) 29 |
| (KM out) 30 | (KM out) 31 LH develop shell documents Shell documents/ writing assignments sent to team NLT COB (LH) | Reviewers: Lindy Martin Jody Tieken-Holecek Joanne Surico |  | Writers: |  |  | Key: LH—Laura Hill KM—Kirstin Mercer LM—Lindy Martin SH—Steve Horn JS—Joanne Surico RFC—Request for Clarification (questions) |  |

September 2009

| SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY |
| --- | --- | --- | --- | --- | --- | --- |
| Key: LH—Laura Hill KM—Kirstin Mercer LM—Lindy Martin SH—Steve Horn JS—Joanne Surico RFC—Request for Clarification (questions) |  | (KM out) 1 Writers develop response | (KM out) 2 Writers develop response | (KM out) 3 Writers develop response | (KM/LH out) 4 Writers develop response | (KM/LH out) 5 |
| (KM/LH out) 6 | (KM/LH out) 7 HOLIDAY | 8 Writers develop response Pink Team input due to LH NLT COB All RFCs due to LH NLT COB | 9 Pink Team review doc development (LH) Edit RFCs (KM) LM approve RFCs Submit RFCs | 10 Pink Team review doc development (LH) Pink Team review document sent to team NLT COB (LH) | 11 Pink Team review | (LH out) 12 |
| (LH out) 13 | (LH out) 14 Pink Team review Pink Team review comments due to LH NLT COB | 15 Pink Team recovery (LH) | 16 Pink Team recovery (LH) Data call sent to writers NLT COB (LH) Final RFC due to Government | 17 Writers develop response | 18 Writers develop response | 19 |
| 20 | 21 Writers develop response | 22 Writers develop response Red Team input due to LH NLT COB | 23 Red Team review doc development (LH) | 24 Red Team review doc development (LH) Red Team review document sent to team NLT COB (LH) | 25 Red Team review | 26 |
| 27 | 28 Red Team review Red Team review comments due to LH NLT COB | 29 Red Team recovery (LH/writers) | 30 Red Team recovery (LH/writers) All final input due to LH NLT COB |  |  |  |

October 2009

| SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY |
| --- | --- | --- | --- | --- | --- | --- |
| Key: LH—Laura Hill KM—Kirstin Mercer LM—Lindy Martin SH—Steve Horn JS—Joanne Surico RFC—Request for Clarification (questions) |  |  |  | 1 Edit (KM) | 2 Edit (KM) Gold Team review document sent to team NLT COB (LH) | 3 |
| 4 | 5 Gold Team review Gold Team review comments due to LH NLT COB | 6 Gold Team recovery/ Final edit (KM/LH) | 7 Final compliance check (LH) | 8 Final compliance check (LH) Data call for final compliance items sent to writers NLT COB (LH) | 9 All final data call items due to LH NLT NOON Compliance check recovery (KM/LH) Approval for production (LM) | 10 |
| 11 | (KM out) 12 Production Ship proposal | (KM/LH out) 13 Confirm delivery | 14 NOON (Belgium)—Proposal due | 15 | 16 | 17 |
| 18 | 19 | 20 | 21 | 22 | 23 | (LH out) 24 |
| (LH out) 25 | (LH out) 26 | 27 | 28 | 29 | 30 | 31 |