## Slide 1
This briefing was inadvertently released to unauthorized contractor personnel and is, therefore, being made available to all potential S3 offerors.
This briefing was developed solely for the purpose of budget planning and should not be construed as the Government’s desired solution.
The information should not be relied on for any purpose and has not been updated to reflect subsequent changes to the Government's funding strategy.
The attached briefing should not be released outside of the S3 Contractors Holders.

## Slide 2
DoD BIOMETRICS
U.S. Central Command
Joint Urgent Operational Needs
Briefing for the Joint Rapid Acquisition Cell
LTC Debora L. Theall
PM, Biometrics
1 June 2006
www.biometrics.dod.mil
Brief is Acquisition Sensitive
Notes: <number>
<footer>
<header>
<date/time>

## Slide 3: Purpose & Agenda
Provide the Joint Rapid Acquisition Cell (JRAC) with an update and spend plan for current and requested funding in support of CENTCOM Enterprise and Base Access efforts
CENTCOM Enterprise JUONS
  JUONS In General
  Current Environment
  Enterprise Roadmap
  Costs
  Cost Summary
  Contracting Strategy
  Next Steps
CENTCOM Base Access JUONS
  Base Access JUONS In General
  Requirements Revisited
  Costs Revisited
  Cost Summary
  Timeline
  Contracting Strategy
  Next Steps

## Slide 4: CENTCOM Enterprise JUONS In General
CENTCOM “urgently requires DOD Support for the development of a comprehensive, requirements based, multi-modal, multi-functional, multi-domain biometric collection, storage, and matching system to achieve identity dominance”
“Currently, DOD and individual service elements are fielding individual systems with varying levels of interoperability…identity data is not readily available to commanders”
“Currently, the lack of a comprehensive management approach to the development and implementation of biometrics…is resulting in unfocused investment of significant fiscal and manpower resources..”
“Must be a joint program of record to secure funding and promote the development of joint doctrine, policy, and training…”
“Because there is not a program of record for development of biometric technologies, DOD Identity Management needs for OEF, OIF, in support of Force Protection are being financially and operationally constrained, as a result biometric program development is not meeting its objectives..”
“Develop a joint system that supports secure line collaborative management of biometric identification results to facilitate the immediate provision of match data and associated intelligence…provide CENTCOM with the ability to view all biometrics identifications/data obtained by US systems.
Develop a National Policy for sharing Biometrics data with non-DoD agencies, coalition and other foreign governments.
Develop a standardized, unclassified, “Watch Lists” detailing persons assessed to be of continued interest to the USG.

## Slide 5: DoD Biometrics Current Environment
Retain
Capture
Release
(Future)
Detainee Management
DRS
Clarksburg, WV
Charlottesville, VA
AIMS – Automated
Ident Management System
NGIC
FBI Integrated Automated Fingerprint Identification System
DOD Automated Biometric Identification System
Systems
Co-located
Baghdad,
Iraq
MPAC
NIPR
SIPR
SIPR
NIPR
NIPR
Deployed at Detainee Locations in AOR - operational at several sites, files collected at prison, connected to NDRC & sent to ABIS
Maritime Interception
Working to get connected to ABIS – Navy Policy Approved Apr 06
Fed Ex via REF
Intelligence, Detainee Mgmt
Physical Access, Checkpoints
BAT
Over 800 devices deployed
throughout AOR
Iraq Multi-Purpose
Access Card
SOCOM
Deployed in AOR - Files collected & delivered to REF – hard drives sent to ABIS in batch intervals
DBIDS
Physical Access Control
BISA
10 BISA Sites with VSAT in AOR
JIOC
IRAQ
TEAMING TO
COMBAT
TERRORISM
DoD ABIS
DHS US-VISIT
FBI IAFIS
Strategic/Interagency
End State, Operator-Focused
3 Sites Ready
19 Sites In Process
Capitalize on synergy with
G2/BAT/HIIDE, PM/BISA, DMDC/ DBIDS,
G3/DRS, PM/SOCOM, PM/Navy
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
Integrated and synchronized
End-to-End Transport Layer
FY07
FY08
FY06
NGIC BAC & BIR
NGIC BAC & AIMS
BAT
DBIDS
BISA
DRS
DoD Biometric Toolkit
EMIO
Migrate & Integrate
Inter-Agency and International Data Sharing
Consolidated Watchlists
MEPCOM
DEERS/RAPIDS
HSPD12
Implement
Tactics, Techniques, & Procedures (JFCOM, TRADOC/CALL) / Logical & Physical Access
Operationalize Detain, Release, Capture, Kill & Institutionalize Training / Execute ILSP
Collect
Store
Match
Append
Reference
Analyze
Share
Act
SOCOM
Next Generation ABIS
DoD Biometric Repository (ABIS Prototype)
Standardization
Data Flow, Fields
Process/TTPs
Configuration/GUI
Training
Integrated Logistics
Multi-Modal, Scalable
Service-Oriented
Architecture
24 x 7 Operations
Permanent Facilities
SIPRnet Website
SIPRnet , JWICS,
CENTRIX Web Portals
NCTC
TSC
FBI
IAFIS
DoD
ABIS
DHS
IDENT
Limited Data Sets
CONOPS-
Based
SIPR
HIIDE
Systems of systems approach to plan, analyze, organize and integrate the capabilities of a mix of existing or new systems into a capability greater than the sum of the capabilities of the constituent parts
Enterprise Roadmap – An End-to-End Approach
Notes: <number>
<footer>
<header>
<date/time>
Acronyms:
-- BAC = Biometric Analytic Cell
-- AIMS = Automated Identity Management System
-- BIR = Biometrics Intelligence Repository
Each arrow stems from a CONOPS-based action or activity….Collect, Store, Match….

## Slide 7: Bottom Line Upfront (BLUF)
Cost Estimate based on refinement of requirements and recent Tiger Team visit to AOR
  Overall costs for integrated, enterprise approach in CENTCOM AOR increased from $88M to $104.93M
  Costs will be refined based on gap analysis (especially key with share process)
CENTCOM focus for JUONS with a “eye” on the future enterprise
  Designed to ensure other COCOM requirements can be incorporated
  Dollars spent in CENTCOM AOR will be leveraged to support the biometric enterprise.
Ensures capitalization on synergies/technologies already created by G2/BAT& HIIDE, G3/DRS, PM, Biometrics/BISA, DMDC/DBIDs, PM Biometrics for SOCOM, Navy, Marines, Air Force
Contracting Strategy matches resources to functional mission while ensuring the ability to take immediate action towards meeting JUONS requirements

## Slide 8
CONOPS Development Requirements analysis and development Prototyping (software) Design Development System integration & testing Operational testing & certification Fielding Sustainment |  | 
FY06
FY07
FY08
JUONS Funding
POM Funding
Collect – Moving toward an Enterprise Solution
Tasks
1Qtr
2Qtr
3Qtr
4Qtr
1Qtr
2Qtr
3Qtr
4Qtr
1Qtr
2Qtr
3Qtr
4Qtr
Supports these Tiger Team Recommendations:
Instutionalize biometrics in doctrine
Identify how biometrics data is utilized, managed & supported within AoR
Review base access requirements
Develop comprehensive training plan
Develop/deploy “biometrics awareness” DVD
AoA for common collection capability
Standardize GUI
Approve minimum contextual data set
Centralize & fund an ILSP
JCIDS Analysis & formal POR
Legend:
Funded via JUONS
Funded via enterprise POM
$0.2 M OMA
$0.3 M OMA
$0.5 M RDT&E
$1.5 M RDT&E
$3 M RDT&E
$1 M RDT&E
$0.5M OMA
$6.0M RDT&E
Capitalize on synergy with
G2/BAT/HIIDE, PM/BISA, DMDC/DBIDS,
G3/DRS, PM/SOCOM, PM/Navy
Notes: PROPOSED SOLUTION. A system that enables rapid collection and near real time matching to a current watch list in an austere environment with an in-theater watch list that is updated regularly. This solution involves developing and integrating enterprise software with tactical man portable enrollment/verification devices that are ruggedized, simplified, smaller and light-weight.
CONOPS development
Requirements analysis and development for common hardware and software, standardized GUI, configurable based on mission, ruggedized and light-weight, communications flexibility, multi-modality (10 Print/Palm) capturing & matching, rapid capture, in-theater watchlist synchronization, data sync to configurable target server, logistics planning, research, market survey and AoA
Prototype to refine users requirements and expectations specifically focusing on GUI and mission configurability
Design. Develop project plans, hardware/software/system specifications, contractual documentations, and letters of agreement. This includes generating all documentation for as applicable aspects of logistics to enable a supported capability. Extensive focus will be place on training and Tactics, Techniques, and Procedures. Other documentation includes maintenance, manpower, supply support, support equipment, technical data, computer resource support, facilities, and design interfaces. All documentation to support transition to a program of records will be generated: programmatic, technical, and budgetary.
Development. Includes development, modification, and integration of hardware and software. The developing will include leveraging existing efforts (e.g Biometrics Automated Toolkit (BAT), BISA (Biometric Identification System for Access), and DBIDS (Defense Biometric Identification System), etc.
System Integration & Testing. Encompasses all tests required for software, middleware, components, subsystems, systems, and end-to-end assessments.
Operational Testing & Certification.
Fielding. Procurement of hardware will include systems for tests, training, and delivery to the user.
Sustainment. The project will support the development of a training plan (POI) and ILSP

## Slide 9
FY06
FY07
FY08
JUONS Funding
POM Funding
Store, Match, and Append – Moving toward an Enterprise Solution
Tasks
7x24 Operations (Labor) HelpDesk Full 7x24 Staffing including Certified Latent Examiners Replicate ABIS on the SIPR Side Repository Growth/Capacity (Material) COOP (Full and Active) Multi-modality Matching and Fusion Face Recognition Prototype Iris Prototype Fusion Prototype IOC Facial Recognition IOC Iris Search & Match IOC Fusion (Finger, Iris, & Facial) TM Enhancements (Material & Labor) Watch List Identity Counter Protection Web Services/Portal (SOA) Response format Piloting Web Services with secured messaging and secure collaboration FOC Web Services and Secured Web Portal Secure Ingest and Collaboration Secure Results Portal Secure Latent Submission portal | 
1Qtr
2Qtr
3Qtr
4Qtr
1Qtr
2Qtr
3Qtr
4Qtr
1Qtr
2Qtr
3Qtr
4Qtr
$8.5 M OMA
$8M OPA
$4 M OMA, $2 M OPA
$9.5 M RDT&E
$3 M OPA
Voice, DNA, etc.
current effort
Supports these Tiger Team Recommendations:
Evolve forensic exploitation capabilities
Implement Biometrics Enterprise JUONS
Improve core analysis and repository capability
Meet short-term operational requirements
current effort
$12.5M OMA
$9.5M RDT&E
$20 M OPA
$7M OPA
Notes: PROPOSED SOLUTION: The proposed solution will provide an initial multi-modal biometric capability to include local watch list synchronization, secure web portal access, and service-oriented architecture (web services). Multi-modal biometric capability will support a broad range of DoD applications to include but not limited to base access systems support, checkpoints, EMIO, detainee management, and intelligence activities. This capability will include fingerprint, face, and iris as well as planning/provisions for future capabilities such as DNA, hand geometry, and palm prints. Deliverables include:
  24x7 Operations to include additional resources for Help Desk operations, latent examiners, and systems operations support.
  Develop the architecture, while leveraging existing biometrics capabilities, that will provide a flexible, scaleable database to support multiple biometric modalities to include fingerprint, face, and iris as well as future capabilities such as DNA, hand geometry, and palm prints
  Incorporate a data management plan which is adaptable to dynamic DoD environment
  Replicate ABIS on SIPR side with synchronization between ABIS Red and Black with Guard Technology – increase interaction between NGIC and BFC (operators)
  Procure servers, storage arrays, databases and software to facilitate multi-modal and net-centric architecture with ability to scale and handle growth (enrollments, information sharing, and multi-modality)
  Provide the ability to concatenate results and consolidate identities from multi-modal searches and multi AFIS searches (i.e. FBI, DHS)
  Provide support for Watch List Synchronization to field systems
  Design in support of multiple languages, character sets (Unicode), and transliteration.
  Provide Integrated Identification and Verification Services
  Provide secure web portals, a service oriented architecture, and other secure mechanisms for system access
  COOP. Develop and implement a comprehensive disaster recovery and continuity of operations plan to prepare equipment, facility, and personnel for emergency situation. The prep will include purchase of equipment, installation and outfitting of the facility, initial “go live” testing and cut-over planning, configuration management, and re-occurring disaster plan testing.

## Slide 10
FY06
FY07
FY08
JUONS Funding
POM Funding
Share – Moving toward an Enterprise Solution
Tasks
1Qtr
2Qtr
3Qtr
4Qtr
1Qtr
2Qtr
3Qtr
4Qtr
1Qtr
2Qtr
3Qtr
4Qtr
Supports these Tiger Team Recommendations:
Establish Data Strategy
Implement Biometric Enterprise JUONS
Hand-selected team to conduct baseline system performance, replication, etc.
Complete analysis of End-End comms
Legend:
Funded via JUONS
Funded via enterprise POM
$11.25M OMA
$4.1M RDT&E
Conduct End-End Data, Comms, System Study
Initial “optimization” gap analysis followed by more
detailed assessment – Access traffic/comms, BAT
Server Replication, Data Flows, Flush out requirements
for in-theater server requirements
Prototype Tactical Comms Mesh Network
Develop/Field Theater Consolidation/Sync Servers
Improve Data Flow in Theater
Improve Comms from ABIS to Theater (NIPRnet)
Improve Comms from ABIS to NGIC
Develop Policy for Inter-Agency Sharing
Develop Policy for International Sharing
Improve Comms/Interagency Exchange
from ABIS/FBI/DHS
Improve and Maintain Watchlist Capability
$1 M OMA
$2 M OMA
$1 M OMA
$3 M OPA, $1 M OMA
current
$3 M RDT&E
$1 M OMA
$5.25 M OMA
current
current
$1.1 M RDT&E
current
$3M OPA
Difficult to estimate without
initial assessment
Costs may be low based on requirements
Notes: PROPOSED SOLUTIONS: The proposed solution will provide improvements and a way-forward to achieving end-to-end system communications; optimized process flow, including the development and implementation of theater-level servers for consolidation, synchronization, and responsive throughput; multi-level watchlist dissemination and matching capability; and inter-agency data sharing. Deliverables include:
Conduct INITIAL of an End-to-End Data, Comms, System Study –
Deploy team to AOR within next 30 days/3-5 Industry subject matter experts with MITRE + AWIPT team members
  Total time required to complete necessary optimization actions is 2 weeks
  Estimated cost is $100-220K
    Conduct BAT server replication analysis
    Conduct network traffic analysis—determine need for additional bandwidth
Prototype/Pilot Implementation of a Tactical Communications Mesh Network
Develop and Field Theater Consolidation/Sync Servers
Improve Data Flow in Theater
Improve Communications from ABIS to Theater
Improve Communications from ABIS to NGIC
Develop Policy for Inter-Agency Sharing
Develop Policy for International Sharing
Improve Communications/Interagency Exchange
Improve and Maintain Watchlist Capability

## Slide 11
4Qtr
1Qtr
2Qrt
3Qtr
4Qtr
FY06
FY07
JUONS Funding
Reference and Analyze – Moving toward an Enterprise Solution
Tasks
NGIC Mgmt & 24 Hr Ops Support & facility
NGIC – BIR Watch List Development/ Nomination and Management
Improve/Enhance CEXC-I/A Latent Collection Equipment
Analysts/Personnel:
CEXC/SSEs/WIT IED and High Value Material Biometric Related Collection
IDENT; CRRB IDENT Support
Off-Site Support for Navy Requirements
AIMS Enhancements; Repository Enhancements; IT Support/Security
Theater Deployable Forensic-Related Biometric Collection/Processing Lab and extra supplies
Theater Deployable Forensic-Related Biometric/Evidence Collection Kits (SEE& WITs); IED DNA Collection Enhancements
Supports these Tiger Team Recommendations:
Evolve forensic exploitation capabilities
On-line collaboration website/analysis
Dedicated contract support for operational rqmt
Identify dedicated personnel prior to fielding
Dedicated biometrics force structure
Improve core analysis and repository capability
$2.0 M OMA
$6.5 M OMA
$0.15 M OMA
$7.95 M OMA
$6.1 M OMA
$4.5 M OMA
$0.95 M OMA
$2.18 M OMA
$30.33M OMA

## Slide 12
FY06
FY07
FY08
JUONS Funding
POM Funding
Tasks
1Qtr
2Qtr
3Qtr
4Qtr
1Qtr
2Qtr
3Qtr
4Qtr
1Qtr
2Qtr
3Qtr
4Qtr
Supports these Tiger Team Recommendations:
Establish doctrinal workgroup
Transition from Rapid Equipment to coordinated DOTMLPF implementation
Instutionalize biometrics in doctrine
Develop comprehensive training plan
Establish biometrics distance learning capability
Institutionalize common training curriculum at service schools, command courses, training centers & mobilization exercises
Develop/Deploy biometrics awareness DVD series
Dedicated biometrics force structure
Establish a Joint/service skill identifier (e.g. ASI); common tasks/training
ID focal point in AOR for end-to-end sustainment
Develop a migration plan for centralized field service engineering
Centralize & fund an ILSP
Legend:
Funded via JUONS
Funded via enterprise POM
$7.75M OMA
$2..25 M OMA
Act – Moving toward an Enterprise Solution
Training
-Develop Training Videos
-Deploy Mobile Training Teams
-Schoolhouse coordination/planning. Institutionalize common training curriculum at service schools, command courses, training centers & mobilization exercises
-Coordinate with Distance Learning Program Office
Sustainment Planning
-Analyze support strategies for current systems/ID focal point in the AoR for end-to-end sustainment.
-Provide/Augment CENTCOM centralized biometrics operations support and begin migration to model.
-Leverage CENTCOM experience to develop plan for other COCOMs as part of centralized funded ILS
Operations
-Embed policy and requirements resources at OSD & Joint Staff
-Augment CENTCOM/MNFI with contractors (in short term) to support biometric operations in AOR – Accelerate on-going MNF-I C-6 efforts to standardize data collection process and methodology
-Establish Doctrine working group - Develop doctrine for known/existing situations to guide operations, maintenance,
and training
$ 0.5 M OMA
$5 M OMA
current
Notes: PROPOSED SOLUTIONS: The proposed solution will provide improvements and a way-forward to achieving end-to-end system communications; optimized process flow, including the development and implementation of theater-level servers for consolidation, synchronization, and responsive throughput; multi-level watchlist dissemination and matching capability; and inter-agency data sharing. Deliverables include:
Training:
Develop Combat Forensics Awareness Video and Evidence Collection & Latent Collection Training Video
Deploy Mobile Training Teams. This includes planning, formation and content management (e.g., Training Package, Equipment, Supplies, and Personnel for WIT, BAT, etc.)
Schoolhouse coordination/planning. Institutionalize common training curriculum at service schools, command courses, training centers & mobilization exercises.
Coordinate with Distance Learning Program Office to incorporate current and plan training content into DoD standard training format.
Sustainment Planning:
Analyze support strategies for current systems identify a focal point in the AoR for end-to-end sustainment.
Provide/Augment CENTCOM centralized biometrics operations support and begin migration to this model.
Leverage CENTCOM experience to develop plan for other COCOMs as part of centralized funded ILS program.
Operations:
Embed policy and requirements resources at OSD & Joint Staff Office
Augment CENTCOM/MNFI with contractors (in short term) to support biometric operations in AOR –
-Improve interoperability
  -Accelerate on-going MNF-I C-6 efforts to standardize data collection process and methodology
  -Support MNF-I C-6 ongoing efforts to enhance data strategy—expand across theater
Establish Doctrine working group
Develop doctrine for known/existing situations to guide operations, maintenance, and training

## Slide 13: Cost Summary – Totals by Task
OMA
OPA
RDTE
Collect
Store
Match
Append
$0M
$20M
$3M
$6M
$9.5M
$4.1M
$0M
$0M
$0M
$0M
$0.5M
$12.5M
$11.25M
$30.33M
$7.75M
Act
Analyze
Share
Sub Totals $6.5M
$42M
$18.35
$30.33M
$7.75M
Grand Total
$104.93M
Notes:
Original Request of $88M was for work performed over 9 month period (No OPA)
Current Estimate for OMA & RDT&E is $78.33M, OPA is $16M for work performed over 15 months
Total
$19.6M
$16.0M
$62.33M

## Slide 14: Cost Summary – By Qtr & Appropriation
Assumptions:
OPA funds will be burned immediately for equipment purchases, etc.
RDT&E and OMA funds will have an even burn rate.
FY06 funds are available for obligation immediately
FY07 funds are available for obligation at the beginning of the FY
OMA
OPA
RDTE
Q3/Q4
Q1
Q2
Q3
Q4
FY06
FY07
$8.5M
$7.5M
$7M
$2.62M
$5.62M
$4.12M
$4.12M
$3.12M
$0
$0
$13.9M
$15.75M
$12.28
$10.58M
$9.82
$25.02M
$28.87M
$23.4M
$14.7M
$12.94M
Total
$19.6M
$23.0M
$62.33M
Grand Total
$104.93M

## Slide 15: Contracting Strategy In General
Streamlining Contracting Strategy from 10 contracts to four performance-based contracts
  Operations
  S&T
  Enterprise Materiel Development/Systems Integration
  PM Support
Current CSC Prime RDT&E performing limited RDT&E, limited Product Testing, and Biometric Matching Operations (Total ~86 FTEs at BFC)
  S&T/RDT&E Contract – ID/IQ type contract to ramp up and down as necessary to support development of biometric enterprise
  Compete new Contract to support Biometric Matching Operations
Current LM Contract is for ABIS Development and Operations. Limited scope does not address enterprise. Sole source with ceiling.
  Competing new contract to support not only ABIS Development but an Enterprise Approach to ensure data access and sharing at tactical, operation, strategic (interagency levels).
All PM Support FTEs being wrapped up under Titan PMSS
Does not impact on numbers of FTEs in WV
Does not include Base Access mission/FTEs (separate slide)
Notes: <number>
<footer>
<header>
<date/time>
Key to our funding strategy is a detailed review of current contracts in place – as well as a proposed contracting strategy.

## Slide 16: Contracting Strategy
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
FY06
Apr
May
Jun
Jul
FY07
RA, EDSI, Titan resources wrapped up in one PMSS Contract for a total of ~30 FTEs.
PM Support Contract (Funded based on options) – 20FTEs
BFC EDSI IV&V (Funded through Jun 06) 7.2 FTEs
PM RA – 1 FTE
PM Titan / (Funded Incrementally) – 1 FTE
BFC CACI / (Funded Increment) – 4 FTEs
BFC Fed Consultant – 1 FTE
BFC BAH – 2 FTEs
BFC CSC Prime – 59 FTEs
BFC - CSC Prime – 59 FTEs. Use options to have CSC continue RDT&E efforts.
BFC - Compete operations work out at BFC. Currently operations are being conducted by CSC Prime (RDT&E).
PM LM / (Funded thru Sep 06) – 53 FTEs
Sole Source to LM x 6 months until ITES2 Protest Complete. Award date 23 July 2006. Expand ceiling. Expand scope to include Enterprise Development. ITES1 Ceiling too low.
Compete/Award Single, Performance-based Systems Integration (Enterrpise) Contract through ITES2. Award within 75 days of protest completion. Overall FTES increased in WV to meet Enteprise vise ABIS mission.
Does not include Contracts/FTEs associated with Base Access
Four Performance-based Contracts –
1-Operations
2-S&T
3-Materiel Development/System Integration
4-PM Support
No reduction of FTEs in WV.
ITES2 Protest Resolution
Six Mitre Stamps
assigned to PM to plan,
organize & execute required
assessments
Enterprise Systems Integration/Materiel Development Contracting Strategy is to award sole source contract to LM until current ITES2 protest is completed and can be utilized. Sole Source Justification – Urgent need + ITES1 has ceiling/do not want to re-compete within 1 – 2 years. Aggressive schedule with award date for sole source NLT 23 Jul 06. Final SOO, J&A, and IGCE due 31 May 06.
Notes: <number>
<footer>
<header>
<date/time>
Key to our funding strategy is a detailed review of current contracts in place – as well as a proposed contracting strategy.

## Slide 17
Base Access JUONs
  Base Access JUONS In General
  Requirements Revisited
  Costs Revisited
  Cost Summary
  Timeline
  Contracting Strategy
  Next Steps

## Slide 18
CENTCOM AOR
IRAQ
AFGHANISTAN
Tier 1 Site (existing)
Tier 2 Site (proposed)
Tier 1 Site (proposed)
10 Tier 1
55 Tier 2
10 Tier 1
30 Tier 2
19 Tier 1 Other AOR Sites
CENTCOM Base Access JUONS In General
Sustain Current 10 Tier 1 Sites in Iraq
Provide 10 Tier 1 Sites in Afghanistan
Provide 19 Tier 1 Sites in Other AOR Sites (Outside Iraq and Afghanistan)
Provide 85 Tier 2 Sites in Iraq and Afghanistan

## Slide 19: Requirements Revisited
Common Requirements (Tier I and II)
  Separation of functions (person that does enrollment cannot print the credential)
  Capable of handling all population groups
    DOD Personnel already in possession of CAC
    Local and third country nationals (Authorized to perform full biometric enrollment)
    Coalition partners (Biometric enrollment not currently authorized)
    Non-DOD US Persons (policy and implementation guidance signed)
    Day Workers (Need to screen against known databases, need to track, will not issue credential)
  Capable of processing minimum of 4 enrollments per hour per enrollment station (# of stations tied to specific sites at spreadsheets)
  Must be able to transmit enrollment data within 30 minutes of collection moved to Tier 1 & Tier 2 specific reqts
  Must be able to collect minimum to DoD Standards (5 facial photos, 1 iris scan, and 10 rolled print , 2 slaps)
  Must be able to connect to the local power grid
  Must be capable of connecting to network and producing other various media for transmission of data
  Must be able to produce a PIN-enable card complete with PIN-reset capability
  Must at a minimum be able to provide minimum two-factor verification at the ECPs (ie. biometric & PIN or Token)
  Ability to screen enrollment data against ABIS and other USG databases
  Idents (records that match 1 or more existing records) must be adjudicated by appropriate authority prior to credential production
  Must have network connectivity to ECPs or standalone verification capability
  Self-contained system (Cannot burden local commander for equipment, power, trailers, buildings, etc.) modified for Tier 1
  Controlled environment at enrollment and credential production/issuance facility modified for Tier 1
  Cannot burden the current communication’s infrastructure, Moved and modified for Tier 1 only
  Operations and support personnel must be provided Moved to Tier 1 only
    SAs and card production personnel need secret clearances
    Enrollers/System Operators must be US Persons w/ minimum NACI
  Initial and sustainment training must be provided
  24x7 ABIS Operations and help/online help must be available
  Equipment must operate reliably in CENTCOM AOR environment
  System must include adequate spares
Clarifications impacted costs –
1 – Reduced number of enrollment stations/enrollers
2 – Comms availability at Tier 2 sites
3 – Mil. manpower vs contracted manpower at Tier 2

## Slide 20
See Spreadsheets
Refined Requirements

## Slide 21
Costs Revisited – Old Costs
Tier I
Equipment ($1.80M)
Labor ($3.76M)
Communications ($710K)
Transportation ($287K)
$6.3M per Tier 1 Site
29 Tier I Sites: $183M
Tier II
Equipment ($39.1K)
Labor ($0)
Communications ($522K)
Transportation ($500)
$562K per Tier II Site
85 Tier II Sites: $47.7M
Sustainment/Forward Cell
Equipment ($424K)
Labor ($31.2M)
Communications ($1.9)
Transportation ($1K)
Current 10 Site Sustainment: $28.5M
Expanded 2 FWD Teams: $6.6M
Total: $40.1M

## Slide 22: Cost Summary – TOTAL
$109,962,454.36
$128,830,321.47
Iraq Cost $41,532,520.61 $48,594,154.61
Afghanistan Cost $35,150,479.89 $39,100,148.73
Other AOR Cost $32,185,453.85 $39,641,351.13
WV 24X7 Operations $ 1,121,000.00 $ 1,494,667.00
12 month cost
16 month cost
OPA $29,239,628.00
OMA $99,590,693.47

## Slide 23: Cost Summary – by Qtr & Appropriation
All OPA funding in Q3/4 FY06
OPA funding for Afghanistan and Other AOR in Q1 FY06
OMA funding for WV Operations spread over FY06-FY07
OMA funding for Iraq and Afghanistan spread over FY06-FY07
OMA funding for Other AOR spread over FY07
OMA Day Workers
OMA
OPA
RDTE
Q3/Q4
Q1
Q2
Q3
Q4
FY06
FY07
$0
$0
$0
$0
$0
$0
$0
$0
$0
$48.3M
$32.4M
$29.2M
$18.9M
$0
$0
Total
$0
$29.2M
$99.6M
$77.5M
$32.4M
$18.9M
$0M
$0M
Grand Total $128.8M
Additional Costs Not Included (Working Requirements/ROMs)
Formal Testing
Unit Pre-Deployment Training
Development of TTPs/CONOPS
Out-year Sustainment
Totals

## Slide 24: PM Proposed Timeline
Critical Path items only shown…
Iraq/Afg (tier 2)
0
30
60
90
120
150
180
210
240
270
Funding
Initial Testing/ CONOPS
Design/Development
Integration Testing
Operational Testing
Production/Fabrication
Deployment/Operation
Afghanistan (tier 1)
Site Surveys
Site Prep
Production/Fabrication
Deployment/Operation
Site Surveys
Equipment Purchase/Ship
Deployment/Operation
Other AOR
IOC
FOC
IOC
FOC
IOC
FOC
BISA Contract Award
Day Worker Solution
Initial Testing/ CONOPS
Design/Development
Integration Testing
Operational Testing
Production/Fabrication
IOC
FOC
Deployment/Operation
CENTCOM Requirements
Tier II in Iraq: 60 days
All sites in Afghanistan: 150 days
Tier I in Other AOR: 150 days
Still an aggressive timeline!
CENTCOM Concern:
Required Timelines not met
Site Prep

## Slide 25: Base Access Contracting Strategy
Other AOR – Existing DBIDS contract vehicles available for immediate obligation of funds and commencement of work
  DMDC has existing enterprise vehicles to support worldwide implementation of DBIDS (COTS H/W & S/W, Procurement, Installation and Maintenance, Worldwide 24x7/365 User Support; Training; Software Development; Program Management, etc.) We currently support over 200 sites world-wide today.
  PM/Technical Support Contract via NIH CIOSP2, Bearing Point: technical, functional, analytical, administrative, acquisition, resource and project management expertise, services, and deliverables PoP, 5 years with a start date of 3/4/05. Contract Ceiling: $36.2M
  FFP Maintenance, HW/SW procurement, via GSA Kansas City, Telos, POP 4 August 2005 with 2 option years, ceiling $41.6M
  User Support, EDS, via GSA Kansas City: Database server installations and on-going administration worldwide; Communications engineering, support centers, OCONUS Support for Existing and New Sites: site support activities, hardware maintenance/warranty support, site installations, de-installations, site relocations, on-site training , user liaison, system and infrastructure support, worldwide user support analysis, world-wide user Help Desk/Support 24x7 / 365, Cardstock and Consumables, POP 31 May 2005, 5 option years, ceiling $61.3M
Day worker and Tier 2 solutions design and initial testing and site surveys – Sole Source Urgent Operations Cell Contract with Ideal Innovations Inc (I3), funded and initiated through the REF – award expected 6 June 2006 ($1.169M ceiling)
Deployment and sustainment of tier 1 and tier 2 in Iraq and Afghanistan – PWS being prepared to wrap existing BISA contracts/task orders (see next slide) into a single performance based task order against a recently awarded GWAC C4ISR contract – TO Award expected NLT 15 Aug 06
  Contract awarded March 2006
  Ceiling--$19.25B over 10 year period; POP--5 year base and one 5 year option (2016).

## Slide 26: Existing BISA Contracts/TOs
May
Jun
Jul
Aug
Sep
Nov
Dec
Jan
Feb
Mar
Apr
Mar
Feb
BISA x 8 Build CSC / POP is Base Year – 1 Option Year Available - $11.427M
(Funded through Jun 06)
BISA Smart Cards/BISA Upgrades NGIT / POP is 1.5 Years 27 Dec 04 – 30 Jun 06 - $7.9M (Funded through Jun 06)
BISA Manning CSC (10 SAs) / POP is Base Year – 1 Option Year Available - $4.543M (Funded through Aug 06)
BISA Enrollment Dyncorps / POP is Base Year – 1 / 2 Option Year Available - $17.07M (Funded through 6 Sep 06)
BISA I3 Support / POP is Base 1.5 Years 20 May 05 – 19 Nov 06 - $9.636M (Funded through Nov 06)
BISA Rental Car – POP Sep 05 to Aug 06 - $94K
(Funded through Aug 06)
BISA VSAT Support – POP Aug 05 to Aug 06 - $2.816M (Funded through Aug 06)
BISA Financial/Contract Oversight – Eskridge / POP 6/05 to 6/08 - $190K (Funded through June 06)
$290K
$13K
$667K
BISA Spend Plan extends major
contract until 30 Sep 06
1 Year Option available for BISA Site Build.
Will be extended until Sep 06, funded with OPA to complete retrofit of Iraq tier 1 sites.
$1.5M
$48K
$400K OPA
(Technical Personnel Only)
Oct
-Working to extend, mod, exercise options as needed to carry current contracts to 30 Sep 06
-Contracting strategy is to use existing GWAC contract to roll all the above except VSAT (support and airtime through PM DWTS) into one performance based Task Order. Award NLT 15 Aug 06.
FY06
FY07
Notes: <number>
<footer>
<header>
<date/time>

## Slide 27: Next Steps…. Enterprise & Base Access JUONS
Establish assessment teams, doctrine working groups, and mobile training teams and begin execution
Execute contracting strategies to meet award dates
Begin ABIS Enhancements using current contracts (key…24x7 Support)
Begin Base Access using current contracts
Coordinate with OSD, JS, CENTCOM and other COCOMS to establish/embed appropriate support for policy, doctrine, and operational support
Complete detailed, integrated master schedule/project plan
Schedule appropriate IPRs with user
Develop enterprise level risk management plan
Begin developing enterprise level training plans & integrated logistic support plans
Refine, refine, refine….

## Slide 28
DoD Biometrics Contact Information
BMO
Director:
Dr. Joseph Guzman
Phone:
703-602-5427
E-mail:
joseph.m.guzman@us.army.mil
BFC
Director:
Mr. Sam Cava
Phone:
304-326-3004
E-mail:
samuel.cava@us.army.mil
www.biometrics.dod.mil
Subscribe to the DoD Biometrics Newsletter at www.biometrics.dod.mil/subscription.aspx
PM
Program Manager:
LTC Debora Theall
Phone:
703-980-8783
703-919-9091
E-mail:
debora-theall@us.army.mil
DIR, DOD BIOMETRICS
Director:
COL David Scarbalis
Phone:
703-602-5427
E-mail:
david.scarbalis@us.army.mil
DEP DIR,
DOD BIOMETRICS
Director:
COL Steve Bristow
Phone:
703-806-0538
E-mail:
james.bristow@us.army.mil