## 6807- 04X
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002A, Delivery Order T0799BG0424
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | Feb 10, 1999 to Feb 9, 2000
Level of Effort - Monthly invoicing for hours delivered and other direct cost expenditures.
LABOR ESTIMATE
Current Order Through 6-30-99
Labor Category | Actual Cost to Date |  | Sced Cost
Senior Computer Systems Analyst (On-Site) | 11761.39 |  | 0
Functional Analyst (On-Site) | 83995.28 |  | 0
Junior Database Management Specialist (On-site) | 18998.1 |  | 0
TOTAL LABOR | 114754.77
ODC's | 8109.76 |  | 0
TOTAL | 122864.53 | #DIV/0! | 0 | #DIV/0!
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002A, Delivery Order T0799BG0424
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | Feb 10, 1999 to Feb 9, 2000
LABOR ESTIMATE
Current Order From 7/1/99 through Contract End Date:
Labor Category | ETC From July 1st to end of contract |  | Sced Cost
Senior Computer Systems Analyst (On-Site) | 427537.61 |  | #VALUE!
Functional Analyst (On-Site) | 597880.72 |  | #VALUE!
Junior Database Management Specialist (On-site) | 66447.9 |  | #VALUE!
TOTAL LABOR | 1091866.23
ODC's | 241890.24 |  | #VALUE!
TOTAL | 1333756.47 | #VALUE! | #VALUE! | #DIV/0!
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.

## 6807-05X
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002C, Delivery Order T0799BG0425
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | Feb 10, 1999 to Feb 9, 2000
LABOR ESTIMATE
Current Order Through 6-30-99
Labor Category | Actual Cost to Date |  | Sced Cost
Senior Applications Engineer (On-Site) | 50457.83 |  | 0
Senior Training Specialist (Off-Site) | 22546.3 |  | 0
Training Specialist (Off-Site) | 12290.72 |  | 0
Functional Analyst (Off-Site) | 28638.66
Technical Writer ( Off-Site) | 14498.55
Administration Support (On-Site) | 21025
TOTAL LABOR | 149457.06
ODC's | 86828.43 |  | 0
TOTAL | 236285.49 | #DIV/0! | 0 | #DIV/0!
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002C, Delivery Order T0799BG0425
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | Feb 10, 1999 to Feb 9, 2000
Level of Effort - Monthly invoicing for hours delivered and other direct cost expenditures.
LABOR ESTIMATE
Current Order From 7/1/99 through Contract End Date:
Labor Category | ETC From July 1st to end of contract |  | Sced Cost
Senior Applications Engineer (On-Site) | 104924.17 |  | #VALUE!
Senior Training Specialist (Off-Site) | 114186.1 |  | #VALUE!
Training Specialist (Off-Site) | 98798.48 |  | #VALUE!
Functional Analyst (Off-Site) | 96136.94
Technical Writer ( Off-Site) | 70947.45
Administration Support (On-Site) | 42218.2
TOTAL LABOR | 527211.34
ODC's | 38171.57 |  | #VALUE!
TOTAL | 565382.91 | #VALUE! | #VALUE! | #DIV/0!
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.

## 6807-07X
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002D, Delivery Order T0799BG0457
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | Feb 19, 1999 to Feb 18, 2000
LABOR ESTIMATE
Current Order Through 6-30-99
Labor Category | Actual Cost to Date |  |  | Sced Cost
Functional Analyst (On-Site) | 64804.44 |  |  | 0
Junior Network Engineer (On-Site) | 0 |  |  | 0
Senior Hardware Maintenance/Installation Technician (Off-Site) | 8412.96 |  |  | 0
Hardware Maintenance/Installation Technician (Off-Site) | 0
Senior Computer Systems Analyst (Off-Site) | 0
Computer Systems Analyst (Off-Site) | 10644.2
Junior Database Management Specialist (Off-Site) | 23032.56
Data Entry Clerk (Off-Site) | 0
TOTAL LABOR | 106894.16
ODC's | 1494643.74 |  |  | 0
TOTAL | 1601537.9 |  | #DIV/0! | 0 | #DIV/0!
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002D, Delivery Order T0799BG0457
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | Feb 10, 1999 to Feb 9, 2000
Level of Effort - Monthly invoicing for hours delivered and other direct cost expenditures.
LABOR ESTIMATE
Current Order From 7/1/99 through Contract End Date:
Labor Category | ETC From July 1st to end of contract |  |  | Sced Cost
Functional Analyst (On-Site) | 549579.56 |  |  | #VALUE!
Junior Network Engineer (On-Site) | 506284 |  |  | #VALUE!
Senior Hardware Maintenance/Installation Technician (Off-Site) | 689367.84 |  |  | #VALUE!
Hardware Maintenance/Installation Technician (Off-Site) | 579115.2
Senior Computer Systems Analyst (Off-Site) | 163221.6
Computer Systems Analyst (Off-Site) | 132292.2
Junior Database Management Specialist (Off-Site) | 166885.04
Data Entry Clerk (Off-Site) | 55554
TOTAL LABOR | 2842299.44 | 2949193.6
ODC's | 1725356.26 | 3220000
TOTAL | 4567655.7
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.

## 6807-08X
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002B, Delivery Order T0799BG0492
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | March 04, 1999 to March 03, 2000
LABOR ESTIMATE
Current Order Through 6-30-99
Labor Category | Actual Cost to Date |  | Sced Cost
Senior Hardware Maintenance/Installation Technician (On-Site) | 32021.28 |  | 0
Hardware Maintenance/Installation Technician (On-Site) | 58110.62 |  | 0
Engineer | 3715.35 |  | 0
Administration Support | 18232.88
TOTAL LABOR | 112080.13
ODC's | 0 |  | 0
TOTAL | 112080.13 | #DIV/0! | 0 | #DIV/0!
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002B, Delivery Order T0799BG0492
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | Feb 10, 1999 to Feb 9, 2000
Level of Effort - Monthly invoicing for hours delivered and other direct cost expenditures.
LABOR ESTIMATE
Current Order From 7/1/99 through Contract End Date:
Labor Category | ETC From July 1st to end of contract |  | Sced Cost
Senior Hardware Maintenance/Installation Technician (On-Site) | 171357.12 |  | #VALUE!
Hardware Maintenance/Installation Technician (On-Site) | 770781.38 |  | #VALUE!
Engineer | 133242.65 |  | #VALUE!
Administration Support | 45010.32
TOTAL LABOR | 1120391.47
ODC's | 420000
TOTAL | 1540391.47
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.

## 6807-09X
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002E, Delivery Order T0799BG0517
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | March 10, 1999 to March 09, 2000
LABOR ESTIMATE
Current Order Through 6-30-99
Labor Category | Actual Cost to Date |  | Sced Cost
Senior Hardware Maintenance/Installations Technician (On-Site) | 68937.71 |  | 0
Hardware Maintenance/Installations Technician (On-Site) | 55310.91
Administrative Support | 12278.6
Date Entry Clerk (On-Site) | 6807.04
TOTAL LABOR | 143334.26
ODC's | 17110.16 |  | 0
TOTAL | 160444.42 | #DIV/0! | 0 | #DIV/0!
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.
To: Ms. Gwayne Walker, Contracting Officer, GSA FTS
From: Ms. Sue Siegel, ManTech Advanced Systems International
Reference: Bid number FG199002E, Delivery Order T0799BG0517
ManTech is pleased to provide the following level of effort cost estimate to support the request referencing GSA web-based on-line ordering system.
Information Technology Services Contract - GS-35F-4660G.
Cost Estimate to support the Department of State Evaluations and Audits Branch in response to request regarding web based on-line ordering system
provided by your office.
Prepared by: | ManTech Advanced Systems International
GSA Schedule for Information Technology Services: GS-35F-4660G
Prepared: | 1999-07-12
Period of Performance: | March 10, 1999 to March 09, 2000
LABOR ESTIMATE
Current Order From 7/1/99 through Contract End Date:
Labor Category | ETC From July 1st to end of contract |  | Sced Cost
Senior Hardware Maintenance/Installations Technician (On-Site) | 337819.09 |  | #VALUE!
Hardware Maintenance/Installations Technician (On-Site) | 1270916.29 |  | #VALUE!
Administrative Support | 114207.8 |  | #VALUE!
Date Entry Clerk (On-Site) | 43182.16
TOTAL LABOR | 1766125.34
ODC's | 192889.84
TOTAL | 1959015.18
If you have any questions, or require additional information, please contact Ms. Sue Siegel at 703-633-1320, fax to 703-633-1301.