## LBE Hawaii
ASC L/T NO. | RECEIPT DATE | FORSCOM L/T NO. | DTG | AFSB | FROM UNIT | INSTL | GAINING UNIT | INSTL | LIN | IN LIEU | NOUN NOMENCLATURE | SCMC | COMMODITY | QTY RQSTD | SUSPENSE | ACTUAL QTY TRANSFERRED | COMPLETED OR IN PROCESS | COMPLETED DATE | TYPE TRANSACTION | TRANSFER STANDARD | REMARKS
ASC 0712-01 | 2007-12-01 | email | 231525ZOct07 | 404th | 552nd MP | SBHI | 524th CSSB | SBHI | T92310 |  | Trk Util M1026 | 7K | Wheel | 10 | 2008-01-15 | 10 | Completed | 2008-10-17 | Temp Loan | TM 10/20 | Equipment inducted back into LBE
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | B Co. 2/11 | SBHI | 84th Eng | SBHI | M60256 |  | Mount, MG192 | 7M | Ground Support | 4 | 2008-05-09 | 0 |  |  | Temp Loan | TM 10/20 | Not issued, equipment was wrong type
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | HHC 1/27 | SBHI | 84th Eng | SBHI | M12647 |  | Mount, MG93 | 2M | Ground Support | 1 | 2008-05-09 | 0 |  |  | Temp Loan | TM 10/20 | Not issued, equipment was wrong type
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | HHC 1/14 | SBHI | 84th Eng | SBHI | L91975 |  | MG, 50 Cal | 7M | Weapon | 1 | 2008-05-09 | 0 |  |  | Temp Loan | TM 10/20 | Did not issue, equipment was NMC
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | 536th Maint | SBHI | 84th Eng | SBHI | T63093 |  | Trk Wkr M984 | 7K | Wheel | 2 | 2008-05-09 | 2 | Completed | 2008-09-29 | Temp Loan | TM 10/20
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | B Co. 225 | SBHI | 84th Eng | SBHI | T63093 |  | Trk Wkr M984 | 7K | Wheel | 1 | 2008-05-09 | 1 | Completed | 2008-09-29 | Temp Loan | TM 10/20
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | HHC 2/11 | SBHI | 84th Eng | SBHI | T61908 |  | Trk Cgo M1083 | 7K | Wheel | 1 | 2008-05-09 | 1 | Completed | 2008-09-29 | Temp Loan | TM 10/20
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | B Co. 225 | SBHI | 84th Eng | SBHI | T61908 |  | Trk Cgo M1083 | 7K | Wheel | 3 | 2008-05-09 | 3 | Completed | 2008-09-29 | Temp Loan | TM 10/20
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | HHC 225 | SBHI | 84th Eng | SBHI | T61908 |  | Trk Cgo M1083 | 7K | Wheel | 1 | 2008-05-09 | 1 | Completed | 2008-09-29 | Temp Loan | TM 10/20
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | B Co. 2/14 | SBHI | 84th Eng | SBHI | T61908 |  | Trk Cgo M1083 | 7K | Wheel | 2 | 2008-05-09 | 2 | Completed | 2008-09-29 | Temp Loan | TM 10/20
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | C Co. 2/14 | SBHI | 84th Eng | SBHI | T61908 |  | Trk Cgo M1083 | 7K | Wheel | 1 | 2008-05-09 | 1 | Completed | 2008-09-29 | Temp Loan | TM 10/20
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | HHC 2/11 | SBHI | 84th Eng | SBHI | T38844 |  | Trk M997 FLA | 7K | Wheel | 2 | 2008-05-09 | 2 | Completed | 2008-09-29 | Temp Loan | TM 10/20
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | 66th Eng | SBHI | 65th Eng | SBHI | T93761 |  | Trlr PLS M1076 | 7K | Trailer | 4 | 2008-05-09 | 4 | In Progress |  | Temp Loan | TM 10/20 | MIPR being processed for BII shortages
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | 66th Eng | SBHI | 65th Eng | SBHI | B83002 |  | Flat Rack, IPF | 7K | Trailer | 8 | 2008-05-09 | 5 | In Progress |  | Temp Loan | TM 10/20 | Unit rejected 3 x Flatrack
ASC 0803-44-CH2 | 2008-03-27 | email | 2008-03-27 | 404th | 66th Eng | SBHI | 65th Eng | SBHI | T38844 |  | Trk M997 FLA | 7K | Wheel | 2 | 2008-05-09 | 2 | In Progress |  | Temp Loan | TM 10/20 | MIPR being processed for BII shortages
ASC 0804-07-CH1 | 2008-04-22 | email | 2008-04-22 | 404th | B Co. 225 | SBHI | B Co. 325 | SBHI | S01427 |  | Shelter (S250/G) | 7G | Ground Support | 1 | 2008-05-18 | 1 | Completed | 2008-06-25 | Lateral Transfer | TM 10/20
ASC 0804-07-CH1 | 2008-04-22 | email | 2008-04-22 | 404th | B Co. 225 | SBHI | D Co. 325 | SBHI | S01427 |  | Shelter (S250/G) | 7G | Ground Support | 1 | 2008-05-18 | 1 | Completed | 2008-05-07 | Lateral Transfer | TM 10/20
ASC 0804-07-CH1 | 2008-04-22 | email | 2008-04-22 | 404th | B Co. 225 | SBHI | A Trp 3/4 Cav | SBHI | S01427 |  | Shelter (S250/G) | 7G | Ground Support | 1 | 2008-05-18 | 0 |  |  | Lateral Transfer | TM 10/20 | Unit rejected did not have platform
ASC 0804-07-CH1 | 2008-04-22 | email | 2008-04-22 | 404th | B Co. 225 | SBHI | B Trp 3/4 Cav | SBHI | S01427 |  | Shelter (S250/G) | 7G | Ground Support | 1 | 2008-05-18 | 1 | Completed | 2008-05-07 | Lateral Transfer | TM 10/20
ASC 0804-07-CH1 | 2008-04-22 | email | 2008-04-22 | 404th | B Co. 225 | SBHI | HHT 3/4 Cav | SBHI | S01427 |  | Shelter (S250/G) | 7G | Ground Support | 1 | 2008-05-18 | 0 |  |  | Lateral Transfer | TM 10/20 | Unit rejected did not need, wanted refrigerated type
ASC 0804-07-CH1 | 2008-04-22 | email | 2008-04-22 | 404th | B Co. 225 | SBHI | B Co. STB | SBHI | S01427 |  | Shelter (S250/G) | 7G | Ground Support | 1 | 2008-05-18 | 1 | Completed | 2008-05-07 | Lateral Transfer | TM 10/20
ASC 0804-54 | 2008-04-24 | email | 2008-04-24 | 404th | HHC 2/11 | SBHI | 25th ID STB | SBHI | T38844 |  | Trk M997 FLA | 7K | Wheel | 1 | 2008-04-30 | 1 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-54 | 2008-04-24 | email | 2008-04-24 | 404th | C Co. 225 | SBHI | 25th ID STB | SBHI | T38844 |  | Trk M997 FLA | 7K | Wheel | 1 | 2008-04-30 | 1 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | C Co. 225 | SBHI | HHC 2/27 | SBHI | T38844 |  | Trk M997 FLA | 7K | Wheel | 2 | 2008-04-30 | 2 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | C Co. 225 | SBHI | HHC 2/35 | SBHI | T38844 |  | Trk M997 FLA | 7K | Wheel | 2 | 2008-04-30 | 2 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | C Co. 225 | SBHI | HHT 3/4 Cav | SBHI | T38844 |  | Trk M997 FLA | 7K | Wheel | 3 | 2008-04-30 | 3 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | C Co. 225 | SBHI | HHB 3/7 FA | SBHI | T38844 |  | Trk M997 FLA | 7K | Wheel | 1 | 2008-04-30 | 0 |  |  | Temp Loan | TM 10/20 | Unit rejected equipment not needed
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | C Co. 225 | SBHI | HSC 325 BSB | SBHI | T38844 |  | Trk M997 FLA | 7K | Wheel | 4 | 2008-04-30 | 4 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | 552 MP | SBHI | HHC 2/27 | SBHI | T92242 |  | Trk Util M1025 | 7K | Wheel | 5 | 2008-04-30 | 5 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | 552 MP | SBHI | HHB 3/7 FA | SBHI | T92242 |  | Trk Util M1025 | 7K | Wheel | 16 | 2008-04-30 | 0 |  |  | Temp Loan | TM 10/20 | Unit rejected equipment not needed
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | 552 MP | SBHI | HHC 2/27 | SBHI | T92310 |  | Trk Util M1026 | 7K | Wheel | 5 | 2008-04-30 | 5 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | 552 MP | SBHI | HSC 325 BSB | SBHI | T92310 |  | Trk Util M1026 | 7K | Wheel | 3 | 2008-04-30 | 3 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | 58th MP | SBHI | HHC 2/35 | SBHI | T92242 |  | Trk Util M1025 | 7K | Wheel | 10 | 2008-04-30 | 10 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | A Co. 2/11 | SBHI | HHC 2/35 | SBHI | T92242 |  | Trk Util M1025 | 7K | Wheel | 1 | 2008-04-30 | 1 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | 66th Eng | SBHI | HHC 2/35 | SBHI | T92242 |  | Trk Util M1025 | 7K | Wheel | 1 | 2008-04-30 | 1 | Completed | 2008-10-08 | Temp Loan | TM 10/20
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | 728th MP | SBHI | A Co. 325 BSB | SBHI | W98825 |  | Tank Wtr M149A2 | 7K | Trailer | 1 | 2008-04-30 | 0 |  |  | Temp Loan | TM 10/20 | Equipment deployed to Iraq
ASC 0804-55-Ch1 | 2008-06-13 | email | 2008-06-13 | 404th | 185th MI | SBHI | A Co. 325 BSB | SBHI | W98825 |  | Tank Wtr M149A2 | 7K | Trailer | 1 | 2008-04-30 | 0 |  |  | Temp Loan | TM 10/20 | Equipment deployed to Iraq
ASC 0805-29 | 2008-05-20 | email | 2008-05-20 | 404th | 82nd Eng | SBHI | DOL | SBHI | L76321 |  | Loader Scoop | 7W | Engineer | 1 | 2008-07-05 | 1 | Completed | 2008-10-01 | Turn In | As Is Complete
ASC 0805-29 | 2008-05-20 | email | 2008-05-20 | 404th | B Co. 225 | SBHI | DOL | SBHI | B83002 |  | Bed, Flatrack | 7K | Trailer | 5 | 2008-07-05 | 5 | Completed | 2008-06-06 | Turn In | As Is Complete
ASC 0806-03 | 2008-06-03 | email | 2008-07-16 | 404th | C Co. 1/21 | SBHI | DOL | SBHI | N04732 |  | PVS-4 w/IMG | 7G | Optics | 33 | 2008-07-16 | 33 | Completed | 2008-07-09 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | B Co. 1/27 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 18 | 2008-07-20 | 18 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | C Co. 1/27 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 19 | 2008-07-20 | 19 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | HHC 1/27 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 11 | 2008-07-20 | 11 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | A Co. 1/14 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 20 | 2008-07-20 | 20 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | B Co. 1/14 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 19 | 2008-07-20 | 19 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | C Co. 1/14 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 19 | 2008-07-20 | 19 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | A Co. 1/21 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 14 | 2008-07-20 | 14 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | B Co. 1/21 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 21 | 2008-07-20 | 21 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | C Co. 1/21 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 17 | 2008-07-20 | 17 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-04 | 2008-06-04 | email | 2008-06-04 | 404th | HHC 1/21 | SBHI | Tobyhanna | PA | R55336 |  | Radio PRC-126 | 7G | COMMEL | 7 | 2008-07-20 | 7 | Completed | 2008-06-24 | Turn In | As Is w/SA
ASC 0806-37 | 2008-06-26 | email | 2008-06-26 | 404th | HHC 1/14 | SBHI | DOL | SBHI | L91975 |  | MG, 50 Cal | 7M | Weapon | 1 | 2008-08-10 | 1 | Completed | 2008-06-07 | Turn In | As Is
ASC 0806-38 | 2008-06-30 | email | 2008-06-30 | 404th | 82nd Eng | SBHI | DOL | SBHI | S74832 |  | STLR M750 | 7K | Trailer | 2 | 2008-08-15 | 2 | Completed | 2008-07-31 | Turn In | As Is
ASC 0806-38 | 2008-06-30 | email | 2008-06-30 | 404th | 82nd Eng | SBHI | DOL | SBHI | T10275 |  | Shop Equip | 7B | Trailer | 1 | 2008-08-15 | 1 | Completed | 2008-07-31 | Turn In | As Is
ASC 0807-05 | 2008-07-03 | email | 2008-07-03 | 404th | 552nd MP | SBHI | TAMC | SBHI | NA0567 |  | Diazepam Injectors | 81 | Medical | 203 | 2008-08-15 | 203 | Completed | 2008-07-02 | Lateral Transfer
ASC 0807-11 | 2008-07-08 | email | 2008-07-08 | 404th | A Co. 225 | SBHI | DOL | SBHI | B83002 |  | Bed, Flatrack | 7K | Trailer | 1 | 2008-08-25 | 1 | Completed | 2008-07-25 | Turn In | As Is
ASC 0807-11 | 2008-07-08 | email | 2008-07-08 | 404th | A Co. 225 | SBHI | DOL | SBHI | X40794 |  | Trk Cgo M923A1 | 7K | Wheel | 1 | 2008-08-25 | 1 | Completed | 2008-07-11 | Turn In | As Is
ASC 0809-37 | 2008-09-22 | email | 2008-09-22 | 404th | 25th ID Band | SBHI | 25th ID Band | SBHI | T61494 |  | Trk Util M998 | 7K | Wheel | 1 | 2008-11-06 | 1 | Completed | 2008-10-01 | Turn In | TM 10/20
ASC 0809-52 | 2008-09-26 | email | 2008-09-26 | 404th | HHC 2/27 | SBHI | DOL | SBHI | W95537 |  | Trlr M101A1 | 7K | Trailer | 6 | 2008-11-11 | 6 | Completed | 2008-10-21 | Turn In | As Is
ASC 0809-52 | 2008-09-26 | email | 2008-09-26 | 404th | HHC 2/27 | SBHI | DOL | SBHI | W95537 |  | Trlr M101 | 7K | Trailer | 1 | 2008-11-11 | 1 | Completed | 2008-10-22 | Turn In | As Is
ASC 0809-52 | 2008-09-26 | email | 2008-09-26 | 404th | HHC 2/27 | SBHI | DOL | SBHI | W95537 |  | Trlr M101A2 | 7K | Trailer | 1 | 2008-11-11 | 1 | Completed | 2008-10-22 | Turn In | As Is
ASC 0809-55 | 2008-09-29 | email | 2008-09-29 | 404th | PBO Manged | SBHI | RRAD | TX | T61494 |  | Trk M998A1 | 7K | Wheel | 1 | 2008-11-15 | 0 | Cancelled | 2008-12-01 | Turn In | As Is Complete | Directive changed to L/T ASC 0811-54
ASC 0809-55 | 2008-09-29 | email | 2008-09-29 | 404th | PBO Manged | SBHI | RRD | TX | T07679 |  | Trk M1097 | 7K | Wheel | 3 | 2008-11-15 | 0 | Cancelled | 2008-12-01 | Turn In | As Is Complete | Directive changed to L/T ASC 0811-54
ASC 0810-13 | 2008-10-06 | email | 2008-10-06 | 404th | HHC 2/27 | SBHI | DOL | SBHI | W95537 |  | Trlr M101A2 | 7K | Trailer | 1 | 2008-11-05 | 1 | Completed | 2008-10-22 | Turn In | As Is
ASC 0810-33 | 2008-09-29 | email | 2008-09-29 | 404th | 25th Trans | SBHI | DOL | SBHI | S70027 |  | STLR M871 | 7K | Trailer | 1 | 2008-09-29 | 1 | Completed | 2008-10-22 | Turn In | As Is
ASC 0811-52Ch1 | 2008-11-21 | email | 2008-11-21 | 404th | PBO Manged | SBHI | PBO Managed | FLWA | T61494 |  | Trk M998 | 7K | Wheel | 2 | 2009-01-05 | 2 | Completed | 2008-12-01 | Lateral Transfer | TM 10/20
ASC 0811-52Ch1 | 2008-11-21 | email | 2008-11-21 | 404th | PBO Manged | SBHI | PBO Managed | FLWA | T67679 |  | Trk M1097 | 7K | Wheel | 2 | 2009-01-05 | 2 | Completed | 2008-12-01 | Lateral Transfer | TM 10/20
ASC 0811-54 | 2008-11-21 | email | 2008-11-21 | 404th | 58th MP | SBHI | Tobyhanna | PA | T92242 |  | Trk M1025 | 7K | Wheel | 10 | 2009-01-05 |  | In Progress |  | Turn In | As Is Complete
ASC 0811-54 | 2008-11-21 | email | 2008-11-21 | 404th | 552nd MP | SBHI | Tobyhanna | PA | T92242 |  | Trk M1026 | 7K | Wheel | 21 | 2009-01-05 |  | In Progress |  | Turn In | As Is Complete
ASC 0811-54 | 2008-11-21 | email | 2008-11-21 | 404th | 552nd MP | SBHI | Tobyhanna | PA | T92310 |  | Trk M1025 | 7K | Wheel | 10 | 2009-01-05 |  | In Progress |  | Turn In | As Is Complete
ASC 0901-04 | 2009-01-02 | email | 2009-01-02 | 404th | LBE Hawaii | SBHI | Tobyhanna | PA | D78555 |  | AN/CYZ-10v3 | 7U | COMMEL | 21 | 2009-02-23 |  | In Progress |  | Turn In | As Is w/SA
LBE Hawaii as of 5 Jan 09