## Sheet1
NATO |  | **Costs forecasted based on historical daily run rates. | [33 empty] | **Yellow highlighted areas indicate actuals | [13 empty] | 2008 Target Rates
[9 empty] | PRB | 0.3749 | [38 empty] | Fringe | 1.3749
|  | **All Euro contracts calculated using average conversion rate of 1.34, (currently) | [6 empty] | ON SITE | 0.0491 | [38 empty] | Onsite OH | 1.0656
|  | (Rate flucuates from month-to-month) | [6 empty] | G&A | 0.1796 | [38 empty] | G&A | 1.176
|  | **GBP contract calculated using current conversion rate | [46 empty] | WRAP Rate | 1.73
|  | **All contracts forecasted through 12/31/08 because orders usually get extended. | [46 empty] | M&H WRAP Rate | 1.03
[7 empty] | Daily Rate |  | DIRECT LABOR | [12 empty] | SUBCONTRACTOR / CONSULTANT LABOR | [12 empty] | REVENUE | [13 empty] | 2008 Actual Burdened Cost | 2008 ETC Burdened Cost | Total Cost | Profit | ROS %
PROJECT # | NATO ORG. | LOCATION | EMPLOYMENT STATUS | NAME | START | END | Bill Rate to us | Bill Rate to Customer | 2008-01-01 | 2008-02-01 | 2008-03-01 | 2008-04-01 | 2008-05-01 | 2008-06-01 | 2008-07-01 | 2008-08-01 | 2008-09-01 | 2008-10-01 | 2008-11-01 | 2008-12-01 | ETC | 2008-01-01 | 2008-02-01 | 2008-03-01 | 2008-04-01 | 2008-05-01 | 2008-06-01 | 2008-07-01 | 2008-08-01 | 2008-09-01 | 2008-10-01 | 2008-11-01 | 2008-12-01 | ETC | 2008-01-01 | 2008-02-01 | 2008-03-01 | 2008-04-01 | 2008-05-01 | 2008-06-01 | 2008-07-01 | 2008-08-01 | 2008-09-01 | 2008-10-01 | 2008-11-01 | 2008-12-01 | ETC | EAC
21653 | NACMA | Belgium | CON/SUB | TO9 - Sandom - OFF | 2003-09-01 | 2008-01-31 | 1340 | 1582.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9380 | 9380 | 9380 | 9380 | 9380 | 9380 | 9380 | 9380 | 9380 | 9380 | 9380 | 9380 | 112560 | 11077.78 | 11077.78 | 11077.78 | 11077.78 | 11077.78 | 11077.78 | 11077.78 | 11077.78 | 11077.78 | 11077.78 | 11077.78 | 11077.78 | 132933.36 | 132933.36 | 19322.8 | 115936.8 | 135259.6 | -2326.24 | -1.75% | X
21653 | NACMA | Belgium | CON/SUB | TO9 - Sandom - ON | 2003-09-01 | 2008-01-31 | 1474 | 1756.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1474 |  | 1474 |  | 1474 |  | 1474 |  | 1474 |  | 1474 |  | 8844 | 1756.74 |  | 1756.74 |  | 1756.74 |  | 1756.74 |  | 1756.74 |  | 1756.74 |  | 10540.44 | 10540.44 | 1518.22 | 9109.32 | 10627.54 | -87.1 | -0.8263% | X
22170 | NAMSA | Belgium | CON/SUB | Ramon Viejo | 2005-03-01 | 2008-02-28 | 536 | 623.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 122208 | 11838.9 | 11838.9 | 11838.9 | 11838.9 | 11838.9 | 11838.9 | 11838.9 | 11838.9 | 11838.9 | 11838.9 | 11838.9 | 11838.9 | 142066.8 | 142066.8 | 20979.04 | 125874.24 | 146853.28 | -4786.48 | -3.369% | X
22171 | NAMSA | Belgium | CON/SUB | Stienaers | 2005-08-16 | 2008-06-30 | 871 | 1176.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 198588 | 22353.88 | 22353.88 | 22353.88 | 22353.88 | 22353.88 | 22353.88 | 22353.88 | 22353.88 | 22353.88 | 22353.88 | 22353.88 | 22353.88 | 268246.56 | 268246.56 | 34090.94 | 204545.64 | 238636.58 | 29609.98 | 11.04% | X
22172 | NACMA | Belgium | CON/SUB | TO23 - Evans | 2005-02-22 | 2008-01-31 | 1104.16 | 1275.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22083.2 | 22083.2 | 22083.2 | 22083.2 | 22083.2 | 22083.2 | 22083.2 | 22083.2 | 22083.2 | 22083.2 | 22083.2 | 22083.2 | 264998.4 | 25513.6 | 25513.6 | 25513.6 | 25513.6 | 25513.6 | 25513.6 | 25513.6 | 25513.6 | 25513.6 | 25513.6 | 25513.6 | 25513.6 | 306163.2 | 306163.2 | 45491.392 | 272948.352 | 318439.744 | -12276.544 | -4.01% | X
22175 | NACMA | emp | EMP | TO24 - Doman - OFF | 2005-02-24 | 2008-01-31 | 494.4 | 1188.58 | 6729.6304 | 6729.6304 | 6729.6304 | 6729.6304 | 6729.6304 | 6729.6304 | 6729.6304 | 6729.6304 | 6729.6304 | 6729.6304 | 6729.6304 | 6729.6304 | 80755.5646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9508.64 | 9508.64 | 9508.64 | 9508.64 | 9508.64 | 9508.64 | 9508.64 | 9508.64 | 9508.64 | 9508.64 | 9508.64 | 9508.64 | 114103.68 | 114103.68 | 23189.6318 | 139137.7908 | 162327.4226 | -48223.7426 | -42.26% | X
22175 | NACMA | emp | EMP | TO24 - Doman - ON | 2005-02-24 | 2008-01-31 | 494.4 | 1030.46 | 2523.6114 | 2523.6114 | 2523.6114 | 2523.6114 | 2523.6114 | 2523.6114 | 2523.6114 | 2523.6114 | 2523.6114 | 2523.6114 | 2523.6114 | 2523.6114 | 30283.3367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3091.38 | 3091.38 | 3091.38 | 3091.38 | 3091.38 | 3091.38 | 3091.38 | 3091.38 | 3091.38 | 3091.38 | 3091.38 | 3091.38 | 37096.56 | 37096.56 | 8696.1119 | 52176.6716 | 60872.7835 | -23776.2235 | -64.09% | X
22230 | NACMA | Belgium | CON/SUB | TO25 - Benoit | 2005-04-01 | 2008-01-31 | 980.88 | 1188.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19617.6 | 19617.6 | 19617.6 | 19617.6 | 19617.6 | 19617.6 | 19617.6 | 19617.6 | 19617.6 | 19617.6 | 19617.6 | 19617.6 | 235411.2 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 270996.24 | 270996.24 | 40412.256 | 242473.536 | 282885.792 | -11889.552 | -4.387% | X
23028 | NAMSA | UK | CON/SUB | Scheibe | 2006-08-01 | 2008-12-31 | 931.3 | 1157.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16763.4 | 16763.4 | 16763.4 | 16763.4 | 16763.4 | 16763.4 | 16763.4 | 16763.4 | 16763.4 | 16763.4 | 16763.4 | 16763.4 | 201160.8 | 20839.68 | 20839.68 | 20839.68 | 20839.68 | 20839.68 | 20839.68 | 20839.68 | 20839.68 | 20839.68 | 20839.68 | 20839.68 | 20839.68 | 250076.16 | 250076.16 | 34532.604 | 207195.624 | 241728.228 | 8347.932 | 3.338% | X
23028 | NAMSA | US | CON/SUB | Martin | 2005-10-19 | 2008-12-31 | 500 | 797.166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 114000 | 15146.154 | 15146.154 | 15146.154 | 15146.154 | 15146.154 | 15146.154 | 15146.154 | 15146.154 | 15146.154 | 15146.154 | 15146.154 | 15146.154 | 181753.848 | 181753.848 | 19570 | 117420 | 136990 | 44763.848 | 24.63% | X
23028 | NAMSA | Belgium | CON/SUB | Tait | 2005-12-01 | 2008-12-31 | 482.4 | 574.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 109987.2 | 10922.34 | 10922.34 | 10922.34 | 10922.34 | 10922.34 | 10922.34 | 10922.34 | 10922.34 | 10922.34 | 10922.34 | 10922.34 | 10922.34 | 131068.08 | 131068.08 | 18881.136 | 113286.816 | 132167.952 | -1099.872 | -0.8392% | X
23028 | NAMSA |  | CON/SUB | Boreman | 2007-03-01 | 2008-12-31 | 670 | 837.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12730 | 12730 | 12730 | 12730 | 12730 | 12730 | 12730 | 12730 | 12730 | 12730 | 12730 | 12730 | 152760 | 15912.5 | 15912.5 | 15912.5 | 15912.5 | 15912.5 | 15912.5 | 15912.5 | 15912.5 | 15912.5 | 15912.5 | 15912.5 | 15912.5 | 190950 | 190950 | 26223.8 | 157342.8 | 183566.6 | 7383.4 | 3.867% | X
23063 | NAMSA | emp | EMP | Hemberg | 2005-08-17 | 2008-10-31 | 282.8 | 834.82 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 109707.6759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15861.58 | 15861.58 | 15861.58 | 15861.58 | 15861.58 | 15861.58 | 15861.58 | 15861.58 | 15861.58 | 15861.58 | 15861.58 | 15861.58 | 190338.96 | 190338.96 | 0 | 0 | 0 | 190338.96 | 100% | X
23063 | NAMSA | emp | EMP | Hemberg | 2005-08-17 | 2008-10-31 | 282.8 | 188.94 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 9142.3063 | 109707.6759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3589.86 | 3589.86 | 3589.86 | 3589.86 | 3589.86 | 3589.86 | 3589.86 | 3589.86 | 3589.86 | 3589.86 | 3589.86 | 3589.86 | 43078.32 | 43078.32 | 0 | 0 | 0 | 43078.32 | 100% | X
23063 | NAMSA | emp | EMP | Manning | 2005-08-26 | 2008-10-31 | 240.4 | 971.5 | 7362.575 | 7362.575 | 7362.575 | 7362.575 | 7362.575 | 7362.575 | 7362.575 | 7362.575 | 7362.575 | 7362.575 | 7362.575 | 7362.575 | 88350.8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17487 | 17487 | 17487 | 17487 | 17487 | 17487 | 17487 | 17487 | 17487 | 17487 | 17487 | 17487 | 209844 | 209844 | 25370.6955 | 152224.1729 | 177594.8683 | 32249.1317 | 15.37% | X
23063 | NAMSA |  | EMP | Colter | 2007-05-07 | 2008-02-28 | 323.12 | 871 | 10445.7639 | 10445.7639 | 10445.7639 | 10445.7639 | 10445.7639 | 10445.7639 | 10445.7639 | 10445.7639 | 10445.7639 | 10445.7639 | 10445.7639 | 10445.7639 | 125349.1664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 198588 | 198588 | 35995.0553 | 215970.3318 | 251965.3871 | -53377.3871 | -26.88% | X
23063 | NAMSA |  | CON/SUB | Wade | 2006-06-12 | 2008-07-31 | 1172.5 | 1402.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23450 | 23450 | 23450 | 23450 | 23450 | 23450 | 23450 | 23450 | 23450 | 23450 | 23450 | 23450 | 281400 | 28059.6 | 28059.6 | 28059.6 | 28059.6 | 28059.6 | 28059.6 | 28059.6 | 28059.6 | 28059.6 | 28059.6 | 28059.6 | 28059.6 | 336715.2 | 336715.2 | 0 | 0 | 0 | 336715.2 | 100% | X
23129 | NACMA | UK | CON/SUB | Bailey | 2006-01-16 | 2008-01-31 | 569.5 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10820.5 | 10820.5 | 10820.5 | 10820.5 | 10820.5 | 10820.5 | 10820.5 | 10820.5 | 10820.5 | 10820.5 | 10820.5 | 10820.5 | 129846 | 12578 | 12578 | 12578 | 12578 | 12578 | 12578 | 12578 | 12578 | 12578 | 12578 | 12578 | 12578 | 150936 | 150936 | 22290.23 | 133741.38 | 156031.61 | -5095.61 | -3.376% | X
23196 | NC3A |  |  | Equipment (Generators) | 2006-03-08 | 2007-06-30 | Milestone | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 15000 |  | 15000 |  | 30000 | 0 | 0 | 0 | 0 |  |  |  | 0 | 20503.28 |  | 20503.28 |  | 41006.56 | 41006.56 | 0 | 0 | 0 | 526262.98 | 100% | X
23321 | NACMA | Belgium | CON/SUB | Benedetti | 2006-03-28 | 2008-01-31 | 716.9 | 776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10036.6 | 10036.6 | 10036.6 | 10036.6 | 10036.6 | 10036.6 | 10036.6 | 10036.6 | 10036.6 | 10036.6 | 10036.6 | 10036.6 | 120439.2 | 10864 | 10864 | 10864 | 10864 | 10864 | 10864 | 10864 | 10864 | 10864 | 10864 | 10864 | 10864 | 130368 | 130368 | 31013.094 | 124052.376 | 155065.47 | -24697.47 | -18.94% | X
23336 | NATO/HQ IT | Belgium | CON/SUB | Atkinson | 2007-01-01 | 2007-12-31 | 1340 | 1527.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26800 | 26800 | 26800 | 26800 | 26800 | 26800 | 26800 | 26800 | 26800 | 26800 | 26800 | 26800 | 321600 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 366624 | 366624 | 55208 | 331248 | 386456 | -19832 | -5.409% | X
23380 | NC3A | UK | CON/SUB | Sansom | 2006-07-18 | 2007-10-31 | 737 | 921.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13266 | 13266 | 13266 | 13266 | 13266 | 13266 | 13266 | 13266 | 13266 | 13266 | 13266 | 13266 | 159192 | 16582.5 | 16582.5 | 16582.5 | 16582.5 | 16582.5 | 16582.5 | 16582.5 | 16582.5 | 16582.5 | 16582.5 | 16582.5 | 16582.5 | 198990 | 198990 | 27327.96 | 163967.76 | 191295.72 | 7694.28 | 3.867% | X
23407 | SHAPE | emp | EMP | Cornett | 2006-07-31 | 2008-01-31 | 230.8 | 904.5 | 10890.4683 | 10890.4683 | 10890.4683 | 10890.4683 | 10890.4683 | 10890.4683 | 10890.4683 | 10890.4683 | 10890.4683 | 10890.4683 | 10890.4683 | 10890.4683 | 130685.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13567.5 | 13567.5 | 13567.5 | 13567.5 | 13567.5 | 13567.5 | 13567.5 | 13567.5 | 13567.5 | 13567.5 | 13567.5 | 13567.5 | 162810 | 162810 | 0 | 0 | 0 | 162810 | 100% | X
23436 | NATO/HQ IT |  | CON/SUB | Dutnell | 2007-01-01 | 2007-12-31 | 1286.4 | 1527.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27728 | 27728 | 27728 | 27728 | 27728 | 27728 | 27728 | 27728 | 27728 | 27728 | 27728 | 27728 | 332736 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 30552 | 366624 | 366624 | 57119.68 | 342718.08 | 399837.76 | -33213.76 | -9.059% | X
23468 | NACMA | Belgium | CON/SUB | Kellens | 2006-08-01 | 2008-12-31 | 683.4 | 746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12984.6 | 12984.6 | 12984.6 | 12984.6 | 12984.6 | 12984.6 | 12984.6 | 12984.6 | 12984.6 | 12984.6 | 12984.6 | 12984.6 | 155815.2 | 14174 | 14174 | 14174 | 14174 | 14174 | 14174 | 14174 | 14174 | 14174 | 14174 | 14174 | 14174 | 170088 | 170088 | 26748.276 | 160489.656 | 187237.932 | -17149.932 | -10.08% | X
23495 | NATO/HQ IT |  | CON/SUB | Verschure, Chris | 2007-01-01 | 2007-12-31 | 1206 | 1527.6 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 274968 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 348292.8 | 348292.8 | 47202.84 | 283217.04 | 330419.88 | 17872.92 | 5.132% | X
23539 | NAMSA |  | EMP (5) | NTM-I | 2006-10-01 | 2009-09-30 | FFP | FFP | 138000 | 138000 | 138000 | 138000 | 138000 | 138000 | 138000 | 138000 | 138000 | 138000 | 138000 | 138000 | 1656000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 170000 | 2040000 | 2040000 | 0 | 0 | 0 | 2040000 | 100% | x
23545 | NC3A |  |  | VTC | 2006-10-07 | 2010-08-31 | Milestone | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | x
23565 | NATO/HQ IT |  | CON/SUB | Mihalcea/Romeo/Coulon | 2007-01-01 | 2007-10-31 | 656.6 | 833.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11818.8 | 11818.8 | 11818.8 | 11818.8 | 11818.8 | 11818.8 | 11818.8 | 11818.8 | 11818.8 | 11818.8 | 11818.8 | 11818.8 | 141825.6 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 180031.68 | 180031.68 | 24346.728 | 146080.368 | 170427.096 | 9604.584 | 5.335% | x
23566 | NATO/HQ IT |  | CON/SUB | Haenecourt | 2007-01-01 | 2007-09-28 | 656.6 | 833.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13818.8 | 13818.8 | 13818.8 | 13818.8 | 13818.8 | 13818.8 | 13818.8 | 13818.8 | 13818.8 | 13818.8 | 13818.8 | 13818.8 | 165825.6 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 15002.64 | 180031.68 | 180031.68 | 28466.728 | 170800.368 | 199267.096 | -19235.416 | -10.68% | x
23588 | NACMA | UK | CON/SUB | TO 33 - Purch Site | 2006-09-01 | 2008-01-31 | 1811.68 | 2164.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3623.36 | 3623.36 | 3623.36 | 3623.36 | 3623.36 | 3623.36 | 3623.36 | 3623.36 | 3623.36 | 3623.36 | 3623.36 | 3623.36 | 43480.32 | 4328.2 | 4328.2 | 4328.2 | 4328.2 | 4328.2 | 4328.2 | 4328.2 | 4328.2 | 4328.2 | 4328.2 | 4328.2 | 4328.2 | 51938.4 | 51938.4 | 7464.1216 | 44784.7296 | 52248.8512 | -310.4512 | -0.5977% | x
23588 | NACMA |  | CON/SUB | TO 33 - Cont Site | 2006-09-01 | 2008-01-31 | 1511.52 | 1800.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4534.56 | 4534.56 | 4534.56 | 4534.56 | 4534.56 | 4534.56 | 4534.56 | 4534.56 | 4534.56 | 4534.56 | 4534.56 | 4534.56 | 54414.72 | 5402.88 | 5402.88 | 5402.88 | 5402.88 | 5402.88 | 5402.88 | 5402.88 | 5402.88 | 5402.88 | 5402.88 | 5402.88 | 5402.88 | 64834.56 | 64834.56 | 9341.1936 | 56047.1616 | 65388.3552 | -553.7952 | -0.8542% | x
23600 | NACMA |  | CON/SUB | Wood | 2006-12-04 | 2008-01-31 | 1064.8396 | 1269.6945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12778.0758 | 12778.0758 | 12778.0758 | 12778.0758 | 12778.0758 | 12778.0758 | 12778.0758 | 12778.0758 | 12778.0758 | 12778.0758 | 12778.0758 | 12778.0758 | 153336.9096 | 15236.3342 | 15236.3342 | 15236.3342 | 15236.3342 | 15236.3342 | 15236.3342 | 15236.3342 | 15236.3342 | 15236.3342 | 15236.3342 | 15236.3342 | 15236.3342 | 182836.0103 | 182836.0103 | 26322.8361 | 157937.0169 | 184259.853 | -1423.8427 | -0.7788% | x
23621 | NC3A |  |  | 1 Tandberg VTC unit at SHAPE | 2006-11-27 | 2007-12-15 | Milestone | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | x
23622 | NATO/HQ IT |  | CON/SUB | Claveau | 2006-11-20 | 2007-09-07 | 589.6 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10612.8 | 10612.8 | 10612.8 | 10612.8 | 10612.8 | 10612.8 | 10612.8 | 10612.8 | 10612.8 | 10612.8 | 10612.8 | 10612.8 | 127353.6 | 11916 | 11916 | 11916 | 11916 | 11916 | 11916 | 11916 | 11916 | 11916 | 11916 | 11916 | 11916 | 142992 | 142992 | 21862.368 | 131174.208 | 153036.576 | -10044.576 | -7.025% | x
23623 | NACMA |  | CON/SUB | Kimura | 2006-12-01 | 2008-01-31 | 1072 | 1286.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17152 | 17152 | 17152 | 17152 | 17152 | 17152 | 17152 | 17152 | 17152 | 17152 | 17152 | 17152 | 205824 | 20582.4 | 20582.4 | 20582.4 | 20582.4 | 20582.4 | 20582.4 | 20582.4 | 20582.4 | 20582.4 | 20582.4 | 20582.4 | 20582.4 | 246988.8 | 246988.8 | 35333.12 | 211998.72 | 247331.84 | -343.04 | -0.1389% | x
23639 | NACMA |  | CON/SUB | Duriau | 2006-12-12 | 2007-07-31 | Milestone | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13816.8 | 13816.8 | 13816.8 | 13816.8 | 13816.8 | 13816.8 | 13816.8 | 13816.8 | 13816.8 | 13816.8 | 13816.8 | 13816.8 | 165801.6 | 18003 | 18003 | 18003 | 18003 | 18003 | 18003 | 18003 | 18003 | 18003 | 18003 | 18003 | 18003 | 216036 | 216036 | 28462.608 | 170775.648 | 199238.256 | 16797.744 | 7.775% | x
23645 | NC3A | Belgium | CON/SUB | Smail | 2007-01-08 | 2007-10-31 | 402 | 482.4 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 7638 | 7638 | 7638 | 7638 | 7638 | 7638 | 7638 | 7638 | 7638 | 7638 | 7638 | 7638 | 91656 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 9165.6 | 109987.2 | 109987.2 | 15734.28 | 94405.68 | 110139.96 | -152.76 | -0.1389% | x
23657 | JALLC | emp | EMP | Moeder | 2007-01-01 | 2007-12-31 | 237.76 | 836.8032 | 10495.3417 | 10495.3417 | 10495.3417 | 10495.3417 | 10495.3417 | 10495.3417 | 10495.3417 | 10495.3417 | 10495.3417 | 10495.3417 | 10495.3417 | 10495.3417 | 125944.0999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 210874.4064 | 210874.4064 | 36165.8954 | 216995.3725 | 253161.2679 | -42286.8615 | -20.05% | x
23657 | JALLC |  | CON/SUB | Eden | 2007-01-01 | 2007-12-31 | 703.5 | 836.8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13366.5 | 13366.5 | 13366.5 | 13366.5 | 13366.5 | 13366.5 | 13366.5 | 13366.5 | 13366.5 | 13366.5 | 13366.5 | 13366.5 | 160398 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 190791.1296 | 190791.1296 | 27534.99 | 165209.94 | 192744.93 | -1953.8004 | -1.024% | x
23657 | JALLC | emp | EMP | Ross | 2007-01-01 | 2007-12-31 | 353.84 | 836.8032 | 14642.9664 | 14642.9664 | 14642.9664 | 14642.9664 | 14642.9664 | 14642.9664 | 14642.9664 | 14642.9664 | 14642.9664 | 14642.9664 | 14642.9664 | 14642.9664 | 175715.5969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 17572.8672 | 210874.4064 | 210874.4064 | 0 | 0 | 0 | 210874.4064 | 100% | x
23657 | JALLC |  | CON/SUB | Hansen | 2007-01-01 | 2007-12-31 | 621.76 | 836.8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11813.44 | 11813.44 | 11813.44 | 11813.44 | 11813.44 | 11813.44 | 11813.44 | 11813.44 | 11813.44 | 11813.44 | 11813.44 | 11813.44 | 141761.28 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 190791.1296 | 190791.1296 | 24335.6864 | 146014.1184 | 170349.8048 | 20441.3248 | 10.71% | x
23657 | JALLC |  | CON/SUB | Meehan | 2007-01-01 | 2007-12-31 | 703.5 | 836.8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14070 | 14070 | 14070 | 14070 | 14070 | 14070 | 14070 | 14070 | 14070 | 14070 | 14070 | 14070 | 168840 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 200832.768 | 200832.768 | 28984.2 | 173905.2 | 202889.4 | -2056.632 | -1.024% | x
23657 | JALLC |  | EMP | Sosa | 2007-04-14 | 2007-12-31 | 628 | 836.8032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11932 | 11932 | 11932 | 11932 | 11932 | 11932 | 11932 | 11932 | 11932 | 11932 | 11932 | 11932 | 143184 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 15899.2608 | 190791.1296 | 190791.1296 | 24579.92 | 147479.52 | 172059.44 | 18731.6896 | 9.818% | x
23657 | JALLC | emp | EMP | Thordsen | 2007-01-01 | 2007-12-31 | 330.8 | 836.8032 | 13256.8858 | 13256.8858 | 13256.8858 | 13256.8858 | 13256.8858 | 13256.8858 | 13256.8858 | 13256.8858 | 13256.8858 | 13256.8858 | 13256.8858 | 13256.8858 | 159082.6293 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 200832.768 | 200832.768 | 0 | 0 | 0 | 200832.768 | 100% | x
23657 | JALLC | emp | EMP | Donahue | 2007-01-01 | 2007-12-31 | 343.2 | 836.8032 | 13678.8488 | 13678.8488 | 13678.8488 | 13678.8488 | 13678.8488 | 13678.8488 | 13678.8488 | 13678.8488 | 13678.8488 | 13678.8488 | 13678.8488 | 13678.8488 | 164146.1862 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 16736.064 | 200832.768 | 200832.768 | 0 | 0 | 0 | 200832.768 | 100% | x
23658 | NATO/HQ IT | emp | EMP | Mattes | 2007-01-08 | 2007-12-31 | 455.44 | 1527.6 | 13948.4657 | 13948.4657 | 13948.4657 | 13948.4657 | 13948.4657 | 13948.4657 | 13948.4657 | 13948.4657 | 13948.4657 | 13948.4657 | 13948.4657 | 13948.4657 | 167381.5884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27496.8 | 27496.8 | 27496.8 | 27496.8 | 27496.8 | 27496.8 | 27496.8 | 27496.8 | 27496.8 | 27496.8 | 27496.8 | 27496.8 | 329961.6 | 329961.6 | 0 | 0 | 0 | 329961.6 | 100% | x
23683 | Area 7 |  | CON/SUB | Walker | 2007-02-12 | 2007-08-31 | 996.96 | 1174.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 203379.84 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 239665.32 | 239665.32 | 34913.5392 | 209481.2352 | 244394.7744 | -4729.4544 | -1.973% | x
23684 | Area 7 |  | CON/SUB | Smit | 2007-01-26 | 2007-09-20 | 1308 | 1444.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15696 | 15696 | 15696 | 15696 | 15696 | 15696 | 15696 | 15696 | 15696 | 15696 | 15696 | 15696 | 188352 | 17328.84 | 17328.84 | 17328.84 | 17328.84 | 17328.84 | 17328.84 | 17328.84 | 17328.84 | 17328.84 | 17328.84 | 17328.84 | 17328.84 | 207946.08 | 207946.08 | 32333.76 | 194002.56 | 226336.32 | -18390.24 | -8.844% | x
23685 | Area 7 |  | CON/SUB | K. Bailey | 2007-03-20 | 2007-10-15 | 996.96 | 1174.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 16948.32 | 203379.84 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 19972.11 | 239665.32 | 239665.32 | 34913.5392 | 209481.2352 | 244394.7744 | -4729.4544 | -1.973% | x
23720 | NAMSA |  | CON/SUB | Marshall | 2007-03-01 | 2007-09-05 | 402 | 502.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7236 | 7236 | 7236 | 7236 | 7236 | 7236 | 7236 | 7236 | 7236 | 7236 | 7236 | 7236 | 86832 | 9045 | 9045 | 9045 | 9045 | 9045 | 9045 | 9045 | 9045 | 9045 | 9045 | 9045 | 9045 | 108540 | 108540 | 14906.16 | 89436.96 | 104343.12 | 4196.88 | 3.867% | x
23726 | Area 7 |  | CON/SUB | Butler | 2007-03-01 | 2007-09-15 | 996.96 | 1174.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15951.36 | 15951.36 | 15951.36 | 15951.36 | 15951.36 | 15951.36 | 15951.36 | 15951.36 | 15951.36 | 15951.36 | 15951.36 | 15951.36 | 191416.32 | 18797.28 | 18797.28 | 18797.28 | 18797.28 | 18797.28 | 18797.28 | 18797.28 | 18797.28 | 18797.28 | 18797.28 | 18797.28 | 18797.28 | 225567.36 | 225567.36 | 32859.8016 | 197158.8096 | 230018.6112 | -4451.2512 | -1.973% | x
23730 | NACMA |  | CON/SUB | Brooks | 2007-03-19 | 2007-12-31 | 1125.6 | 1340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21386.4 | 21386.4 | 21386.4 | 21386.4 | 21386.4 | 21386.4 | 21386.4 | 21386.4 | 21386.4 | 21386.4 | 21386.4 | 21386.4 | 256636.8 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 305520 | 305520 | 44055.984 | 264335.904 | 308391.888 | -2871.888 | -0.94% | x
23753 | NACMA |  | CON/SUB | Hendricks | 2007-03-27 | 2007-10-15 | 603 | 757.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11457 | 11457 | 11457 | 11457 | 11457 | 11457 | 11457 | 11457 | 11457 | 11457 | 11457 | 11457 | 137484 | 14384.9 | 14384.9 | 14384.9 | 14384.9 | 14384.9 | 14384.9 | 14384.9 | 14384.9 | 14384.9 | 14384.9 | 14384.9 | 14384.9 | 172618.8 | 172618.8 | 23601.42 | 141608.52 | 165209.94 | 7408.86 | 4.292% | x
23790 | NATO/HQ IT |  | CON/SUB | Stephensen/Lobo | 2007-03-29 | 2007-09-28 | 911.2 | 1188.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16401.6 | 16401.6 | 16401.6 | 16401.6 | 16401.6 | 16401.6 | 16401.6 | 16401.6 | 16401.6 | 16401.6 | 16401.6 | 16401.6 | 196819.2 | 21394.44 | 21394.44 | 21394.44 | 21394.44 | 21394.44 | 21394.44 | 21394.44 | 21394.44 | 21394.44 | 21394.44 | 21394.44 | 21394.44 | 256733.28 | 256733.28 | 33787.296 | 202723.776 | 236511.072 | 20222.208 | 7.877% | x
23793 | NATO/HQ IT |  | CON/SUB | Grandjean | 2007-03-28 | 2007-09-28 | 1273 | 1527.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 10184 | 122208 | 12220.8 | 12220.8 | 12220.8 | 12220.8 | 12220.8 | 12220.8 | 12220.8 | 12220.8 | 12220.8 | 12220.8 | 12220.8 | 12220.8 | 146649.6 | 146649.6 | 20979.04 | 125874.24 | 146853.28 | -203.68 | -0.1389% | x
23819 | NACMA |  | CON/SUB | ALTBMD - Outram | 2007-05-08 | 2007-12-31 | 1050.6418 | 1261.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10506.4179 | 10506.4179 | 10506.4179 | 10506.4179 | 10506.4179 | 10506.4179 | 10506.4179 | 10506.4179 | 10506.4179 | 10506.4179 | 10506.4179 | 10506.4179 | 126077.0146 | 12615.8145 | 12615.8145 | 12615.8145 | 12615.8145 | 12615.8145 | 12615.8145 | 12615.8145 | 12615.8145 | 12615.8145 | 12615.8145 | 12615.8145 | 12615.8145 | 151389.7742 | 151389.7742 | 21643.2208 | 129859.325 | 151502.5458 | -112.7716 | -0.07449% | x
23824 | SHAPE |  | EMP | Hughes | 2007-05-21 | 2007-12-31 | 307.76 | 904.5 | 9425.5661 | 9425.5661 | 9425.5661 | 9425.5661 | 9425.5661 | 9425.5661 | 9425.5661 | 9425.5661 | 9425.5661 | 9425.5661 | 9425.5661 | 9425.5661 | 113106.7926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16281 | 16281 | 16281 | 16281 | 16281 | 16281 | 16281 | 16281 | 16281 | 16281 | 16281 | 16281 | 195372 | 195372 | 0 | 0 | 0 | 195372 | 100% | x
23860 | Area 7 |  | CON/SUB | Ayaydin | 2007-07-02 | 2008-02-15 | 812.5 | 1174.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15437.5 | 15437.5 | 15437.5 | 15437.5 | 15437.5 | 15437.5 | 15437.5 | 15437.5 | 15437.5 | 15437.5 | 15437.5 | 15437.5 | 185250 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 267861.24 | 267861.24 | 31801.25 | 190807.5 | 222608.75 | 45252.49 | 16.89% | x
23868 | NATO/HQ IT |  | CON/SUB | Young | 2007-06-04 | 2007-12-31 | 1457.92 | 1672.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27700.48 | 27700.48 | 27700.48 | 27700.48 | 27700.48 | 27700.48 | 27700.48 | 27700.48 | 27700.48 | 27700.48 | 27700.48 | 27700.48 | 332405.76 | 31774.08 | 31774.08 | 31774.08 | 31774.08 | 31774.08 | 31774.08 | 31774.08 | 31774.08 | 31774.08 | 31774.08 | 31774.08 | 31774.08 | 381288.96 | 381288.96 | 57062.9888 | 342377.9328 | 399440.9216 | -18151.9616 | -4.761% | x
23871 | NACMA |  | CON/SUB | James | 2007-07-16 | 2008-01-31 | 1340 | 2106.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 25460 | 305520 | 40023.12 | 40023.12 | 40023.12 | 40023.12 | 40023.12 | 40023.12 | 40023.12 | 40023.12 | 40023.12 | 40023.12 | 40023.12 | 40023.12 | 480277.44 | 480277.44 | 52447.6 | 314685.6 | 367133.2 | 113144.24 | 23.56% | x
23877 | NC3A | Belgium | CON/SUB | ECU's to ISAF | 2007-06-25 | 2007-09-15 | Milestone | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | x
23915 | NATO/HQ IT |  | CON/SUB | Aiston | 2007-07-02 | 2007-08-28 | 1286.4 | 1527.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24441.6 | 24441.6 | 24441.6 | 24441.6 | 24441.6 | 24441.6 | 24441.6 | 24441.6 | 24441.6 | 24441.6 | 24441.6 | 24441.6 | 293299.2 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 348292.8 | 348292.8 | 50349.696 | 302098.176 | 352447.872 | -4155.072 | -1.193% | x
23916 | NC3A |  | CON/SUB | Studio VTCs at SACT, JWC, & JFTC | 2007-07-06 | 2009-06-30 | Milestone | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | x
23940 | NACMA |  | CON/SUB | Wells | 2007-09-03 | 2008-09-03 | 1166.253 | 1389.3622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22158.806 | 22158.806 | 22158.806 | 22158.806 | 22158.806 | 22158.806 | 22158.806 | 22158.806 | 22158.806 | 22158.806 | 22158.806 | 22158.806 | 265905.6726 | 26397.882 | 26397.882 | 26397.882 | 26397.882 | 26397.882 | 26397.882 | 26397.882 | 26397.882 | 26397.882 | 26397.882 | 26397.882 | 26397.882 | 316774.5839 | 316774.5839 | 45647.1405 | 273882.8428 | 319529.9832 | -2755.3994 | -0.8698% | x
23949 | NACMA |  | CON/SUB | Thornton | 2007-07-16 | 2007-12-31 | 687.21 | 824.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12369.78 | 12369.78 | 12369.78 | 12369.78 | 12369.78 | 12369.78 | 12369.78 | 12369.78 | 12369.78 | 12369.78 | 12369.78 | 12369.78 | 148437.36 | 14839.2 | 14839.2 | 14839.2 | 14839.2 | 14839.2 | 14839.2 | 14839.2 | 14839.2 | 14839.2 | 14839.2 | 14839.2 | 14839.2 | 178070.4 | 178070.4 | 25481.7468 | 152890.4808 | 178372.2276 | -301.8276 | -0.1695% | x
23956 | NC3A |  | CON/SUB | O'Brien | 2007-07-23 | 2007-08-10 | 837.5 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15075 | 15075 | 15075 | 15075 | 15075 | 15075 | 15075 | 15075 | 15075 | 15075 | 15075 | 15075 | 180900 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 216000 | 216000 | 31054.5 | 186327 | 217381.5 | -1381.5 | -0.6396% | x
23957 | Area 7 |  | CON/SUB | Etienne | 2007-07-16 | 2008-03-15 | 984.9 | 1174.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18713.1 | 18713.1 | 18713.1 | 18713.1 | 18713.1 | 18713.1 | 18713.1 | 18713.1 | 18713.1 | 18713.1 | 18713.1 | 18713.1 | 224557.2 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 22321.77 | 267861.24 | 267861.24 | 38548.986 | 231293.916 | 269842.902 | -1981.662 | -0.7398% | x
23958 | Area 7 |  | CON/SUB | Humphrys | 2007-07-16 | 2008-04-30 | 1005 | 1174.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | x
23958 | Area 7 |  | CON/SUB | Humphrys | 2007-07-16 | 2008-04-30 | 2167.2088 | 2630.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30340.9232 | 30340.9232 | 30340.9232 | 30340.9232 | 30340.9232 | 30340.9232 | 30340.9232 | 30340.9232 | 30340.9232 | 30340.9232 | 30340.9232 | 30340.9232 | 364091.0784 | 36832.6 | 36832.6 | 36832.6 | 36832.6 | 36832.6 | 36832.6 | 36832.6 | 36832.6 | 36832.6 | 36832.6 | 36832.6 | 36832.6 | 441991.2 | 441991.2 | 62502.3018 | 375013.8108 | 437516.1125 | 4475.0875 | 1.012% | x
23960 | NACMA |  | CON/SUB | Hulstaert | 2007-07-01 | 2008-02-28 | 683.4 | 759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12301.2 | 12301.2 | 12301.2 | 12301.2 | 12301.2 | 12301.2 | 12301.2 | 12301.2 | 12301.2 | 12301.2 | 12301.2 | 12301.2 | 147614.4 | 13662 | 13662 | 13662 | 13662 | 13662 | 13662 | 13662 | 13662 | 13662 | 13662 | 13662 | 13662 | 163944 | 163944 | 25340.472 | 152042.832 | 177383.304 | -13439.304 | -8.197% | x
23961 | NATO/HQ IT |  | CON/SUB | Gaunard | 2007-08-06 | 2007-12-31 | 1005 | 1527.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19095 | 19095 | 19095 | 19095 | 19095 | 19095 | 19095 | 19095 | 19095 | 19095 | 19095 | 19095 | 229140 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 29024.4 | 348292.8 | 348292.8 | 39335.7 | 236014.2 | 275349.9 | 72942.9 | 20.94% | x
23962 | NATO/HQ IT |  | CON/SUB | Costes | 2007-08-27 | 2007-12-31 | 871 | 1188.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 16549 | 198588 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 22583.02 | 270996.24 | 270996.24 | 34090.94 | 204545.64 | 238636.58 | 32359.66 | 11.94% | x
TBD | NATO/HQ IT |  | CON/SUB | Mainwaring | 2007-08-16 | 2007-12-31 | 1206 | 1460.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 22914 | 274968 | 27751.4 | 27751.4 | 27751.4 | 27751.4 | 27751.4 | 27751.4 | 27751.4 | 27751.4 | 27751.4 | 27751.4 | 27751.4 | 27751.4 | 333016.8 | 333016.8 | 47202.84 | 283217.04 | 330419.88 | 2596.92 | 0.7798% | x
TDB | NATO/HQ IT |  | CON/SUB | England
TBD | NATO/HQ IT |  | CON/SUB | Moarcas
TBD |  |  |  | Two new Systems VTC | [16 empty] | 0 | [12 empty] | 0 |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
NEW BUSINESS |  |  |  | NEW BUSINESS | [16 empty] | 0 | [8 empty] | 1791918.75 | 1456861 | 1817624.8 | 1577620.19 | 6644024.74 |  | 0 | 48361.02 | 117.68 | 13556.84 | -200754.4 | -114874 |  | 228577.33 | 443073.1 | 443073.1 | 443073.1 | 1304203.77 | 1304203.77
[8 empty] | TOTALS | 269684.7361 | 269684.7361 | 269684.7361 | 269684.7361 | 269684.7361 | 269684.7361 | 269684.7361 | 269684.7361 | 269684.7361 | 269684.7361 | 269684.7361 | 269684.7361 | 3236216.833 | 827693.4429 | 826219.4429 | 827693.4429 | 826219.4429 | 827693.4429 | 826219.4429 | 827693.4429 | 826219.4429 | 2634612.1929 | 2283080.4429 | 2660318.2429 | 2403839.6329 | 16597502.0552 | 1377202.1935 | 1375445.4535 | 1425563.2135 | 1375563.1335 | 1390759.0335 | 1174691.0535 | 1262328.1935 | 1375445.4535 | 1626282.8035 | 1818518.5535 | 1840778.5735 | 1818518.5535 | 17861096.212 | 17861096.212
[47 empty] | ETC | EAC
Note on E10: Off-site
Note on E11: On-site
Note on E15: employee
Note on E16: employee
Note on G10: Forecasted thru 12/31/06 b/c orders usually get extended
Note on H10: Offsite rate = 1000euros Onsite rate = 1100euros
Note on H53: Bills us in USD
Note on I27: Contract in USD