- A Capability Package (CP) is developed that will provide NATO with a specific capability.  This CP contains all the various projects required to be completed that, once implemented, will provide NATO with this particular capability.

- The CP is approved by the North Atlantic Council (NAC).  Nothing is funded at this point.  Only the decision to provide NATO with a particular capability has been made by the NAC.

- Once the CP is approved by the NAC, for any project within the CP, there is a two-phase approval process.  The first phase is approving the Scope of the project and the second phase is approving the Funding of the project.

- The Infrastructure Committee (IC) appoints a Host Nation (HN), which could be any NATO Nation or Agency.  The appointed HN is given approval by the Infrastructure Committee (IC) to spend up to 3% of the total anticipated project cost to prepare a “Type B” Cost Estimate or a “35% Design” for the project.

- Once finalized, this project “Type B” goes before the International Staff for screening and authorization where the project is reviewed by National Experts (NATEXs) from an engineering point of view.

- The screened and authorized project “Type B” then goes back to the IC where the IC approves the scope of the project and all the remaining funds for the project.

- The IFB is then published.

- There are generally two exceptions to the above procedure.

  - Projects in excess of €75 Million need additional approval from the IC just before contract signature; and

  - Projects that exceed the “Type B” cost estimate must return to the IC for additional funding.

Note 1:	The scope of a project may change during the approval process and a project may go through the IC approval cycle more than once before getting final approval.

Note 2:	All funding for any project is approved before the IFB is released.