## Feb
FEBRUARY
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
[5 empty] | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
| Safe Harbor Application - Cindy | Sanitized Sub payments sent to B&M - Theresa | -Receive Dutch translation of Annex B - B&M -Proposed Comp. Structure - Cindy | -Annex B signed & notorized - Theresa & Jay - Financial Impact of Comp Structure - Theresa & Dion | -Additional Information submitted to B&M - Dion & Cindy -Meeting with Jay to review Comp Structure & Job Fair Tour - MSS
17 | 18 | 19 | 20 | 21 | 22 | 23
|  |  | Annex B Apostille Completed- Jeff & Theresa | Landlords contacted and initial indication given - Cindy | -Branch Application Submitted - B&M -Obtain Registration # -Provide MQ new compensation information - Cindy
24 | 25 | 26 | 27 | 28 | 29
|  |  | Paperwork processed to set up Org Units/Dept IDs in PS- Dion |  | Bank Account Established - Hui & Dion
Note on F9: Additional Information includes Rental Agreements, Subtantiation of US ties, and overhead details

## March
MARCH
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
1
2 | 3 | 4 | 5 | 6 | 7 | 8
| Receive back tax employee estimate - B&M |  | -Impact of new comp structure on US taxes & payroll - J. Ireland, J. Fitzgeral, J. Clark
9 | 10 | 11 | 12 | 13 | 14 | 15
| Decision on EE Back Tax Payment by ManTech - ALL |  | -Dutch translation of Annex B - B&M -Proposed Comp. Structure - Cindy | Internal Final Approval for Comp Structure - ALL | Compensation Paperwork to George for Payroll - Cindy
16 | 17 | 18 | 19 | 20 | 21 | 22
| Department IDs established in PS - Cindy/Dion |  | Updated Offer Letters for New EE in Belgium - Cindy |  | VAT # Assigned to ManTech
23 | 24 | 25 | 26 | 27 | 28 | 29
|  |  | Orientation Package for EE and ICs - Theresa & Cindy |  | Written recommendation to corporate on how to do business with MGS - MSS
30 | 31
IWAs and Activity IDs set up in PS - Theresa
Ongoing Nogotiations & Discussions with Employees - Cindy

## April
APRIL
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
|  | 1 | 2 | 3 | 4 | 5
|  | Any new contracts set up under MGS - Theresa |  |  |  | Begin Belgian Payroll Withholding Begins
6 | 7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
-Dutch translation of Annex B - B&M -Proposed Comp. Structure - Cindy
20 | 21 | 22 | 23 | 24 | 25 | 26
27 | 28 | 29 | 30