## Sheet1
NATO PROGRAM STATUS REPORT
AS OF PERIOD ENDING: 29-JUNE-2007
PS Contract #: | 21653 |  |  | PS Contract #: | 21658
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | SMIS, CO-9772-ACCS |  |  | Contract # | SMIS, CO-9772-ACCS
Contractor Name: | NACMA |  |  | Customer: | NACMA
Consultant Name: | TO 9 Sandom |  |  | Consultant Name: | Outram
Est Period of Performance: | 09/01/03 - 1/31/08 |  |  | Est Period of Performance: | 08/18/03 - 12/31/07
Contract Value: | 645008.76 |  |  | Contract Value: | 400739
Contract Funding: | 645008.76 |  |  | Contract Funding: | 400739
EAC: | 644990 |  |  | EAC: | 397727
CAC: | 546712 |  |  | CAC: | 341559
Funding Status: | 18.76 |  |  | Funding Status: | 3012
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 14312 | 66274 | 545598 | Revenue: | -1218 | 56972 | 397727
Cost: | 12441 | 57542 | 461482 | Cost: | 7 | 48558 | 341559
Profit: | 15.04% | 15.18% | 18.23% | Profit: | -17500% | 17.33% | 16.44%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 12798.02 | 12.4K Accruals |  | Unbilled Status: | 4056.79 | 3.3K accruals
Other: |  |  |  | Other:
PS Contract #: | 21673 |  |  | PS Contract #: | 21675
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | SMIS, CO-9772-ACCS |  |  | Contract # | SMIS, CO-9772-ACCS
Customer: | NACMA |  |  | Customer: | NACMA
Consultant Name: | TO 30 Thornton |  |  | Consultant Name: | Hulstaert
Est Period of Performance: | 09/01/05 - 01/31/08 |  |  | Est Period of Performance: | 08/29/05 - 01/31/08
Contract Value: | 277866 |  |  | Contract Value: | 315745
Contract Funding: | 277866 |  |  | Contract Funding: | 315745
EAC: | 368072 |  |  | EAC: | 388986
CAC: | 313527 |  |  | CAC: | 344320
Funding Status: | -90206 |  |  | Funding Status: | -73241
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 13397 | 83269 | 271160 | Revenue: | 14421 | 83529 | 304284
Cost: | 11247 | 71024 | 232599 | Cost: | 13409 | 77294 | 270220
Profit: | 19.12% | 17.24% | 16.58% | Profit: | 7.547% | 8.067% | 12.61%
Receivables +60: | 15114 | Paid in July |  | Receivables +60: | 0
Unbilled Status: | 15278.3 | Accruals |  | Unbilled Status: | 14345.31 | Accruals
Other: |  |  |  | Other:
PS Contract #: | 22172 |  |  | PS Contract #: | 22175
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | SMIS, CO-9772-ACCS |  |  | Contract # | SMIS, CO-9772-ACCS
Customer: | NACMA |  |  | Customer: | NACMA
Consultant Name: | TO 23 Evans |  |  | Employee Name: | TO 24 Doman
Est Period of Performance: | 02/22/06 - 12/31/07 |  |  | Est Period of Performance: | 02/28/05 - 01/31/08
Contract Value: | 774564 |  |  | Contract Value: | 382689
Contract Funding: | 774564 |  |  | Contract Funding: | 382689
EAC: | 799130 |  |  | EAC: | 407820
CAC: | 708506 |  |  | CAC: | 375706
Funding Status: | -24566 |  |  | Funding Status: | -25131
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 26997 | 143128 | 646141 | Revenue: | 22951 | 84751 | 319719
Cost: | 23969 | 126690 | 576155 | Cost: | 17409 | 68798 | 299999
Profit: | 12.63% | 12.97% | 12.15% | Profit: | 31.83% | 23.19% | 6.573%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 21938.15 | 23K Accruals |  | Unbilled Status: | 10506.58 | 10.1K WIP
Other: |  |  |  | Other: | Re'cd MOD for 100 days in July
PS Contract #: | 22230 |  |  | PS Contract #: | 23129
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | SMIS, CO-9772-ACCS |  |  | Contract # | SMIS, CO-9772-ACCS
Customer: | NACMA |  |  | Customer: | NACMA
Consultant Name: | TO 25 Benoit |  |  | Consultant Name: | Bailey
Est Period of Performance: | 05/01/05 - 01/31/08 |  |  | Est Period of Performance: | 01/06/06 - 01/31/08
Contract Value: | 538797 |  |  | Contract Value: | 261160
Contract Funding: | 538797 |  |  | Contract Funding: | 261160
EAC: | 646260 |  |  | EAC: | 269674
CAC: | 556483 |  |  | CAC: | 232966
Funding Status: | -107463 |  |  | Funding Status: | -8514
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 13250 | 111175 | 494880 | Revenue: | 10510 | 57246 | 182842
Cost: | 11378 | 95726 | 428968 | Cost: | 9294 | 51351 | 157826
Profit: | 16.45% | 16.14% | 15.37% | Profit: | 13.08% | 11.48% | 15.85%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 17559.47 | 18K Accruals |  | Unbilled Status: | 8735.08 | Accruals
Other: | Re'cd MOD for 100 days in July |  |  | Other:
PS Contract #: | 23321 |  |  | PS Contract #: | 23468
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-9772-ACCS |  |  | Contract # | SMIS, CO-9772-ACCS
Customer: | NACMA |  |  | Customer: | NACMA
Consultant Name: | Benedetti |  |  | Consultant Name: | Kellens
Est Period of Performance: | 03/28/06 - 01/31/08 |  |  | Est Period of Performance: | 08/06/06 - 11/30/07
Contract Value: | 192544 |  |  | Contract Value: | 187706
Contract Funding: | 192544 |  |  | Contract Funding: | 187706
EAC: | 196668 |  |  | EAC: | 187581
CAC: | 180151 |  |  | CAC: | 168343
Funding Status: | -4124 |  |  | Funding Status: | 125
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 5297 | 49844 | 115964 | Revenue: | 13692 | 87032 | 121548
Cost: | 5567 | 47505 | 107819 | Cost: | 12742 | 80647 | 111793
Profit: | -4.85% | 4.924% | 7.554% | Profit: | 7.456% | 7.917% | 8.726%
Receivables +60: | 0 |  |  | Receivables +60: | 14421 | Waiting on status
Unbilled Status: | 7227.82 | Accruals |  | Unbilled Status: | 57179.77 | WIP
Other: |  |  |  | Other:
PS Contract #: | 23588 |  |  | PS Contract #: | 23600
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | SMIS, CO-9772-ACCS |  |  | Contract # | CO-9772-ACCS
Customer: | NACMA |  |  | Customer: | NACMA
Consultant Name: | TO 33 Stasys |  |  | Consultant Name: | Wood
Est Period of Performance: | 09/27/06 - 01/31/08 |  |  | Est Period of Performance: | 12/04/06 - 01/31/08
Contract Value: | 186494 |  |  | Contract Value: | 185140
Contract Funding: | 186494 |  |  | Contract Funding: | 185140
EAC: | 166508 |  |  | EAC: | 223838
CAC: | 141522 |  |  | CAC: | 190219
Funding Status: | 19986 |  |  | Funding Status: | -38698
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 21392 | 48983 | 90982 | Revenue: | 16374 | 89320 | 89320
Cost: | 18395 | 41913 | 78208 | Cost: | 14096 | 77374 | 77374
Profit: | 16.29% | 16.87% | 16.33% | Profit: | 16.16% | 15.44% | 15.44%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 9042.5 | 9.3K Accruals |  | Unbilled Status: | 12175.58 | 12.5K Accruals
Other: |  |  |  | Other:
PS Contract #: | 23623 |  |  | PS Contract #: | 23730
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-9772-ACCS |  |  | Contract # | CO-9772-ACCS
Customer: | NACMA |  |  | Customer: | NACMA
Consultant Name: | Kimura |  |  | Consultant Name: | Brooks
Est Period of Performance: | 12/01/06 - 01/31/08 |  |  | Est Period of Performance: | 3/19/07-12/31/07
Contract Value: | 140730 |  |  | Contract Value: | 249791
Contract Funding: | 140730 |  |  | Contract Funding: | 249791
EAC: | 227826 |  |  | EAC: | 249356
CAC: | 198763 |  |  | CAC: | 211203
Funding Status: | -87096 |  |  | Funding Status: | 435
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 7728 | 27853 | 46866 | Revenue: | 22960 | 80456 | 80456
Cost: | 6631 | 23733 | 40059 | Cost: | 19780 | 69267 | 69267
Profit: | 16.54% | 17.36% | 16.99% | Profit: | 16.08% | 16.15% | 16.15%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 7024.76 | 7.7K Accruals |  | Unbilled Status: | 27038.51 | Accruals
Other: |  |  |  | Other:
PS Contract #: | 23753 |  |  | PS Contract #: | 23336
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-9772-ACCS |  |  | Contract # | 2812/AC
Customer: | NACMA |  |  | Customer: | NATO HQ
Consultant Name: | Hendricks |  |  | Consultant Name: | Atkinson
Est Period of Performance: | 3/27/07-10/30/07 |  |  | Est Period of Performance: | 07/03/06 - 12/31/07
Contract Value: | 90095 |  |  | Contract Value: | 548597
Contract Funding: | 90095 |  |  | Contract Funding: | 548597
EAC: | 90521 |  |  | EAC: | 543588
CAC: | 72910 |  |  | CAC: | 503578
Funding Status: | -426 |  |  | Funding Status: | 5009
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 14498 | 43513 | 43513 | Revenue: | 30793 | 159232 | 339748
Cost: | 11821 | 35470 | 35470 | Cost: | 28740 | 154896 | 321578
Profit: | 22.65% | 22.68% | 22.68% | Profit: | 7.143% | 2.799% | 5.65%
Receivables +60: | 2309.61 | Paid in July |  | Receivables +60: | 0
Unbilled Status: | 13739.12 | Accruals |  | Unbilled Status: | 27999.7 | 28.5K Accruals
Other: |  |  |  | Other:
PS Contract #: | 23337 |  |  | PS Contract #: | 23436
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | 2807/AC |  |  | Contract # | 2831/AC
Customer: | NATO HQ |  |  | Customer: | NATO HQ
Consultant Name: | Sai |  |  | Consultant Name: | Dutnell
Est Period of Performance: | 06/26/06 - 08/14/07 |  |  | Est Period of Performance: | 09/01/06 - 12/31/07
Contract Value: | 265583 |  |  | Contract Value: | 468444
Contract Funding: | 265583 |  |  | Contract Funding: | 468444
EAC: | 255665 |  |  | EAC: | 459413
CAC: | 230960 |  |  | CAC: | 411086
Funding Status: | 9918 |  |  | Funding Status: | 9031
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 14064 | 92739 | 207240 | Revenue: | 35404 | 194327 | 280091
Cost: | 13151 | 90977 | 190335 | Cost: | 31617 | 176247 | 252318
Profit: | 6.942% | 1.937% | 8.882% | Profit: | 11.98% | 10.26% | 11.01%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 15626.11 | 16K Accruals |  | Unbilled Status: | 28532.64 | Accruals
Other: |  |  |  | Other:
PS Contract #: | 23495 |  |  | PS Contract #: | 23565
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | 2844/AC |  |  | Contract # | CO-9772-ACCS
Customer: | NATO HQ |  |  | Customer: | NATO HQ
Consultant Name: | Verschure |  |  | Consultant Name: | Mihalcea/Romeo
Est Period of Performance: | 10/02/06 - 12/31/07 |  |  | Est Period of Performance: | 10/19/06 - 10/23/07
Contract Value: | 456941 |  |  | Contract Value: | 190052
Contract Funding: | 456941 |  |  | Contract Funding: | 190052
EAC: | 445890 |  |  | EAC: | 174797
CAC: | 372047 |  |  | CAC: | 152034
Funding Status: | 11051 |  |  | Funding Status: | 15255
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 30786 | 167084 | 248784 | Revenue: | -2567 | 70921 | 102023
Cost: | 25968 | 147782 | 216437 | Cost: | -1308 | 68922 | 94704
Profit: | 18.55% | 13.06% | 14.95% | Profit: | 96.25% | 2.9% | 7.728%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 24020.07 | 25.3K Accruals; |  | Unbilled Status: | -757.09
Other: |  |  |  | Other: | Mihalcea to be replaced by Romeo 6/27/07
PS Contract #: | 23566 |  |  | PS Contract #: | 23594
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-9772-ACCS |  |  | Contract # | CO-9772-ACCS
Customer: | NATO HQ |  |  | Customer: | NATO HQ
Consultant Name: | Haenecourt |  |  | Consultant Name: | Kok
Est Period of Performance: | 10/19/06 - 09/28/07 |  |  | Est Period of Performance: | 10/10/06 - 09/28/07
Contract Value: | 191775 |  |  | Contract Value: | 195429
Contract Funding: | 191775 |  |  | Contract Funding: | 195429
EAC: | 176954 |  |  | EAC: | 190499
CAC: | 160556 |  |  | CAC: | 166601
Funding Status: | 14821 |  |  | Funding Status: | 4930
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 15541 | 90396 | 129452 | Revenue: | 10531 | 83130 | 127163
Cost: | 13592 | 82008 | 114336 | Cost: | 9525 | 79094 | 115641
Profit: | 14.34% | 10.23% | 13.22% | Profit: | 10.56% | 5.103% | 9.964%
Receivables +60: | 17798.28 | Paid in July |  | Receivables +60: | 0
Unbilled Status: | 14728.99 |  |  | Unbilled Status: | 13129.84 | 13.8K Accruals
Other: |  |  |  | Other:
PS Contract #: | 23622
Contract Type: | T&M
Contract # | CO-9772-ACCS
Customer: | NATO HQ
Consultant Name: | Claveau
Est Period of Performance: | 11/20/06 - 07/06/07
Contract Value: | 101318
Contract Funding: | 101318
EAC: | 101242
CAC: | 100625
Funding Status: | 76
Profit Analysis: | MTD | YTD | CTD
Revenue: | 13876 | 78715 | 86079
Cost: | 13799 | 83528 | 90329
Profit: | 0.558% | -5.762% | -4.705%
Receivables +60: | 0
Unbilled Status: | 11473.59 | Accruals
Other:
PS Contract #: | 23658 |  |  | PS Contract #: | 23659
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-9772-ACCS |  |  | Contract # | CO-9772-ACCS
Customer: | NATO HQ |  |  | Customer: | NATO HQ
Employee Name: | Mattes |  |  | Consultant Name: | Vanham
Est Period of Performance: | 01/08/07 - 12/31/07 |  |  | Est Period of Performance: | 01/08/07 - 06/30/07
Contract Value: | 370703 |  |  | Contract Value: | 182652
Contract Funding: | 370703 |  |  | Contract Funding: | 182652
EAC: | 347873 |  |  | EAC: | 130621
CAC: | 196444 |  |  | CAC: | 108174
Funding Status: | 22830 |  |  | Funding Status: | 52031
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 32256 | 170241 | 170241 | Revenue: | -4318 | 130620 | 130621
Cost: | 18941 | 101905 | 101905 | Cost: | -2453 | 108173 | 108174
Profit: | 70.3% | 67.06% | 67.06% | Profit: | 76.03% | 20.75% | 20.75%
Receivables +60: | 34174.01 | Paid in July |  | Receivables +60: | 32620.64 | Paid in July
Unbilled Status: | 29477.96 | WIP |  | Unbilled Status: | 20391.12 | 21K Accruals
Other: |  |  |  | Other:
PS Contract #: | 23735 |  |  | PS Contract #: | 23790
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-9772-ACCS |  |  | Contract # | CO-9772-ACCS
Customer: | NATO HQ |  |  | Customer: | NATO HQ
Consultant Name: | Dewil |  |  | Consultant Name: | Stephenson
Est Period of Performance: | 02/15/07 - 09/28/07 |  |  | Est Period of Performance: | 3/29/07-9/28/07
Contract Value: | 186509 |  |  | Contract Value: | 150406
Contract Funding: | 186509 |  |  | Contract Funding: | 150406
EAC: | 183468 |  |  | EAC: | 161923
CAC: | 159496 |  |  | CAC: | 128107
Funding Status: | 3041 |  |  | Funding Status: | -11517
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 29307 | 105057 | 105057 | Revenue: | 24816 | 67369 | 67369
Cost: | 26634 | 94613 | 94612 | Cost: | 20812 | 55619 | 55619
Profit: | 10.04% | 11.04% | 11.04% | Profit: | 19.24% | 21.13% | 21.13%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 22327.94 | 22.6K Accruals |  | Unbilled Status: | 21424.82 | Accruals
Other: |  |  |  | Other:
PS Contract #: | 23793 |  |  | PS Contract #: | 23794
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-9772-ACCS |  |  | Contract # | CO-9772-ACCS
Customer: | NATO HQ |  |  | Customer: | NATO HQ
Consultant Name: | Grandjean |  |  | Consultant Name: | LRE Team
Est Period of Performance: | 3/28/07-9/28/07 |  |  | Est Period of Performance: | 4/10/07-7/31/07
Contract Value: | 194856 |  |  | Contract Value: | 234271
Contract Funding: | 194856 |  |  | Contract Funding: | 234271
EAC: | 183997 |  |  | EAC: | 347136
CAC: | 157328 |  |  | CAC: | 302757
Funding Status: | 10859 |  |  | Funding Status: | -112865
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 7789 | 59509 | 59509 | Revenue: | 73316 | 197636 | 197636
Cost: | 7647 | 53588 | 53588 | Cost: | 67539 | 179517 | 179517
Profit: | 1.857% | 11.05% | 11.05% | Profit: | 8.554% | 10.09% | 10.09%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 48767.57 | Accruals |  | Unbilled Status: | 66808.57 | Accruals
Other: |  |  |  | Other:
PS Contract #: | 21670 |  |  | PS Contract #: | 21672
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-11703-FMB |  |  | Contract # | CO-11541-ACE
Customer: | NC3A-BE |  |  | Customer: | NC3A-BE
Consultant Name: | Baker |  |  | Consultant Name: | Kouloukakos
Est Period of Performance: | 07/18/05 - 09/30/07 |  |  | Est Period of Performance: | 09/01/05 - 02/28/07
Contract Value: | 208933 |  |  | Contract Value: | 233930
Contract Funding: | 208933 |  |  | Contract Funding: | 233930
EAC: | 202195 |  |  | EAC: | 233759
CAC: | 185178 |  |  | CAC: | 194198
Funding Status: | 6738 |  |  | Funding Status: | 171
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 7090 | 37532 | 171067 | Revenue: | 0 | 23706 | 233759
Cost: | 6650 | 39788 | 156708 | Cost: | 0 | 21544 | 194198
Profit: | 6.617% | -5.67% | 9.163% | Profit: | #DIV/0! | 10.04% | 20.37%
Receivables +60: | 0 |  |  | Receivables +60: | 10828.19 | Paid in June
Unbilled Status: | 7671.95 | 7.9K accruals |  | Unbilled Status: | -922.7
Other: |  |  |  | Other: | Kouloukakos to start work again in Sept - Need Funding
PS Contract #: | 23289 |  |  | PS Contract #: | 23380
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-12006-CON |  |  | Contract # | CO-11459-NC3
Customer: | NC3A-BE |  |  | Customer: | NC3A-BE
Consultant Name: | Mitchell/Erten |  |  | Consultant Name: | Sansom
Est Period of Performance: | 06/12/06 - 06/30/07 |  |  | Est Period of Performance: | 07/18/06 - 5/31/07
Contract Value: | 114732 |  |  | Contract Value: | 147630
Contract Funding: | 114732 |  |  | Contract Funding: | 147630
EAC: | 115811 |  |  | EAC: | 147630
CAC: | 98598 |  |  | CAC: | 123163
Funding Status: | -1079 |  |  | Funding Status: | 0
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 9012 | 46189 | 107660 | Revenue: | 0 | 76153 | 147630
Cost: | 7024 | 39448 | 92423 | Cost: | 10 | 64155 | 123163
Profit: | 28.3% | 17.09% | 16.49% | Profit: | -100% | 18.7% | 19.87%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 10185.18 | 10.5K Accruals |  | Unbilled Status: | 10533.23 | 10.8K Accruals
Other: |  |  |  | Other: | Rec'd MOD for 45 days in July
PS Contract #: | 23645 |  |  | PS Contract #: | 23505
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-12195-CON |  |  | Contract # | TO 2
Customer: | NC3A-BE |  |  | Customer: | AREA 7
Consultant Name: | Smail |  |  | Consultant Name: | Briggs
Est Period of Performance: | 01/08/07 - 07/15/07 |  |  | Est Period of Performance: | 10/02/06 - 07/31/07
Contract Value: | 57608 |  |  | Contract Value: | 105735
Contract Funding: | 57608 |  |  | Contract Funding: | 105735
EAC: | 64886 |  |  | EAC: | 129232
CAC: | 58502 |  |  | CAC: | 110303
Funding Status: | -7278 |  |  | Funding Status: | -23497
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 7851 | 51782 | 51782 | Revenue: | 8725 | 49637 | 105735
Cost: | 7004 | 47582 | 47582 | Cost: | 7784 | 43340 | 90803
Profit: | 12.09% | 8.827% | 8.827% | Profit: | 12.09% | 14.53% | 16.44%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 7117.95 | 7.4K Accruals |  | Unbilled Status: | 7048.89 | Accruals
Other: | Rec'd MOD for 60 days in July |  |  | Other:
PS Contract #: | 23640 |  |  | PS Contract #: | 23641
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-12043-SSC |  |  | Contract # | CO-12043-SSC
Customer: | AREA 7 |  |  | Customer: | AREA 7
Consultant Name: | Joachim |  |  | Consultant Name: | Briggs
Est Period of Performance: | 12/14/06 - 07/31/07 |  |  | Est Period of Performance: | 12/14/06 - 07/31/07
Contract Value: | 153071 |  |  | Contract Value: | 58742
Contract Funding: | 153071 |  |  | Contract Funding: | 58742
EAC: | 158188 |  |  | EAC: | 63898
CAC: | 143176 |  |  | CAC: | 55216
Funding Status: | -5117 |  |  | Funding Status: | -5156
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 23105 | 132195 | 132195 | Revenue: | 9964 | 29152 | 38052
Cost: | 21710 | 120946 | 120946 | Cost: | 9137 | 26038 | 33766
Profit: | 6.426% | 9.301% | 9.301% | Profit: | 9.051% | 11.96% | 12.69%
Receivables +60: | 50542.52 | 27.5K pd July, 23K wait status |  | Receivables +60: | 0
Unbilled Status: | 20279.79 | Accruals |  | Unbilled Status: | 6918.88 | Accruals
Other: |  |  |  | Other:
PS Contract #: | 23683 |  |  | PS Contract #: | 23684
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | CO-12043-SSC |  |  | Contract # | CO-12043-SSC
Customer: | AREA 7 |  |  | Customer: | AREA 7
Consultant Name: | Walker |  |  | Consultant Name: | Smit
Est Period of Performance: | 02/12/07 - 08/31/07 |  |  | Est Period of Performance: | 01/26/07 - 09/30/07
Contract Value: | 148658 |  |  | Contract Value: | 205305
Contract Funding: | 148658 |  |  | Contract Funding: | 205305
EAC: | 179359 |  |  | EAC: | 218052
CAC: | 153000 |  |  | CAC: | 180566
Funding Status: | -30701 |  |  | Funding Status: | -12747
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 24797 | 108869 | 108869 | Revenue: | 27437 | 132852 | 132852
Cost: | 21798 | 94968 | 94968 | Cost: | 25506 | 123502 | 123501
Profit: | 13.76% | 14.64% | 14.64% | Profit: | 7.571% | 7.571% | 7.572%
Receivables +60: | 24671.44 | Waiting status |  | Receivables +60: | 31769.55 | Waiting on status
Unbilled Status: | 21140.6 | Accruals |  | Unbilled Status: | 76533.46 | Accruals
Other: |  |  |  | Other:
PS Contract #: | 23685 |  |  | PS Contract #: | 22170
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | TO 07 |  |  | Contract # | 4600001127
Customer: | AREA 7 |  |  | Customer: | NAMSA
Consultant Name: | Bailey |  |  | Consultant Name: | Garcia
Est Period of Performance: | 03/20/07 - 10/15/07 |  |  | Est Period of Performance: | 03/01/05 - 02/28/08
Contract Value: | 171810 |  |  | Contract Value: | 402577
Contract Funding: | 171810 |  |  | Contract Funding: | 402577
EAC: | 122425 |  |  | EAC: | 414761
CAC: | 125136 |  |  | CAC: | 359612
Funding Status: | 49385 |  |  | Funding Status: | -12184
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 18801 | 46061 | 46061 | Revenue: | 13169 | 67168 | 315621
Cost: | 16509 | 40116 | 40116 | Cost: | 14502 | 61838 | 274332
Profit: | 13.88% | 14.82% | 14.82% | Profit: | -9.192% | 8.619% | 15.05%
Receivables +60: | 0 |  |  | Receivables +60: | 0
Unbilled Status: | 13168.18 | Accruals |  | Unbilled Status: | 20113.47 | 11K Accruals; 9KWIP
Other: |  |  |  | Other:
PS Contract #: | 22171 |  |  | PS Contract #: | 23720
Contract Type: | T&M |  |  | Contract Type: | T&M
Contract # | 4600001110 |  |  | Contract # | 4600001187
Customer: | NAMSA |  |  | Customer: | NAMSA
Consultant Name: | Steinaers |  |  | Consultant Name: | Marshall
Est Period of Performance: | 04/01/05 - 12/31/07 |  |  | Est Period of Performance: | 03/05/07 - 09/05/07
Contract Value: | 585518 |  |  | Contract Value: | 59981
Contract Funding: | 585518 |  |  | Contract Funding: | 59981
EAC: | 576825 |  |  | EAC: | 59756
CAC: | 462028 |  |  | CAC: | 48372
Funding Status: | 8693 |  |  | Funding Status: | 225
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 21655 | 117026 | 444063 | Revenue: | 8581 | 30506 | 30506
Cost: | 20010 | 94775 | 359783 | Cost: | 7046 | 24972 | 24972
Profit: | 8.221% | 23.48% | 23.43% | Profit: | 21.79% | 22.16% | 22.16%
Receivables +60: | 0 |  |  | Receivables +60: | 102.19 | Discount, cleared in July
Unbilled Status: | 16793.2 | 18.9K Accruals |  | Unbilled Status: | -43.64
Other: |  |  |  | Other:
PS Contract #: | 23349 |  |  | PS Contract #: | 23407
Contract Type: | FP |  |  | Contract Type: | T&M
Contract # | 5080/JFCJQP&C/105-06 |  |  | Contract # | 4007109
Customer: | JFC HQ BRUNSSUM |  |  | Customer: | SHAPE
Employee Name: | Schiller |  |  | Employee Name: | Cornett
Est Period of Performance: | 07/10/06 - 04/30/07 |  |  | Est Period of Performance: | 08/01/06 - 01/31/08
Contract Value: | 173147 |  |  | Contract Value: | 311488
Contract Funding: | 173147 |  |  | Contract Funding: | 311488
EAC: | 168711 |  |  | EAC: | 291133
CAC: | 182114 |  |  | CAC: | 250031
Funding Status: | 4436 |  |  | Funding Status: | 20355
Profit Analysis: | MTD | YTD | CTD | Profit Analysis: | MTD | YTD | CTD
Revenue: | 708 | 64328 | 156711 | Revenue: | 15453 | 83374 | 163894
Cost: | 1701 | 77593 | 170269 | Cost: | 17144 | 81975 | 158090
Profit: | -58.38% | -17.1% | -7.963% | Profit: | -9.864% | 1.707% | 3.671%
Receivables +60: | 16351.2 | Paid in July |  | Receivables +60: | 0
Unbilled Status: | 4054.92 | WIP |  | Unbilled Status: | 11585.85 | WIP
Other: | Contract over, billing final invoice |  |  | Other:
PS Contract #: | 23824
Contract Type: | T&M
Contract # | 4007983
Customer: | SHAPE
Employee Name: | Hughes
Est Period of Performance: | 5/21/07-12/31/07
Contract Value: | 153555
Contract Funding: | 153555
EAC: | 124262
CAC: | 101379
Funding Status: | 29293
Profit Analysis: | MTD | YTD | CTD
Revenue: | 18962 | 18962 | 18962
Cost: | 20237 | 23379 | 23379
Profit: | -6.3% | -18.89% | -18.89%
Receivables +60: | 0
Unbilled Status: | 18961.94 | WIP
Other: