## PROFIT ANALYSIS
MPSR for ENVIRONMENTAL TEST AND INTEGRATION SUPPORT SERVICES (ETISS)
NATO PROFIT ANALYSIS
| Jan '07 | Feb '07 | Mar '07 | Apr '0 | May '07 | Jun '07 | Jul '07 | Aug '07 | Sep '07 | Oct' 07 | Nov' 07 | Dec' 07 | TOTAL
SALES | 736986 | 1185814 | 1170929 | 1291416 | 1309913 | 1407724 | 1525730 | 2146775 | 2227912 | 2015325 | 1999148 | 1962756
COST OF SALES | 844426 | 771304 | 870220 | 1106696 | 942979 | 1078898 | 1210539 | 1755204 | 1864664 | 1518539 | 1611204 | 1568664
INCOME FROM OPERATIONS | -161958 | 271191 | 174143 | 92097 | 250726 | 205580 | 241072 | 292585 | 250739 | 411643 | 294112 | 292177
PROFIT % | -21.98% | 22.87% | 14.87% | 7.131% | 19.14% | 14.6% | 15.8% | 13.63% | 11.25% | 20.43% | 14.71% | 14.89% | #DIV/0!

## Actual V. Forecast
Q2 NATO - Actuals V. Forecast Analysis
| Jan | Feb | Mar | Apr | May | Jun | JUL | AUG | SEP | OCT | NOV | DEC
FORECAST - Rev | 1500000 | 1500000 | 1300000 | 1203221 | 1275455 | 1271196 | 1525730 | 2146775 | 2227912 | 2015325 | 1999148 | 1962756 | 19927518
ACTUAL - Rev | 736986 | 1185814 | 1170929 | 1291416 | 1309913 | 1407724 | 1525730 | 2146775 | 2227912 | 2015325 | 1999148 | 1962756 | 18980428
VARIANCE | Q2 NATO - Actuals V. Forecast Analysis Jan: -763014; Q2 NATO - Actuals V. Forecast Analysis Feb: -314186; Q2 NATO - Actuals V. Forecast Analysis Mar: -129071; Q2 NATO - Actuals V. Forecast Analysis Apr: 88195; Q2 NATO - Actuals V. Forecast Analysis May: 34458; Q2 NATO - Actuals V. Forecast Analysis Jun: 136528
| Jan | Feb | Mar | Apr | May | Jun | JUL | AUG | SEP | OCT | NOV | DEC
FORECAST - Labor | 130193 | 130193 | 162742 | 248621 | 248621 | 248621 | 107968 | 126808 | 160491 | 107968 | 126808 | 160491
ACTUAL - Labor | 112241 | 111227 | 120804 | 107968 | 126808 | 160491 | 107968 | 126808 | 160491 | 107968 | 126808 | 160491 | 1530073
VARIANCE | Jan: -17952; Feb: -18966; Mar: -41938; Apr: -140653; May: -121813; Jun: -88130
| Jan | Feb | Mar | Apr | May | Jun | JUL | AUG | SEP | OCT | NOV | DEC
FORECAST - ODC | 1103761 | 1101843 | 878887 | 602360 | 695649 | 680456 | 1052000 | 1569000 | 1629000 | 1360000 | 1425000 | 1333000
ACTUAL - ODC | 676506 | 570875 | 685612 | 926586 | 747180 | 819631 | 1052000 | 1569000 | 1629000 | 1360000 | 1425000 | 1333000 | 12794390
VARIANCE | Jan: -427255; Feb: -530968; Mar: -193275; Apr: 324226; May: 51531; Jun: 139175
| Jan | Feb | Mar | Apr | May | Jun | JUL | AUG | SEP | OCT | NOV | DEC
FORECAST - EBIT | 145686 | 147654 | 121094 | 161996 | 138487 | 149821 | 241072 | 292585 | 250739 | 411643 | 294112 | 292177
ACTUAL - EBIT | -161958 | 271191 | 174143 | 92097 | 250726 | 205580 | 241072 | 292585 | 250739 | 411643 | 294112 | 292177 | 2614107
VARIANCE | Jan: -307644; Feb: 123537; Mar: 53049; Apr: -69899; May: 112239; Jun: 55759

## TOTAL
NATO CY 2007 FORECAST REVISIONS
DESCRIPTION | 2006 | 2007
| Original Forecast | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
|  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Revenue | 25491075 | 25491075 | 25251913 | 24712401 | 25491075 | 21943719 | 19112532 | 18980428 | 18980428 | 18980428 | 18980428 | 18980428 | 18980428
Labor | 1861300 | 1861300 | 1843348 | 1824382 | 2056624 | 1648729 | 1663537 | 1530073 | 1530073 | 1530073 | 1530073 | 1530073 | 1530073
Subs, Matls & Odc's | 19252376 | 19252376 | 19274591 | 18551655 | 17505871 | 15355105 | 12899759 | 12794390 | 6399674 | 6399674 | 6399674 | 6399674 | 6399674
JAN - ITSP gets extended. Revenue increased along with Labor decrease and sub Labor increase
FEB - Same
MAR - PASS and ETASS timing changing and Revenue, Labor and ODC's change.
APR - PASS and ETASS timing changing and Revenue, Labor and ODC's change.
MAY - PASS and ETASS timing changing and Revenue, Labor and ODC's change.
JUNE - Lost Phase 0 Task Orders which we bid on. Revenue, Labor and ODC's change.
Protest included as of June Forecast through August 31.

## REVENUE-LAB vs ODC's
NATO
REVENUE - LABOR vs ODC's
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | YTD TOTAL
REVENUE | 736986 | 1185814 | 1170929 | 1291416 | 1309913 | 1407724 | 1525730 | 2146775 | 2227912 | 2015325 | 1999148 | 1962756 | 18980428
LABOR | 112241 | 111227 | 120804 | 107968 | 126808 | 160491 | 107968 | 126808 | 160491 | 107968 | 126808 | 160491 | 1530073
ODC's | 676506 | 570875 | 685612 | 926586 | 747180 | 819631 | 1052000 | 1569000 | 1629000 | 1360000 | 1425000 | 1333000 | 12794390
% ODC TO REVENUE | 91.79% | 48.14% | 58.55% | 71.75% | 57.04% | 58.22% | 68.95% | 73.09% | 73.12% | 67.48% | 71.28% | 67.91%

## TOTAL (2)
NATO CY 2007 FORECAST REVISIONS
DESCRIPTION | 2006 | 2007
| Original Forecast | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
|  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Revenue | 25491075 | 1500000 | 1500000 | 1300000 | 1203221 | 1275455 | 1271196 | 1525730 | 2146775 | 2227912 | 2015325 | 1999148 | 1962756
Labor | 1861300 | 130193 | 130193 | 162742 | 248621 | 248621 | 248621 | 146378 | 151003 | 183551 | 151003 | 126808 | 160491
Subs, Matls & Odc's | 19252376 | 1103761 | 1101843 | 878887 | 602360 | 695649 | 680456 | 1052000 | 1569000 | 1629000 | 1360000 | 1425000 | 1333000
JAN - ITSP gets extended. Revenue increased along with Labor decrease and sub Labor increase
FEB - Same
MAR - PASS and ETASS timing changing and Revenue, Labor and ODC's change.
APR - PASS and ETASS timing changing and Revenue, Labor and ODC's change.
MAY - PASS and ETASS timing changing and Revenue, Labor and ODC's change.
JUNE - Lost Phase 0 Task Orders which we bid on. Revenue, Labor and ODC's change.
Protest included as of June Forecast through August 31.