## Sheet1
Lead ID | Short Title | BUGM | Stage | Lead Type | Prime/Sub | Expected RFP Date | Prop Due Date | Est. Award Date | Days outstanding | MT Value | Contract Category | BD Manager | Capture Manager | Action and comments
8105 | FilesX Training | C4ILOG | Proposal Outstanding | New | Prime | 2010-03-09 | 2010-04-30 | 2010-05-13 | 13 | 1000000 | Task Order | Clyne, Patricia | Paone, Nicholas
8331 | Alliant - Customer Support Office (CSO) | C4ILOG | Proposal Outstanding | New | Prime | 2010-04-19 | 2010-04-30 | 2010-05-20 | 20 | 9302260 | Task Order | Clyne, Patricia | Martin, Felix
8104 | NDIC Support extension | C4ILOG | Proposal Outstanding | Add-on | Subcontractor | 2010-06-01 | 2010-06-15 | 2010-07-15 | 30 | 2592000 | Task Order | Clyne, Patricia | Burgess, Charles
5223 | MDA - QS | SEIAERO | Proposal Outstanding | Recompete | Subcontractor | 2009-07-15 | 2009-08-17 | 2010-05-30 | 286 | 12502000 | IDIQ | Bryant, B Carter | Bryant, B Carter | Delayed by CO, but should happen by eo year
7433 | HMDS - Niitek | C4ILOG | Proposal Outstanding | New | Prime | 2010-03-29 | 2010-04-09 | 2010-05-19 | 40 | 3000000 | Basic Contract | Mancuso, Louis | Clyne, Patricia
7766 | GATA | C4ILOG | Proposal Outstanding | New | Subcontractor | 2010-03-15 | 2010-05-03 | 2010-06-15 | 43 | 41250000 | IDIQ | Markey, John | Rice, Robin
8079 | Yemen FSR | SSILOG | Proposal Outstanding | New | Prime | 2010-02-28 | 2010-04-02 | 2010-05-21 | 49 | 400000 | Basic Contract | Hansen, Richard | Hansen, Richard
8210 | QREWS | C4ILOG | Proposal Outstanding | New | Subcontractor | 2010-03-25 | 2010-04-28 | 2010-06-30 | 63 | 2800000 | IDIQ | Murphy, Kristen | Clyne, Patricia
7823 | COMM ANA | C4ILOG | Proposal Outstanding | New | Subcontractor | 2010-04-12 | 2010-04-29 | 2010-07-01 | 63 | 12500000 | Task Order | Lusk, Patrick | Arinello, Dennis
5964 | SMDC Battle Lab support | SEIAERO | Proposal Outstanding | New | Subcontractor | 2009-04-24 | 2009-06-26 | 2010-05-14 | 322 | 13333333.3333 | IDIQ | Bryant, B Carter | Bryant, B Carter | Delayed by CO.
7931 | STOS OY4 | C4ILOG | Proposal Outstanding | Other | Subcontractor | 2010-03-09 | 2010-03-10 | 2010-05-17 | 68 | 7000000 | Task Order | Markey, John | Rice, Robin
7861 | WAREHOUSE MANAGEMENT SUPPORT Albany GA for DSCA | SSILOG | Proposal Outstanding | New | Subcontractor | 2010-02-01 | 2010-05-05 | 2010-07-15 | 71 | 1600000 | Basic Contract | Hansen, Richard | Hansen, Richard
8037 | PM Prophet Storage and Mnt | C4ILOG | Proposal Outstanding | New | Prime | 2010-02-05 | 2010-02-25 | 2010-06-01 | 96 | 756000 | Task Order | Horvath, Andrew | Horvath, Andrew
7829 | MiDAESS Task Order - Admin Services | SEIAERO | Proposal Outstanding | New | Subcontractor | 2009-04-17 | 2009-08-17 | 2010-07-15 | 332 | 4800000 | Task Order | Bryant, B Carter | Bryant, B Carter | Delayed by CO.
8023 | GPMS OY3 | C4ILOG | Proposal Outstanding | Add-on | Prime | 2010-03-01 | 2010-03-10 | 2010-06-16 | 98 | 58000000 | Basic Contract | Horvath, Andrew | Hopewell, Joshua
4093 | MDA SEI/Test (Sub Gp 3) | SEIAERO | Proposal Outstanding | Recompete | Subcontractor | 2009-07-15 | 2009-08-17 | 2010-07-15 | 332 | 75000000 | Task Order | Bryant, B Carter | Fincher, Kennon | Delayed by CO.
5677 | MDA Inf & Dep (MiDAESS Gp 4) | SEIAERO | Proposal Outstanding | New | Subcontractor | 2009-07-15 | 2009-08-17 | 2010-07-15 | 332 | 12500000 | IDIQ | Bryant, B Carter | Bryant, B Carter | Delayde by CO.
8314 | JCCC Mod 1 | GCIS | Proposal Outstanding | New | Prime | 2010-03-15 | 2010-03-25 | 2010-05-31 | 67 | 5142940 | Basic Contract | Martin, Lindy | Martin, Lindy | Delayed by CO - Operational requirement evolving.
8155 | Polycom Reseller Agreement | GCIS | Proposal Outstanding | New | Prime | 2010-03-04 | 2010-03-08 | 2010-06-30 | 114 | 123758 | Basic Contract | Martin, Lindy | Schoenfelt, Stephen | Contacted customer for an update and projected award date on 26 Apr. Appears that they (NC3A)are waiting for funding and approval to buy. Follow up call planned for next week.
6999 | Support Services Contract (Area 1) | GCIS | Proposal Outstanding | New | Subcontractor | 2009-06-05 | 2009-08-31 | 2010-06-30 | 303 | 1800000 | Basic Contract | Martin, Lindy | Martin, Lindy | Delayed due to funding issues. Award expected by 30 June
5818 | Support Services Contract (Area 2) | GCIS | Proposal Outstanding | New | Prime | 2009-06-05 | 2009-08-31 | 2010-06-30 | 303 | 12000000 | Basic Contract | Martin, Lindy | Martin, Lindy | Delayed due to funding issues. Award not expected until 1st Qtr 2011.
7548 | PM Battle Command JCPD RTEP | C4ILOG | Proposal Outstanding | New | Subcontractor | 2010-01-07 | 2010-01-22 | 2010-06-01 | 130 | 500000 | Task Order | Palitto, Carolyn | Palitto, Carolyn
7134 | SCMP I (CACI) | SSILOG | Proposal Outstanding | New | Subcontractor | 2010-01-05 | 2010-02-01 | 2010-06-15 | 134 | 5000000 | Basic Contract | Ceballos, Lorenzo | Ceballos, Lorenzo | Date has been confirmed with the Prime from the KO of 15 June
7547 | GCCS-A/DRRS-A Development RTEP | C4ILOG | Proposal Outstanding | New | Subcontractor | 2009-11-13 | 2009-12-29 | 2010-06-01 | 154 | 3120000 | Task Order | Palitto, Carolyn | Palitto, Carolyn
6833 | OPTARSS II (SB SA) 1 | SEITE | Proposal Outstanding | New | Subcontractor | 2009-08-14 | 2009-12-16 | 2010-06-07 | 173 | 5769230.7692 | IDIQ | Landers, Ronald | Wright, Robert
6835 | OPTARSS II | SEITE | Proposal Outstanding | New | Subcontractor | 2009-08-14 | 2009-12-16 | 2010-06-07 | 173 | 5769230.7692 | IDIQ | Landers, Ronald | Wright, Robert
7475 | OPTARSS II | SEITE | Proposal Outstanding | New | Subcontractor | 2009-08-12 | 2009-12-16 | 2010-06-07 | 173 | 5769230.7692 | IDIQ | Landers, Ronald | Wright, Robert
7339 | OPTARSS II- Small Business | SEITE | Proposal Outstanding | New | Subcontractor | 2009-08-12 | 2009-12-16 | 2010-06-07 | 173 | 5769230.7692 | IDIQ | Landers, Ronald | Wright, Robert
5081 | USAFE Communications Support | C4ILOG | Proposal Outstanding | Recompete | Prime | 2009-10-22 | 2009-12-23 | 2010-06-15 | 174 | 40200000 | Basic Contract | Wood, Peter | Lancaster, Michael | UCSC: responded to ENs. Expect FPR before end of May. Award on/about 15 June.
5817 | Support Services (Area 3 - Area 7 Re-compete) | GCIS | Proposal Outstanding | Recompete | Prime | 2009-06-05 | 2009-08-31 | 2010-06-30 | 303 | 12000000 | Basic Contract | Martin, Lindy | Martin, Lindy | Delayed due to funding issues. Award expected by 30 June
7467 | Field Service Representative Support For The U.S. Marine Corps Mine Roller System | SSILOG | Proposal Outstanding | New | Prime | 2009-10-29 | 2009-12-15 | 2010-06-16 | 183 | 19688212 | Basic Contract | Hansen, Richard | Hansen, Richard | Contacted by KO last week requesting us to hold pricnig for another 6- days which we are.
7824 | SETA AFghan | C4ILOG | Proposal Outstanding | New | Subcontractor | 2009-12-18 | 2009-12-21 | 2010-07-01 | 192 | 7000000 | Task Order | Lusk, Patrick | Arinello, Dennis
7410 | OPTARSS II (SB SA) 3 | C4ILOG | Proposal Outstanding | New | Subcontractor | 2009-08-14 | 2009-12-16 | 2010-06-30 | 196 | 10416666.6667 | IDIQ | Hopewell, Joshua | Horvath, Andrew
6032 | STARS II | C4ILOG | Proposal Outstanding | New | Subcontractor | 2009-08-25 | 2009-10-01 | 2010-06-01 | 243 | 1000000 | IDIQ | Clyne, Patricia | Paone, Nicholas
6120 | MPO - ISPEMS II | GCIS | Proposal Outstanding | Recompete | Prime | 2010-03-17 | 2010-04-07 | 2010-05-14 | 37 | 47562091 | Basic Contract | Polmar, Michael | Martin, Felix | N/A
7391 | JNCC-A | C4ILOG | Proposal Outstanding | New | Subcontractor | 2009-08-26 | 2009-12-11 | 2010-09-30 | 293 | 14040000 | Basic Contract | Davis, Winston | Murphy, Kristen
5244 | Wallops Range Operations | GCIS | Proposal Outstanding | New | Prime | 2008-12-09 | 2009-02-20 | 2011-01-01 | 680 | 117000000 | Basic Contract | Rhoades, Gregory | Rhoades, Gregory | CO notified MT last week that award was pushed out to 2/20/2011. Award was slowed down by a curent protest of the origional SKENS/NENS contract
7971 | RTS Aurora VTS-1000/7 | GCIS | Proposal Outstanding | New | Prime | 2010-01-25 | 2010-02-12 | 2010-06-21 | 129 | 500000 | Basic Contract | Rovitti, Paul | Rovitti, Paul | RTS expects to hear from Ft. Monmouth in two weeks or less regarding their proposal to establish a Repair Depot in India for the Firefinder system. Once their proposal is accepted, RTS should issue a PO to ManTech for the VTS-1000 and associated spares.
8200 | Studio VTC Spares | GCIS | Proposal Outstanding | Other | Prime | 2010-01-04 | 2010-02-17 | 2010-05-26 | 98 | 55933 | Basic Contract | Schoenfelt, Stephen | Headen, Sidney | Awaiting award
7095 | ICTA | SEITE | Proposal Outstanding | New | Subcontractor | 2009-07-06 | 2009-09-08 | 2010-07-15 | 310 | 7500000 | IDIQ | Landers, Ronald | Landers, Ronald
6088 | INSCOM OMNIBUS III (IT SB) | C4ILOG | Proposal Outstanding | Recompete | JV | 2009-11-13 | 2010-01-15 | 2010-11-30 | 319 | 6600000 | IDIQ | Davis, Winston | Davis, Winston
8199 | The Hague HDX4K | GCIS | Proposal Outstanding | New | Prime | 2010-03-15 | 2010-03-18 | 2010-06-30 | 104 | 10531 | Basic Contract | Schoenfelt, Stephen | Schoenfelt, Stephen | Contacted customer for an update and projected award date on 26 Apr. Appears that they (NC3A)are waiting for funding and approval to buy. Follow up call planned for next week.
8187 | The Hague | GCIS | Proposal Outstanding | New | Prime | 2010-03-11 | 2010-03-15 | 2010-06-30 | 107 | 99500 | Basic Contract | Schoenfelt, Stephen | Schoenfelt, Stephen | Contacted customer for an update and projected award date on 26 Apr. Appears that they (NC3A)are waiting for funding and approval to buy. Follow up call planned for next week.
8119 | Add-on for CO-12734-VTC | GCIS | Proposal Outstanding | Add-on | Prime | 2010-02-25 | 2010-03-03 | 2010-06-30 | 119 | 13858 | Basic Contract | Schoenfelt, Stephen | Schoenfelt, Stephen | Contacted customer for an update and projected award date on 26 Apr. Appears that they (NC3A)are waiting for funding and approval to buy. Follow up call planned for next week.
7849 | Products Q3 | SEIAERO | Proposal Outstanding | Add-on | Prime | 2010-02-16 | 2010-02-26 | 2010-07-01 | 125 | 1200000 | Basic Contract | Stone, Edward | Moore, James | Regular sales pipeline for polymer materials. Purchase order driven.
5861 | ITS-SB | C4ILOG | Proposal Outstanding | New | Subcontractor | 2009-03-27 | 2009-04-23 | 2010-05-31 | 403 | 5000000 | IDIQ | Davis, Winston | Palitto, Carolyn
5991 | Acota Training | C4ILOG | Proposal Outstanding | Add-on | Subcontractor | 2009-03-28 | 2009-05-14 | 2010-09-30 | 504 | 750000 | Basic Contract | Clyne, Patricia | Smith, Thomas
3584 | CSMC | SEIAERO | Proposal Outstanding | Recompete | Subcontractor | 2009-09-14 | 2009-12-21 | 2010-06-15 | 176 | 9000000 | IDIQ | Stone, Edward | Lucas, Richard | Still on time for an IDIQ award
| Total | [8 empty] | 607736006.0768