## NTM-B BOE(Max Likely)
| PL: | P-13527
| RFP: | LJLA10021/LR-RBG-6000446638
| Offeror: | ManTech Telecommunications and Information Systems Corporation | [7 empty] | = Expected end state of a Svce
| Title: | NATO ITM-B
| Monthly FTE Hours | 220
| FTE Count by Scenario |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
| 48 |  |  |  | Most likely | bar: 3; 5; 8 to 15; 18 to 19; 21; 25; 27 to 28; 30 to 32; 34
| 13 |  |  |  | Minimum | bar: 6; 9; 16; 20; 22; 26; 33
| 10 |  |  |  | Butmir | bar: 3 to 4; 14; 19; 28
| WBS# |  |  |  | Contract Line | Phase I | Phase II | 1 | 2 | 3 | 4.1 | 4.2 | 4.3 | 5.1 | 5.2 | 5.3 | 5.4 | 5.5 | 6.1 | 6.2 | 7.1 | 7.2 | 7.3 | 8 | 9.1 | 19 | 10.1 | 10.2 | 10.3 | 10.4 | 11.1 | 11.2 | 12 | 13.1 | 13.2 | 14 | 15 | 16 | 16.2 |  | FILTER
[5 empty] | Service | Transition | Acceptance & Ramp-up | AIS | M131 | M131 | U131 | U131 | U131 | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | VTC and IDNX Support | VTC and IDNX Support | Service desk and Network Monitoring | Service desk and Network Monitoring | Service desk and Network Monitoring | Crypto | Configuration Management | Configuration Management | Telephone Services | Telephone Services | Telephone Services | Telephone Services | Management, Admin and tech support for Leased lines | Management, Admin and tech support for Leased lines | RCC/LOT House Support | MTCT | MTCT | Stock Management and Property Accounting | Assistance to Presentations | Contract Management | Contract Management |  | 1
[5 empty] | Package Name | Transition | Acceptance & Ramp-up | PAIS/0 | PM131/0 | PM131/1 | PU131/1 | PU131/2 | PU131/3 | PMNSA/1 | PMNSA/2 | PMNSA/3 | PMNSA/4 | PMNSA/5 | PVTCI/0 | PVTCI/1 | PSDNM/1 | PSDNM/2 | PSDNM/3 | PCCM/0 | PCCM/1 | PCCM/2 | PTS/1 | PVS/2 | PVS/3 | PVS/4 | PLLS/1 | PLLS/2 | RCCLOT/0 | MTCT/1 | MTCT/2 | SMPA/1 | PRES/1 | PCON/1 | PCON/2
[5 empty] | Package Contents | Transition | Acceptance & Ramp-up | AIS (NS) Server Admin[1], Network and cable Infrastructure[2], Desktop Support[3] | M131 (MS) Server Admin, Network and cable Infrastructure, Desktop Support for =<150 Workstations | M131 (MS) Server Admin, Network and cable Infrastructure, Desktop Support for =>150 Workstations | U131 (Unclassified) Server Admin for Bldg 001, Network and cable Infrastructure, Desktop Support for <=100 Workstations | U131 (Unclassified) Server Admin for Camp Butmir and Bldg 001 only, Network and cable Infrastructure for <=200 Workstations | U131 (Unclassified) Server Admin for Camp Butmir and Bldg 001, Network and cable Infrastructure, Desktop Support for <=500 Workstations | Desktop Support for <= 10 standalone workstations or Laptops, support for <= 20 NROI (NATO Restricted over the Internet) Laptops | Administrative Support for all standalone Workstations or Laptops as detailed in Statement of Work | Support for ID Card Network, including all workstations and associated network devices and infrastructure | Support for DOCEX, including all workstations and associated network devices and infrastructure | Support for NDSS, including all workstations and associated network devices and infrastructure | Provision, maintenance, operation and administration of secure VTC Services and equipment | Crypto engineering, support and maintenance | Provision of Service Desk service during normal business hours 8:30 until 17:00 hrs Mon to Fri at Bldg 001 only | Provision of Service Desk service during normal business hours 8:30 until 17:00 hrs Mon to Fri at Bldg 001 and Camp Butmir | Provision of Service Desk service 0745 hrs until 1815 hrs Mon to Fri at Camp Butmir, Sat 07:45 until 12:00, and 0900 hrs until 1700 hrs Mon-Fri Bldg 001. Network Control Desk (NCD) manned 24/7 at Camp Butmir | Maintenance of Cryptographic accounts at Camp Butmir etc. | Configuration Management of CIS Facilities at Bldg 001 | Configuration Management of CIS Facilities at Camp Butmir, Bldg 001 and all locations within theatre | Maintenance and operation of PBX and associated lines and handsets in Bldg 001 and support of <= 100 telephone handsets | Attended service (duty hours), maintenance and operation of PBX and associated lines and handsets in Bldg 001 and support of <= 100 telephone handsets | Attended service (24/7), maintenance, and operation of PBX, SDH and all telephone assets as details in Annex F of Statement of Work and support of <= 750 telephone handsets | Attended service (24/7), maintenance, and operation of PBX, SDH and all telephone assets as details in Annex F of Statement of Work and support of <= 1500 telephone handsets | Management, administration and technical support of leased communication lines providing CIS facilities to Bldg 001 | Management, administration and technical support of leased communication lines providing CIS facilities to NHQ Sarajevo/EUFOR HQ in Camp Butmir and all locations with BiH as details in Statement of Work V1.0 | Hardware and software support for EUFOR RCC/LOT House workstations, this is limited to telephone assistance from Camp Butmir and to those workstations delivered to the Contractors ADP Maintenance workshop in Building 200, Camp Butmir | Provide one people to support the MTCT | Provide two person to support the MTCT | Provide Staff to operate the Depot and provide Stock Management and Property Accounting (Please see below Para. 4. Depot Workload Statistics) | Provide technical assistance to presentations and seminars | Management of O&M contract for services provided to NHQ Sa facilities in Bldg 001 | Management of O&M contract for services provided to NHQ Sarajevo/EUFOR HQ in Camp Butmir and all locations with BiH and facilities in Bldg 001
[5 empty] | SOW Paras | 5.1, 5.2, 5.3, 5.4, 5.6, 5.8, 5.11, 5.15, 5.16 5.17, 5.18, 5.20 | 5.1, 5.2, 5.3, 5.4, 5.6, 5.8, 5.11, 5.15, 5.16 5.17, 5.18, 5.20 | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.11, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.11, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1, 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16 | 3.1, 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16 | 3.26 | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.11, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 | 3.4 | 3.6 | 3.6 | 3.6 | 3.11 | 3.17 | 3.17 | 3.12 | 3.12 | 3.12 | 3.12 | 3.13 | 3.13 | 3.4, 3.5 | 3.27 | 3.27 | 3.28 | 3.29 | 3.18, 3.19, 3.20, 3.21 3.22, 3.23, 3.24, 3.25 | 3.18, 3.19, 3.20, 3.21 3.22, 3.23, 3.24, 3.25
[6 empty] | 2 weeks | 6 weeks
| Brass Ring | MT Job Code | Current Lab Cats | Site | Total Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  | 1
[5 empty] | 0 | 1.8182 | 19 | 4 | 3 | 5 | 3 | 5 | 7 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 4 | 1 | 1 | 1 | 2 | 2 | 4 | 4 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2.1818 | 2.1818 |  | 0
| Government Site |  |  |  |  | 400 | 4180 | 880 | 660 | 1100 | 660 | 1100 | 1540 | 220 | 440 | 440 | 440 | 440 | 220 | 220 | 440 | 660 | 880 | 220 | 220 | 220 | 440 | 440 | 880 | 880 | 220 | 440 | 220 | 220 | 440 | 440 | 220 | 480 | 480 |  | 1
1 | Project Manager | Vanleishout,Ronald W | ManTech | Govt | 220 | 100 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 3300 | 1
2 | Project Manager, Deputy | Capurro,Jorge L | ManTech | Govt | 220 | 100 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 2420 | 1
3 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 3300 | 0 | 220 | 0 | 0 | 220 | 0 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 0 | 220 | 0 | 0 | 1100 | 1
4 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 880 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 1100 | 1
5 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2420 | 1
6 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540 | 1
7 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 0
8 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0
9 | Help Desk Specialist | Allison,James S | ManTech | Govt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0
10 | Help Desk Specialist | Allison,James S | ManTech | Govt | 1320 | 0 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
11 | Help Desk Specialist, Staff | Allison,James S | ManTech | Govt | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 1
12 | Help Desk Specialist | Allison,James S | ManTech | Govt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0
13 | Help Desk Specialist | Allison,James S | ManTech | Govt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0
14 | NDSS - NTM-B | Hughes,Christopher J | ManTech | Govt | 880 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2860 | 1
15 | NDSS - Logistician Tech | Hughes,Christopher J | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 0 | 0 | 660 | 1
16 | Network Engineer | Butler,David | ManTech | Govt | 1100 | 100 | 220 | 440 | 220 | 440 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
17 | Systems Administrator | Hawi,Jason N | ManTech | Govt | 1320 | 100 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
18 | Systems Administrator | Hawi,Jason N | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
19 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 1540 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
20 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 1540 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
21 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 1100 | 0 | 220 | 0 | 0 | 0 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4400 | 1
22 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 1
23 | Switchboard Operator A | Ilarraza,Margaret R | LocalNational | Govt_Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Switchboard Operator B | Ilarraza,Margaret R | LocalNational | Govt_Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Site Manager/Crypto Custodian | Boston, Randall | ManTech | Govt | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
26 | Configuration Manager | Hawi,Jason N | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
27 | Project Control Analyst | Wendy Bibb | ManTech | Contr | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 |  | 1
| TOTAL LABOR |  |  |  | 16320 | 400 | 4180 | 880 | 660 | 1100 | 660 | 1100 | 1540 | 220 | 440 | 440 | 440 | 440 | 220 | 220 | 440 | 660 | 880 | 220 | 220 | 220 | 440 | 440 | 880 | 880 | 220 | 440 | 220 | 220 | 440 | 440 | 220 | 480 | 480 |  | 1
[6 empty] | 2: 4140 |  | 1
| Other Direct Costs |  |  |  |  | 2: 18.8182 |  | 1
28 | DBA Insurance | 2% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
29 | War Risk Insurance | 100 |  |  | 9381.8182 | 181.8182 | 1800 | 400 | 300 | 500 | 300 | 500 | 700 | 100 | 200 | 200 | 200 | 200 | 100 | 100 | 200 | 300 | 400 | 100 | 0 | 0 | 200 | 200 | 400 | 400 | 100 | 200 | 100 | 100 | 200 | 200 | 100 | 200 | 200 |  | 1
30 | Bonus/COLA | 500 |  |  | 46000 | 0 | 9000 | 2000 | 1500 | 2500 | 1500 | 2500 | 3500 | 500 | 1000 | 1000 | 1000 | 1000 | 500 | 500 | 1000 | 1500 | 2000 | 500 | 0 | 0 | 1000 | 1000 | 2000 | 2000 | 500 | 1000 | 500 | 500 | 1000 | 1000 | 500 | 1000 | 1000 |  | 1
31 | Visas | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
32 | Passports $175*[(21New*1)] | 175 |  |  | 4375 | 0 | 3325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 525 |  | 1
33 | Immunizations/medical exams $400*(21New*1) | 400 |  |  | 10000 | 0 | 7600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 |  | 1
34 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
35 | Truck Lease 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
36 | Fuel (Truck Lease 1) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
37 | Van Lease 1 | 1450 |  |  | 4350 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 |  | 1
38 | Fuel (Van Lease 2) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
39 | Van Lease 2 | 1450 |  |  | 4350 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 |  | 1
40 | Fuel (Van Lease 3) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
41 | Cell Phone | 400 |  |  | 1600 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 |  | 1
42 | Travel | 7726.4 | 32049.25 | 0 | 51087.15 | 7726.4 | 32049.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5655.75 | 5655.75 |  | 1
| Total ODC's |  |  |  | 131143.9682 | 11208.2182 | 57074.25 | 2400 | 1800 | 3000 | 1800 | 3000 | 4200 | 600 | 1200 | 1200 | 1200 | 1200 | 600 | 600 | 1200 | 1800 | 2400 | 600 | 0 | 0 | 1200 | 1200 | 2400 | 2400 | 600 | 1200 | 600 | 600 | 1200 | 1200 | 600 | 10430.75 | 10430.75 |  | 1
1
| Materials | [39 empty] | 1
43 | Tools & Supplies (Plug) | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 |  | 1
44 | Material #2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
45 | Material #3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
46 | Material #4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
47 | Material #5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Materials |  |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 |  | 1
1
| Subcontractors | [39 empty] | 1
48 | Subcontractor |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
49 | Consultant |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
50 | LocalNational |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
51 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
52 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
53 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
54 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
55 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Materials |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
132143.9682

## NTM-B BOE(Butmir+Likely)
| PL: | P-13527
| RFP: | LJLA10021/LR-RBG-6000446638
| Offeror: | ManTech Telecommunications and Information Systems Corporation | [7 empty] | = Expected end state of a Svce
| Title: | NATO ITM-B
| Monthly FTE Hours | 220
| FTE Count by Scenario |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
| 30 |  |  |  | Most likely | bar: 3; 5; 8 to 9; 14; 16; 19 to 20; 22; 27 to 28; 34
| 13 |  |  |  | Minimum | bar: 6; 9; 16; 20; 22; 26; 33
| 10 |  |  |  | Minimum Butmir | bar: 3 to 4; 14; 19; 28
| WBS# |  |  |  | Contract Line | Phase I | Phase II | 1 | 2 | 3 | 4.1 | 4.2 | 4.3 | 5.1 | 5.2 | 5.3 | 5.4 | 5.5 | 6.1 | 6.2 | 7.1 | 7.2 | 7.3 | 8 | 9.1 | 19 | 10.1 | 10.2 | 10.3 | 10.4 | 11.1 | 11.2 | 12 | 13.1 | 13.2 | 14 | 15 | 16 | 16.2 |  | FILTER
[5 empty] | Service | Transition | Acceptance & Ramp-up | AIS | M131 | M131 | U131 | U131 | U131 | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | VTC and IDNX Support | VTC and IDNX Support | Service desk and Network Monitoring | Service desk and Network Monitoring | Service desk and Network Monitoring | Crypto | Configuration Management | Configuration Management | Telephone Services | Telephone Services | Telephone Services | Telephone Services | Management, Admin and tech support for Leased lines | Management, Admin and tech support for Leased lines | RCC/LOT House Support | MTCT | MTCT | Stock Management and Property Accounting | Assistance to Presentations | Contract Management | Contract Management |  | 1
[5 empty] | Package Name | Transition | Acceptance & Ramp-up | PAIS/0 | PM131/0 | PM131/1 | PU131/1 | PU131/2 | PU131/3 | PMNSA/1 | PMNSA/2 | PMNSA/3 | PMNSA/4 | PMNSA/5 | PVTCI/0 | PVTCI/1 | PSDNM/1 | PSDNM/2 | PSDNM/3 | PCCM/0 | PCCM/1 | PCCM/2 | PTS/1 | PVS/2 | PVS/3 | PVS/4 | PLLS/1 | PLLS/2 | RCCLOT/0 | MTCT/1 | MTCT/2 | SMPA/1 | PRES/1 | PCON/1 | PCON/2
[5 empty] | Package Contents | Transition | Acceptance & Ramp-up | AIS (NS) Server Admin[1], Network and cable Infrastructure[2], Desktop Support[3] | M131 (MS) Server Admin, Network and cable Infrastructure, Desktop Support for =<150 Workstations | M131 (MS) Server Admin, Network and cable Infrastructure, Desktop Support for =>150 Workstations | U131 (Unclassified) Server Admin for Bldg 001, Network and cable Infrastructure, Desktop Support for <=100 Workstations | U131 (Unclassified) Server Admin for Camp Butmir and Bldg 001 only, Network and cable Infrastructure for <=200 Workstations | U131 (Unclassified) Server Admin for Camp Butmir and Bldg 001, Network and cable Infrastructure, Desktop Support for <=500 Workstations | Desktop Support for <= 10 standalone workstations or Laptops, support for <= 20 NROI (NATO Restricted over the Internet) Laptops | Administrative Support for all standalone Workstations or Laptops as detailed in Statement of Work | Support for ID Card Network, including all workstations and associated network devices and infrastructure | Support for DOCEX, including all workstations and associated network devices and infrastructure | Support for NDSS, including all workstations and associated network devices and infrastructure | Provision, maintenance, operation and administration of secure VTC Services and equipment | Crypto engineering, support and maintenance | Provision of Service Desk service during normal business hours 8:30 until 17:00 hrs Mon to Fri at Bldg 001 only | Provision of Service Desk service during normal business hours 8:30 until 17:00 hrs Mon to Fri at Bldg 001 and Camp Butmir | Provision of Service Desk service 0745 hrs until 1815 hrs Mon to Fri at Camp Butmir, Sat 07:45 until 12:00, and 0900 hrs until 1700 hrs Mon-Fri Bldg 001. Network Control Desk (NCD) manned 24/7 at Camp Butmir | Maintenance of Cryptographic accounts at Camp Butmir etc. | Configuration Management of CIS Facilities at Bldg 001 | Configuration Management of CIS Facilities at Camp Butmir, Bldg 001 and all locations within theatre | Maintenance and operation of PBX and associated lines and handsets in Bldg 001 and support of <= 100 telephone handsets | Attended service (duty hours), maintenance and operation of PBX and associated lines and handsets in Bldg 001 and support of <= 100 telephone handsets | Attended service (24/7), maintenance, and operation of PBX, SDH and all telephone assets as details in Annex F of Statement of Work and support of <= 750 telephone handsets | Attended service (24/7), maintenance, and operation of PBX, SDH and all telephone assets as details in Annex F of Statement of Work and support of <= 1500 telephone handsets | Management, administration and technical support of leased communication lines providing CIS facilities to Bldg 001 | Management, administration and technical support of leased communication lines providing CIS facilities to NHQ Sarajevo/EUFOR HQ in Camp Butmir and all locations with BiH as details in Statement of Work V1.0 | Hardware and software support for EUFOR RCC/LOT House workstations, this is limited to telephone assistance from Camp Butmir and to those workstations delivered to the Contractors ADP Maintenance workshop in Building 200, Camp Butmir | Provide one people to support the MTCT | Provide two person to support the MTCT | Provide Staff to operate the Depot and provide Stock Management and Property Accounting (Please see below Para. 4. Depot Workload Statistics) | Provide technical assistance to presentations and seminars | Management of O&M contract for services provided to NHQ Sa facilities in Bldg 001 | Management of O&M contract for services provided to NHQ Sarajevo/EUFOR HQ in Camp Butmir and all locations with BiH and facilities in Bldg 001
[5 empty] | SOW Paras | 5.1, 5.2, 5.3, 5.4, 5.6, 5.8, 5.11, 5.15, 5.16 5.17, 5.18, 5.20 | 5.1, 5.2, 5.3, 5.4, 5.6, 5.8, 5.11, 5.15, 5.16 5.17, 5.18, 5.20 | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.11, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.11, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1, 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16 | 3.1, 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16 | 3.26 | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.11, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 | 3.4 | 3.6 | 3.6 | 3.6 | 3.11 | 3.17 | 3.17 | 3.12 | 3.12 | 3.12 | 3.12 | 3.13 | 3.13 | 3.4, 3.5 | 3.27 | 3.27 | 3.28 | 3.29 | 3.18, 3.19, 3.20, 3.21 3.22, 3.23, 3.24, 3.25 | 3.18, 3.19, 3.20, 3.21 3.22, 3.23, 3.24, 3.25
| Brass Ring | MT Job Code | Current Lab Cats | Site | Total Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  | 1
[5 empty] | 0 | 2 weeks | 6 weeks | 4 | 3 | 5 | 3 | 5 | 7 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 4 | 1 | 1 | 1 | 2 | 2 | 4 | 4 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2.1818 | 2.1818 |  | 0
| Government Site | [6 empty] | 880 | 660 | 1100 | 660 | 1100 | 1540 | 220 | 440 | 440 | 440 | 440 | 220 | 220 | 440 | 660 | 880 | 220 | 220 | 220 | 440 | 440 | 880 | 880 | 220 | 440 | 220 | 220 | 440 | 440 | 220 | 480 | 480 |  | 1
1 | Project Manager | Vanleishout,Ronald W | ManTech | Govt | 220 | 100 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 3300 | 1
2 | Project Manager, Deputy | Capurro,Jorge L | ManTech | Govt | 220 | 100 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 2420 | 1
3 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 3300 | 0 | 220 | 0 | 0 | 220 | 0 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 0 | 220 | 0 | 0 | 1100 | 1
4 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 880 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 1100 | 1
5 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2420 | 1
6 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540 | 1
7 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 0
8 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0
9 | Help Desk Specialist | Allison,James S | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0
10 | Help Desk Specialist | Allison,James S | ManTech | Govt | 1320 | 0 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
11 | Help Desk Specialist, Staff | Allison,James S | ManTech | Govt | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 1
12 | Help Desk Specialist | Allison,James S | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0
13 | Help Desk Specialist | Allison,James S | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0
14 | NDSS - NTM-B | Hughes,Christopher J | ManTech | Govt | 880 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2860 | 1
15 | NDSS - Logistician Tech | Hughes,Christopher J | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 0 | 0 | 660 | 1
16 | Network Engineer | Butler,David | ManTech | Govt | 1100 | 100 | 220 | 440 | 220 | 440 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
17 | Systems Administrator | Hawi,Jason N | ManTech | Govt | 1320 | 100 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
18 | Systems Administrator | Hawi,Jason N | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
19 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 1540 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
20 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 1540 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
21 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 1100 | 0 | 220 | 0 | 0 | 0 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4400 | 1
22 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 1
23 | Switchboard Operator A | Ilarraza,Margaret R | LocalNational | Govt_Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Switchboard Operator B | Ilarraza,Margaret R | LocalNational | Govt_Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Site Manager/Crypto Custodian | Boston, Randall | ManTech | Govt | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
26 | Configuration Manager | Hawi,Jason N | ManTech | Govt | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
27 | Project Control Analyst | Wendy Bibb | ManTech | Contr | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 |  | 1
| TOTAL LABOR |  |  |  | 16320 | 400 | 4840 | 880 | 660 | 1100 | 660 | 1100 | 1540 | 220 | 440 | 440 | 440 | 440 | 220 | 220 | 440 | 660 | 880 | 220 | 220 | 220 | 440 | 440 | 880 | 880 | 220 | 440 | 220 | 220 | 440 | 440 | 220 | 480 | 480 |  | 1
1
| Other Direct Costs | [39 empty] | 1
28 | DBA Insurance | 2% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
29 | War Risk Insurance | 100 |  |  | 9981.8182 | 181.8182 | 2200 | 400 | 300 | 500 | 300 | 500 | 700 | 100 | 200 | 200 | 200 | 200 | 100 | 100 | 200 | 300 | 400 | 100 | 100 | 100 | 200 | 200 | 400 | 400 | 100 | 200 | 100 | 100 | 200 | 200 | 100 | 200 | 200 |  | 1
30 | Bonus/COLA | 500 |  |  | 49000 | 0 | 11000 | 2000 | 1500 | 2500 | 1500 | 2500 | 3500 | 500 | 1000 | 1000 | 1000 | 1000 | 500 | 500 | 1000 | 1500 | 2000 | 500 | 500 | 500 | 1000 | 1000 | 2000 | 2000 | 500 | 1000 | 500 | 500 | 1000 | 1000 | 500 | 1000 | 1000 |  | 1
31 | Visas | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
32 | Passports $175*[(21New*1)] | 3675 |  |  | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1837.5 | 1837.5 |  | 1
33 | Immunizations/medical exams $400*(21New*1) | 8400 |  |  | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4200 |  | 1
34 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
35 | Truck Lease 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
36 | Fuel (Truck Lease 1) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
37 | Van Lease 1 | 1450 |  |  | 4350 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 |  | 1
38 | Fuel (Van Lease 2) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
39 | Van Lease 2 | 1450 |  |  | 4350 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 |  | 1
40 | Fuel (Van Lease 3) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
41 | Cell Phone | 400 |  |  | 1600 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 |  | 1
42 | Travel | 7726.4 | 32049.25 | 0 | 51087.15 | 7726.4 | 32049.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5655.75 | 5655.75 |  | 1
| Total ODC's |  |  |  | 132443.9682 | 11208.2182 | 48549.25 | 2400 | 1800 | 3000 | 1800 | 3000 | 4200 | 600 | 1200 | 1200 | 1200 | 1200 | 600 | 600 | 1200 | 1800 | 2400 | 600 | 600 | 600 | 1200 | 1200 | 2400 | 2400 | 600 | 1200 | 600 | 600 | 1200 | 1200 | 600 | 14743.25 | 14743.25 |  | 1
1
| Materials | [39 empty] | 1
43 | Tools & Supplies (Plug) | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 |  | 1
44 | Material #2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
45 | Material #3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
46 | Material #4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
47 | Material #5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Materials |  |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 |  | 1
1
| Subcontractors | [39 empty] | 1
48 | Subcontractor |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
49 | Consultant |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
50 | LocalNational |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
51 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
52 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
53 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
54 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
55 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Materials |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
133443.9682

## NTM-B BOE(Butmir+Min)
| PL: | P-13527
| RFP: | LJLA10021/LR-RBG-6000446638
| Offeror: | ManTech Telecommunications and Information Systems Corporation | [7 empty] | = Expected end state of a Svce
| Title: | NATO ITM-B
| Monthly FTE Hours | 220
| FTE Count by Scenario |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
| 45 |  |  |  | Most likely | bar: 3; 5; 8; 10 to 13; 15; 18 to 19; 21; 24; 27 to 28; 30 to 31; 34
| 13 |  |  |  | Minimum | bar: 6; 9; 16; 20; 22; 26; 33
| 10 |  |  |  | Butmir | bar: 3 to 4; 14; 19; 28
| WBS# |  |  |  | Contract Line | Phase I | Phase II | 1 | 2 | 3 | 4.1 | 4.2 | 4.3 | 5.1 | 5.2 | 5.3 | 5.4 | 5.5 | 6.1 | 6.2 | 7.1 | 7.2 | 7.3 | 8 | 9.1 | 19 | 10.1 | 10.2 | 10.3 | 10.4 | 11.1 | 11.2 | 12 | 13.1 | 13.2 | 14 | 15 | 16 | 16.2 |  | FILTER
[5 empty] | Service | Transition | Acceptance & Ramp-up | AIS | M131 | M131 | U131 | U131 | U131 | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | Minor Networks and Standalone W/S | VTC and IDNX Support | VTC and IDNX Support | Service desk and Network Monitoring | Service desk and Network Monitoring | Service desk and Network Monitoring | Crypto | Configuration Management | Configuration Management | Telephone Services | Telephone Services | Telephone Services | Telephone Services | Management, Admin and tech support for Leased lines | Management, Admin and tech support for Leased lines | RCC/LOT House Support | MTCT | MTCT | Stock Management and Property Accounting | Assistance to Presentations | Contract Management | Contract Management |  | 1
[5 empty] | Package Name | Transition | Acceptance & Ramp-up | PAIS/0 | PM131/0 | PM131/1 | PU131/1 | PU131/2 | PU131/3 | PMNSA/1 | PMNSA/2 | PMNSA/3 | PMNSA/4 | PMNSA/5 | PVTCI/0 | PVTCI/1 | PSDNM/1 | PSDNM/2 | PSDNM/3 | PCCM/0 | PCCM/1 | PCCM/2 | PTS/1 | PVS/2 | PVS/3 | PVS/4 | PLLS/1 | PLLS/2 | RCCLOT/0 | MTCT/1 | MTCT/2 | SMPA/1 | PRES/1 | PCON/1 | PCON/2
[5 empty] | Package Contents | Transition | Acceptance & Ramp-up | AIS (NS) Server Admin[1], Network and cable Infrastructure[2], Desktop Support[3] | M131 (MS) Server Admin, Network and cable Infrastructure, Desktop Support for =<150 Workstations | M131 (MS) Server Admin, Network and cable Infrastructure, Desktop Support for =>150 Workstations | U131 (Unclassified) Server Admin for Bldg 001, Network and cable Infrastructure, Desktop Support for <=100 Workstations | U131 (Unclassified) Server Admin for Camp Butmir and Bldg 001 only, Network and cable Infrastructure for <=200 Workstations | U131 (Unclassified) Server Admin for Camp Butmir and Bldg 001, Network and cable Infrastructure, Desktop Support for <=500 Workstations | Desktop Support for <= 10 standalone workstations or Laptops, support for <= 20 NROI (NATO Restricted over the Internet) Laptops | Administrative Support for all standalone Workstations or Laptops as detailed in Statement of Work | Support for ID Card Network, including all workstations and associated network devices and infrastructure | Support for DOCEX, including all workstations and associated network devices and infrastructure | Support for NDSS, including all workstations and associated network devices and infrastructure | Provision, maintenance, operation and administration of secure VTC Services and equipment | Crypto engineering, support and maintenance | Provision of Service Desk service during normal business hours 8:30 until 17:00 hrs Mon to Fri at Bldg 001 only | Provision of Service Desk service during normal business hours 8:30 until 17:00 hrs Mon to Fri at Bldg 001 and Camp Butmir | Provision of Service Desk service 0745 hrs until 1815 hrs Mon to Fri at Camp Butmir, Sat 07:45 until 12:00, and 0900 hrs until 1700 hrs Mon-Fri Bldg 001. Network Control Desk (NCD) manned 24/7 at Camp Butmir | Maintenance of Cryptographic accounts at Camp Butmir etc. | Configuration Management of CIS Facilities at Bldg 001 | Configuration Management of CIS Facilities at Camp Butmir, Bldg 001 and all locations within theatre | Maintenance and operation of PBX and associated lines and handsets in Bldg 001 and support of <= 100 telephone handsets | Attended service (duty hours), maintenance and operation of PBX and associated lines and handsets in Bldg 001 and support of <= 100 telephone handsets | Attended service (24/7), maintenance, and operation of PBX, SDH and all telephone assets as details in Annex F of Statement of Work and support of <= 750 telephone handsets | Attended service (24/7), maintenance, and operation of PBX, SDH and all telephone assets as details in Annex F of Statement of Work and support of <= 1500 telephone handsets | Management, administration and technical support of leased communication lines providing CIS facilities to Bldg 001 | Management, administration and technical support of leased communication lines providing CIS facilities to NHQ Sarajevo/EUFOR HQ in Camp Butmir and all locations with BiH as details in Statement of Work V1.0 | Hardware and software support for EUFOR RCC/LOT House workstations, this is limited to telephone assistance from Camp Butmir and to those workstations delivered to the Contractors ADP Maintenance workshop in Building 200, Camp Butmir | Provide one people to support the MTCT | Provide two person to support the MTCT | Provide Staff to operate the Depot and provide Stock Management and Property Accounting (Please see below Para. 4. Depot Workload Statistics) | Provide technical assistance to presentations and seminars | Management of O&M contract for services provided to NHQ Sa facilities in Bldg 001 | Management of O&M contract for services provided to NHQ Sarajevo/EUFOR HQ in Camp Butmir and all locations with BiH and facilities in Bldg 001
[5 empty] | SOW Paras | 5.1, 5.2, 5.3, 5.4, 5.6, 5.8, 5.11, 5.15, 5.16 5.17, 5.18, 5.20 | 5.1, 5.2, 5.3, 5.4, 5.6, 5.8, 5.11, 5.15, 5.16 5.17, 5.18, 5.20 | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.11, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.11, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1, 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16 | 3.1, 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16 | 3.26 | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.11, 3.14, 3.15, 3.16, | 3.1 3.2, 3.3, 3.4, 3.5, 3.7, 3.8, 3.9, 3.14, 3.15, 3.16, | 3.1 | 3.4 | 3.6 | 3.6 | 3.6 | 3.11 | 3.17 | 3.17 | 3.12 | 3.12 | 3.12 | 3.12 | 3.13 | 3.13 | 3.4, 3.5 | 3.27 | 3.27 | 3.28 | 3.29 | 3.18, 3.19, 3.20, 3.21 3.22, 3.23, 3.24, 3.25 | 3.18, 3.19, 3.20, 3.21 3.22, 3.23, 3.24, 3.25
| Brass Ring | MT Job Code | Current Lab Cats | Site | Total Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  | 1
[5 empty] | 0 | 2 weeks | 6 weeks | 4 | 3 | 5 | 3 | 5 | 7 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 4 | 1 | 1 | 1 | 2 | 2 | 4 | 4 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 2.1818 | 2.1818 |  | 0
| Government Site | [6 empty] | 880 | 660 | 1100 | 660 | 1100 | 1540 | 220 | 440 | 440 | 440 | 440 | 220 | 220 | 440 | 660 | 880 | 220 | 220 | 220 | 440 | 440 | 880 | 880 | 220 | 440 | 220 | 220 | 440 | 440 | 220 | 480 | 480 |  | 1
1 | Project Manager | Vanleishout,Ronald W | ManTech | Govt | 220 | 100 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 3300 | 1
2 | Project Manager, Deputy | Capurro,Jorge L | ManTech | Govt | 220 | 100 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 2420 | 1
3 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 3300 | 0 | 220 | 0 | 0 | 220 | 0 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 0 | 220 | 0 | 0 | 1100 | 1
4 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 880 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 1100 | 1
5 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2420 | 1
6 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540 | 1
7 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 0
8 | Desktop Support/ADPE Technician | LaSala,Laura J. | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0
9 | Help Desk Specialist | Allison,James S | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0
10 | Help Desk Specialist | Allison,James S | ManTech | Govt | 1320 | 0 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
11 | Help Desk Specialist, Staff | Allison,James S | ManTech | Govt | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 1
12 | Help Desk Specialist | Allison,James S | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0
13 | Help Desk Specialist | Allison,James S | ManTech | Govt | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0
14 | NDSS - NTM-B | Hughes,Christopher J | ManTech | Govt | 880 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2860 | 1
15 | NDSS - Logistician Tech | Hughes,Christopher J | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 0 | 0 | 660 | 1
16 | Network Engineer | Butler,David | ManTech | Govt | 1100 | 100 | 220 | 440 | 220 | 440 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
17 | Systems Administrator | Hawi,Jason N | ManTech | Govt | 1320 | 100 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
18 | Systems Administrator | Hawi,Jason N | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
19 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 1540 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
20 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 1540 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 220 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1
21 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 1100 | 0 | 220 | 0 | 0 | 0 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4400 | 1
22 | Telecommunications Analyst, Staff | Harris,Troy N | ManTech | Govt | 440 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 1
23 | Switchboard Operator A | Ilarraza,Margaret R | LocalNational | Govt_Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Switchboard Operator B | Ilarraza,Margaret R | LocalNational | Govt_Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Site Manager/Crypto Custodian | Boston, Randall | ManTech | Govt | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
26 | Configuration Manager | Hawi,Jason N | ManTech | Govt | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
27 | Project Control Analyst | Wendy Bibb | ManTech | Contr | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 |  | 1
| TOTAL LABOR |  |  |  | 16320 | 400 | 4840 | 880 | 660 | 1100 | 660 | 1100 | 1540 | 220 | 440 | 440 | 440 | 440 | 220 | 220 | 440 | 660 | 880 | 220 | 220 | 220 | 440 | 440 | 880 | 880 | 220 | 440 | 220 | 220 | 440 | 440 | 220 | 480 | 480 |  | 1
1
| Other Direct Costs | [39 empty] | 1
28 | DBA Insurance | 2% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
29 | War Risk Insurance | 100 |  |  | 9981.8182 | 181.8182 | 2200 | 400 | 300 | 500 | 300 | 500 | 700 | 100 | 200 | 200 | 200 | 200 | 100 | 100 | 200 | 300 | 400 | 100 | 100 | 100 | 200 | 200 | 400 | 400 | 100 | 200 | 100 | 100 | 200 | 200 | 100 | 200 | 200 |  | 1
30 | Bonus/COLA | 500 |  |  | 49000 | 0 | 11000 | 2000 | 1500 | 2500 | 1500 | 2500 | 3500 | 500 | 1000 | 1000 | 1000 | 1000 | 500 | 500 | 1000 | 1500 | 2000 | 500 | 500 | 500 | 1000 | 1000 | 2000 | 2000 | 500 | 1000 | 500 | 500 | 1000 | 1000 | 500 | 1000 | 1000 |  | 1
31 | Visas | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
32 | Passports $175*[(21New*1)] | 3675 |  |  | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1837.5 | 1837.5 |  | 1
33 | Immunizations/medical exams $400*(21New*1) | 8400 |  |  | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4200 |  | 1
34 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
35 | Truck Lease 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
36 | Fuel (Truck Lease 1) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
37 | Van Lease 1 | 1450 |  |  | 4350 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 |  | 1
38 | Fuel (Van Lease 2) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
39 | Van Lease 2 | 1450 |  |  | 4350 | 1450 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 |  | 1
40 | Fuel (Van Lease 3) | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
41 | Cell Phone | 400 |  |  | 1600 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 |  | 1
42 | Travel | 7726.4 | 32049.25 | 0 | 51087.15 | 7726.4 | 32049.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5655.75 | 5655.75 |  | 1
| Total ODC's |  |  |  | 132443.9682 | 11208.2182 | 48549.25 | 2400 | 1800 | 3000 | 1800 | 3000 | 4200 | 600 | 1200 | 1200 | 1200 | 1200 | 600 | 600 | 1200 | 1800 | 2400 | 600 | 600 | 600 | 1200 | 1200 | 2400 | 2400 | 600 | 1200 | 600 | 600 | 1200 | 1200 | 600 | 14743.25 | 14743.25 |  | 1
1
| Materials | [39 empty] | 1
43 | Tools & Supplies (Plug) | 1000 |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 |  | 1
44 | Material #2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
45 | Material #3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
46 | Material #4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
47 | Material #5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Materials |  |  |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 |  | 1
1
| Subcontractors | [39 empty] | 1
48 | Subcontractor |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
49 | Consultant |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
50 | LocalNational |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
51 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
52 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
53 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
54 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
55 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Materials |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
133443.9682