Portfolio Review Meeting
May 18, 2015

Seed Grants
Global Drug Policy Program

Akos Lipcsey

- Summary of this Portfolio Analysis

This is an analysis of a group of seed grants supported by the Global Drug Policy program. The objective of the grants is to build the capacity of fledging drug policy organizations and expand the number and variety of voices that engage in drug policy debates.

Our Ambitions:  This portfolio is aimed at bringing new voices to drug policy reform debates in key countries through its support of NGOs and international organizations, including a few that are not exclusively focused on drug policy. The portfolio also intends to strengthen and sharpen existing reform movements, and represents the Global Drug Policy Program (GDPP) grantees working at a national level. We have also leveraged seed grants in order to capitalize on political opportunities when potentially significant individuals engaged in the reform movement. Additionally, a few seed grants enabled small and rather isolated grantees to join a large international campaign. Other grants provided a tool for networking and created opportunities for GDPP to meet new groups aligned with our objectives.

Our Place: Recognizing that these young initiatives are more successful if they receive external mentoring and guidance, GDPP participated in the planning and execution of the projects. This support ranged from providing technical assistance, contributing to the design of advocacy strategies, creating networking opportunities, and introducing groups to other Open Society Foundations (OSF) programs. Despite our best intentions, our contribution to some fledging initiatives was not always helpful in expanding the potential of their projects.

Our Work: Seed grants are the riskiest category of our grant-making because they involve grants to organizations that are new to us and/or operating in challenging or uncertain environments. Yet, we observe that more than 50% of the grants within this portfolio were able to accomplish the project goals set out in the proposal.  Others, while not explicitly leading to successful projects, were able to create benefits to our program and the drug policy movement beyond the project terms.  While some grantees are improving their capacity in strengthening their organizational health or advocacy strategies, a few have already had a significant impact on national politics. We hope to build on our experience and continue our work in Asia and Africa where our collaborating partners are still few in number.

- Definition of the Portfolio

Typically, a seed grant provides funds for initiating a new project or a new organization.  These funds are provided to finance the initial stages of a new venture that may not otherwise receive funding. Seed grants are sometimes also known as ‘start-up money.’

In all of the cases highlighted by this portfolio, the common characteristics of the seed grants are that they are small in size (mostly under $25,000); short term (usually up to 1 year); and represent a high degree of risk and uncertainty with respect to accomplishment of project goals. As outlined in Table 1, GDPP has awarded grants in this area since its establishment in 2008. GDPP has issued seed grants to approximately 10 grantees per year; and all of these were first-time recipients of our support. The average annual allocation of funds for seed grants has been less than 5 percent of GDPP’s annual budget. Typically, there is no co-funding involved due to the high-risk nature of the grants.

This review focuses on seed grants as a cross-cutting tool across our strategy. The opportunities that are surfaced by seed grants ideally feed into our strategy as we seek collaboration with partners for the longer term.

Assumptions, methods and activities described in this review developed over the years and the portfolio was defined and assumed a distinct part of the program’s work only recently.

| GRANTEE ORGANIZATION | PROJECT TITLE | GDPP’S APPROACH | GRANT ID | GRANT TERM | GRANT AMOUNT | PROJECT DESCRIPTION |
| --- | --- | --- | --- | --- | --- | --- |
| Espolea A.C | Campaign: Do Not Hallucinate, Find Out | 1. Developing an all-new organization with specific focus on drug policy reform | OR2009-15807 | 8 mo. | $10,000 | Provide information to the Mexican youth of what their drug policy entails in particular in relation to sexuality, HIV and human rights. Specific goals of the project were to hold discussion forums on drug policy and what harm reduction means in Mexico, in particular for youth, to promote harm reduction programs and the proposals that emerge from the discussion generated, to observe and follow up on federal addiction centers Centros Nueva Vida and to study the relationship between HIV and non-injecting drug use among youth in particular. |
| Canadian Drug Policy Coalition (CDPC) via the Centre for Addiction Research of BC, University of Victoria | Founding Meeting of the Canadian Drug Policy Consortium | 1. Developing an all-new organization with specific focus on drug policy reform | OR2009-15172 | 2 mo. | $24,000 | Facilitate a meeting on behalf of the emerging Canadian Drug Policy Consortium (CDPC) that would recommend a structure and course of action for the organization over the near term. The meeting took place in late May 2009, in Vancouver, and brought together approximately 30 individuals with expertise in civil society organization. |
| Polish Drug Policy Network (PDPN) via Association JUMP’93 | Ombudsman for Rights of Addicted People | 1. Developing an all-new organization with specific focus on drug policy reform | OR2009-15233 | 12 mo. | $25,000 | By hosting the newly formed Polish Drug Policy Network, the project allowed for considerable improvement of efforts focused on protecting rights of people who use drugs, with rational and evidence based approaches to the problems of drug use and drug addiction. In particular, the project included the monitoring of violations of rights of drug users and supported prosecution in cases of rights violations in prisons, therapeutic programs, welfare institutions, as well as by police. |
| Diogenis Association | Drug Policy Dialogue in Southeast Europe | 1. Developing an all-new organization with specific focus on drug policy reform | OR2011-19610 | 5 mo. | $25,000 | The project supported the establishment of the Drug Policy Network in Southeast Europe. Agreements made at the founding meeting in Thessaloniki on 3-6 March, 2011 were communicated to the members to form an action plan for the following period (April-May). Diogenis would identify and work on recruiting new members to the network from the region. The grant also provided support towards Diogenis’ office requirements and the setting up of a professional website. |
| The Andrey Rylkov Foundation for Health and Social Justice (ARF) | Drugs as a Tool of Political Repression in Russia | 2. Contributing to the agenda of an existing organization | OR2011-20336 | 8 mo. | $25,000 | The project was aimed at raising visibility and stirring public debate on the problem of the use of the topic of drugs as a tool for political repression in Russia with focus on demands for improved access to freedom of speech and fair trial. The project aimed to achieve this by involving social art activists, media, and human rights organizations into the drug policy debate in Russia; and by generating artwork that can be used during the action as well as further on in drug policy reform activities. |
| International Community of Women Living with HIV/AIDS – Asia Pacific (ICW) | Strengthening the voice of HIV positive women using drugs in South Asia | 2. Contributing to the agenda of an existing organization | OR2010-16765 | 12 mo. | $23,000 | The project was aimed at developing an advocacy plan by and for HIV positive women who use drugs to come up with a comprehensive strategic and planning exercise leading to the implementation of a coherent program and the creation of a think tank by and for women living with HIV/AIDS, and drug users in South Asia to critically review current policies and programs and support advocacy efforts to be more effective in involving HIV positive women into drug policy discussions. |
| German Hemp Association | Disclose discrimination against cannabis consumers in Germany | 2. Contributing to the agenda of an existing organization | IN2010-15688 | 6 mo. | $23,270 | The objective of the project was to highlight discrimination against cannabis users and the multiple harms of prohibitionist policies in Germany. The German Hemp association documented the disproportionate treatment of cannabis users in a series of test cases and provided legal assistance for people who have received prison sentences, large fines, or lost their drivers license (thought they were not driving under the influence of any substance) and, in some cases, their jobs. |
| Polish Academy of Sciences, Institute of Philosophy and Sociology | Pilot Postgraduate Teaching Program on Drug Policy | 3. Contributing to a meeting or to networking | OR2010-18759 | 25 mo. (originally 10) | $19,000 ($4,358 refunded) | The project supported the launch of a semester-long seminar program for doctoral students as a pilot for the development of teaching modules on Drugs Policy which could be offered as a one-year postgraduate degree program taught in English and targeted at professionals working in this policy area. Doctoral students attending the seminar were drawn from a student body from 20 different countries (US, Europe -particularly Central and Eastern, Central Asia). |
| Gajna Law Reform Coalition Limited (GLRC) | Ganja Law Reform in Jamaica | 3. Contributing to a meeting or to networking | OR2012-21965 | 24 mo. | $25,000 | GLRC drafted a policy paper on ganja reform to educate the wider public in Jamaica on the issue of drug policy and law reform. |
| Comitato Promotore Referendum (project transferred to Luca Coscioni Association - LCA) | The legalization of Drugs Explained to Adults | 4.Taking advantage of a political opportunity | OR2013-06126 | 4 mo. | $21,000 | The project produced a video to promote reforms in the field of drug policy in Italy using common-sense arguments to mobilize viewers in support of a campaign that aimed at presenting a draft bill to legalize marijuana. The video summed up the current drug policy situation in Italy and urged viewers to support the need for change. |
| All Party Parliamentary Group for Drug Policy Reform (APPG) via International Drug Policy Consortium | European Initiative for Drug Policy Reform and UK political campaign | 4.Taking advantage of a political opportunity | OR2013-05367 | 7 mo. | $24,900 | APPG held an international conference in January 2014, involving ministers/drug policy directors from about 17 countries in Europe to bring together representatives of reform-minded European countries to strategize on how best to mobilize their voice and clout in international drug policy debates. APPG would also seek to advance UK drug policy reform through engaging with advocates and decision-makers nationally. |
| Carusel Association | ”Let’s Talk About Drugs” day of action | 5. Enabling collaboration on international campaigns | OR2014-14745 | 5.5 mo. | $10,000 | As part of the June 26 international campaign for the World Drug Day in 2014, Carusel translated the campaign materials into Romanian and engaged a local graphic designer and comic artist to draw images drawing attention to the need of reforming the law. These were put on display in 10 of Bucharest’s pubs and distributed in the center of the city. A photo exhibition was also organized where children aged 10-15 introduced the viewers to their neighborhood drawing attention to drug use in public places. |
| Coalition H3 | ”Let’s Talk About Drugs” day of action | 5. Enabling collaboration on international campaigns | OR2014-14773 | 2 mo. | $9,998 | As part of the June 26 international campaign for the World Drug Day in 2014, Coalition H3 promoted debate by convening a National Symposium on Drug Policy Reform. The national debate and day of action were promoted in television, newspaper ads, and social media. On June 26 peaceful marches and demonstrations took place in Kathmandu and five other major cities in the country. The organization issued a press release prior to the events to encourage public engagement in the day of action. They also produced a position paper to promote awareness among key stakeholders and stress the need for drug policy reform that protects human rights and promotes public health. |
| Accion Tecnica Social (ATS) | ”Let’s Talk About Drugs” day of action | 5. Enabling collaboration on international campaigns | OR2014-15012 | 1 mo. | $10,000 | As part of the June 26 international campaign for the World Drug Day in 2014, ATS called on citizens to create 30 second videos advocating for the decriminalization of drug use and why the war on drugs should end. Another activity included a series of portraits in the streets of Bogota, where people were asked to take a picture holding the “Support, Don’t Punish” sign. With support from the Mayor of Bogota and other elected officials from Colombia’s capital, they presented evidence of successful drug policies that respect human rights, public health, and civil liberties. |
| Tanzanian People who Use Drugs (TANPUD) via MUKIKUTE | ”Let’s Talk About Drugs” day of action | 5. Enabling collaboration on international campaigns | OR2014-15062 | 1 mo. | $8,408 | As part of the June 26 international campaign for the World Drug Day in 2014 TANPUD set up a booth at the National Anti-drugs Symposium to raise awareness among community leaders and policymakers about harms associated with drug use and drug policy in Tanzania. In addition, the grant supported the airing of a video completed earlier by TANPUD members in collaboration with VAMA, a local media production NGO. The video counters negative stereotypes about people who use drugs, and was broadcast on national TV during prime time. The airtime totaled 15 minutes over 5 TV channels. |

Table 1 – List of Grants in this Portfolio. Seed grants made by GDPP between 2009 and 2014.

- GDPP’s Approach

This review identifies five broad ambitions of our seed grants:

  - Developing an all-new organization with specific focus on drug policy reform

  - Contributing to the agenda of an existing organization whose focus is not specifically drug policy reform

  - Contributing to a meeting or conference with the aim of networking with other actors

  - Taking advantage of a political opportunity

  - Enabling collaboration on international campaigns

OSF is one of very few donors that explicitly fund drug policy reform work. Many young organizations are aware of this fact and come to us for support. Since 2008, GDPP has funded new organizations that show promise to grow and strengthen the reform movement. We have also supported new drug policy initiatives within organizations that work on health, human rights, criminal justice, and development because they can offer a valuable new perspective and bring new sectors to the reform discussion.

Some seed grants made by GDPP contributed to the convening of meetings, forums, seminars and conferences with the ambition of discovering new players in the field and establishing connections. Not only were the grants dispersed geographically, agendas of meetings also varied. When deciding to support these meetings, we placed particular attention on their potential participants; thus providing GDPP staff opportunities to participate and build connections.

In other cases, when a political opportunity presented itself, GDPP engaged by offering an exploratory grant. These cases involve individuals with some political visibility and an interest in engaging in drug policy reform.  They usually have a degree of media access and initiate debates with a significant audience. The program actively looked for such emerging opportunities, but given their nature, these rarely present themselves without our encouragement. We have played a role in initiating projects such as the All Party Parliamentary Group for Drug Policy Reform in the UK. This approach does not contribute directly to the strengthening of organizations, but rather capitalizes on our connections with these actors in the field.

GDPP has used the seed grant mechanism recently to create an opportunity for somewhat isolated and small organizations to join the advocacy campaigns of other large institutions already in the reform movement. Smaller organizations tend to have a limited ability to contribute to the international reform movement on their own, lacking the technical, human, and financial resources. However, through organized support joining ready-made international campaigns, they form important linkages with a larger global movement creating synergy in reform. The projects aimed at benefiting the grantees through international recognition for their participation in a large campaign as well as through the technical assistance they received during the implementation of the objectives.

The time span of this portfolio is seven years. The mission and objectives of grants funded in this portfolio range across all categories of work within our strategy.

- Changes in Context: Why this Portfolio Review is Timely

Many years ago, when GDPP started out as a new program, the field of drug policy reform was limited to a few large organizations. In our early years, the seed grants were an important mechanism to bring new voices to the table and strengthen the reform movement in general.

Recently, this has changed in some parts of the world. We see many active organizations working on policy reform in Latin America, North America, and Europe and competition for grants has increased. In these regions the field may require less seed funding to foster new players. However, in Asia and Africa, where the reform movement has progressed much more slowly, there are still strong reasons to continue with seed funding. With the changing climate in drug policy reform in several regions around the world, it is a timely opportunity to review our long-standing ambitions and make optimizations or establish new areas of focus.

Another consideration is the significant amount of staff time required to administer 5% of our budget, as discussed in more detail later in this review. Based on the scarcity of our human resources, it is important to find the most efficient approaches to determine the best way to use our time.

- The Constellation of GDPP Seed Grants: Looking at the Whole Picture

For this portfolio review of seed grants, we want to compare our goals for the projects against actual outcomes. The critical analysis below will demonstrate our rationale for support as well as the experience and lessons learned. The 15 grants that we look at under this portfolio (Table 1) are engaged in a diversity of strategies and are evenly disbursed geographically.

- The metrics of seed grants in GDPP’s arsenal

Relying on our initial assumptions and our perception of the field, the grants in this portfolio were made with a degree of uncertainty and risk. The unknown elements for us ranged from organizational performance and commitment, managerial and leadership talent and skills, environmental risk to cultural factors. Additionally, there is the unknown factor of sustainability in the longer term. How long should we support organizations that seem to struggle with sustainability if they appear to be capable of achieving change?

Projects that seem promising are in many cases followed by a more substantial grant in size that enables meaningful activities for reform. However, when deciding to fund projects of applicants we have not worked with before, grant proposals have been checked against the criteria below:

1) Does the applicant have an effective record in advocacy and campaigning?

2) Does the project open up new geographical areas?

3) Does it support the growth of a new organization (or new to drug policy)?

4) Does it support a promising project that might change policy?

5) Will it operate politically / strategically in a way that benefits our program?

or any combination of these.

Narrowing it down, success would mean we changed politics. Drug policy reform has taken place in form of incremental steps so far in most parts of the planet and so we have to interpret success more broadly. Our seed grants are part of this incremental process and we measure results along the points established above. Some grantees tend to show better potential along more of these lines, others along fewer. The question for us is which are the organizations with better potential to take off?

Of the 15 grantees in this portfolio, we continue to be partners with up to 10 grantees from the list on Table 1. This means the majority of grantees in this review still show potential from several aspects. This percentage makes us bold in this part of our work. If a significant majority of the riskiest category of our grant making shows such potential, we want to consider awarding more of these.

- Geographic Distribution

Grantees in this portfolio are spread across 5 continents. We recognize that there is an uneven starting ground for many of these players that comes from the environment they are located in. The lack of funding in drug policy in Africa and Asia left our grantees particularly disadvantaged in these regions and it is these very regions where we are yet to have formed a strong alliance with a partner highly capable of inducing reform. We have also observed a tendency that fledging organizations, especially in the non-Western world, have stronger fundraising plans targeting national foundations and state funds, but seemingly struggle to step to the next level and raise funds from international donors and bi/multilateral funds.

Projects with more significant achievements are concentrated in Europe and North America. While our risk in relation to these projects was lower, these grantees had access to a variety of donors that their counterparts elsewhere did not.

The Canadian Drug Policy Coalition, Espolea, the All Party Parliamentary Group for Drug Policy Reform, Diogenis, and the International Community of Women Living with HIV/AIDS – Asia Pacific are grantees operating with a regional focus. Other groups in this portfolio operate exclusively in their home country.

- Analysis of Seed Grants Based on GDPP’s Approaches

- Developing an all-new organization with specific focus on drug policy reform

Grants under this category are intended to support the start-up of new organizations with a specific focus on drug policy reform. We funded new organizations with the intention of filling a gap in the movement or in a particular geography and we hoped that the seed funding would allow them to build their capacity and sharpen their skillset in national level advocacy. OSF’s support on medium and long term is aimed at enabling them to become credible advocates capable of creating breakthrough potential for reform. As part of our strategic goal of promoting reform initiatives in key countries, and enabling national leaders to advocate publicly for progressive change we supported the establishment of these organizations to grow the capacity of civil society organizations in countries where it was lacking or non-existent.

Working with Espolea was strategic; not only because of their specific agenda on drug policy, but also that they are a youth-led organization representing the interest of the youth, which overlaps with our other strategic goal of bringing new voices to drug policy reform debates. While the grants to Polish Drug Policy Network, Diogenis and Canadian Drug Policy Coalition were instrumental in supporting the establishment of the NGOs, in Espolea’s case it was merely a seed grant to support their work, build their capacity and explore possibilities of future cooperation.

The pace of institutional development and move towards financial independence of these organizations was slower than we anticipated. Reasons for slow institutional development might be due to multiple factors, from leadership focusing on project outcomes as opposed to organizational capacity, limited fundraising efforts or attempts to diversify funding streams to the lack of donors in the field in the context of geographical location. After providing continuous funding for several years, we are still above the 1/3rd threshold with some organizations in this review as they continue to be quite reliant on our support (CDPC).

Espolea has succeeded in providing training to dozens of new youth advocates about drug policy debates in both national and international policy discussions. It has grown in staff size and in capacity to carry out research on their own (both in English and Spanish). They have added new overlapping programs focusing on HIV and gender (supported by UNAIDS and UNFPA). Despite these positive developments, we have been concerned about the leadership style of their Executive Director (further details in section F).

Diogenis has become the main coordinator of the South East European drug policy network. Since their establishment in 2010 they have facilitated various events for members of the network, but their informal dialogues have been particularly successful based on feedback we received. These were expert seminars with policy makers, practitioners and NGOs to exchange ideas and proposals for regional reform initiatives. Diogenis was recently awarded a grant from the European Commission in the amount of 150,000 EUR that greatly contributed to their organizational stability and holds new opportunities for the entire network. We are pleased to see them progress with their institutional development and efforts ensuring sustainability. CDPC, PDPN and Diogenis remain our grantees, with funding at or slightly above 1/3rd of their budget.

- Contributing to the agenda of an existing organization whose focus is not specifically drug policy reform

Whenever we saw the opportunity to collaborate with a local actor working on issues related to drug policy reform, we used the mechanism of a seed grant to enable them to consider including drug policy in their agenda. In other words the aim was to attract the engagement of other sectors in drug policy reform to have the voices of advocates as diverse and widespread as possible. Seed funding would allow us to get to know them better and see if we might collaborate successfully. Most of these grants were made in regions where the potential for reform was slim, however we felt it was important to have the voice of reformists represented – to the extent possible. We thought that providing a modest amount of support to these actors would maintain a minimum level of engagement and might reveal some cracks in the oppressive prohibitionist systems.

Supporting the International Community of Women Living with HIV/AIDS – Asia Pacific (ICW) seemed strategic, not only because of their location, but also because the group had extensive experience in mobilizing women’s rights groups and HIV communities. Completing the grant term, our experience with ICW was mixed. We had concerns about their productivity, outreach, and the lack of co-funding. We also had the impression that they are not as successful in advocating for drug policy reform as we were hoping they would be. We planned on continuing modest support to them at a level of under $25,000; however serious cash-flow problems emerged and the leadership expressed their inability to sustain the organization. Our efforts for supporting them were also complicated by the regulations of the Ministry of Home affairs in India. A government authorization had to be obtained each time a transfer was made. We stopped working with ICW in 2012 when they announced that they were closing their office.

Although an advocacy organization, the German Hemp Association had an unusual structure under German law, where an individual – the founder – held the legal personality and ownership of the organization as a sort of private enterprise. GDPP had consultations with the Executive Director and made it clear that our support was on the assumption that they would develop themselves institutionally to form a structure acceptable by international standards with built-in checks and balances and governance. With encouragement from our Advisory Board, we provided modest support, even though Germany has not been among our priority countries. Our impression was that they used our funds to develop their own agenda without significant alignment with our agreement. After receiving two OSF grants, we realized they would not change the structure of the organization.  In light of these developments, we could not continue collaborating with this organization on reform in Germany.

The Andrey Rylkov Foundation has a strong and passionate leadership and we feel confident that our modest support to their policy work enables them to continue educating public opinion on the drug problem faced by Russia, highlighting victims of political repression, and drawing attention to repressive police methods used against activists and drug users. ARF works to promote public debate about these issues but their efforts saw limited success due to the increasingly challenging context in which they operate. We appreciate that the current organizational structure keeps them dynamic, flexible, and quick to change, which are essential qualities to be able to function in that environment. Achieving any notable reform appears to be impossible in Russia at this time, and we are concerned that government agencies might attempt legal actions against the organization and/or its staff based on their pursuit of politically unpopular subjects.

    - Contributing to a meeting or conference with the aim of networking with other actors

With the grant to the Polish Academy of Sciences we aimed to establish an education program in Poland similar to the one at the Central European University (CEU). As was the case with the CEU, GDPP was deeply involved in planning, with the ultimate long term objective of building drug policy into the academic curricula of the host institution. Unfortunately, the drug policy course didn’t generate the expected level of interest from the staff. We learned that both the students and the faculty were highly uncomfortable with considering alternatives to the current drugs regime and that the level of controversy this inspired was not helpful in moving the discussion forward.  GDPP’s lesson was that transferring a successful program from one context to another may not guarantee the same level of success and recognition. In order to succeed, the course should have been tailored move carefully to the Polish context, which also would have meant including multiple local stakeholders that were not appealing partners for us.

Funding the Ganja Law Reform Coalition was our vehicle to establish connections and network with civil society organizations in Jamaica. OSF’s first grant to the Ganja Law Reform Coalition was intended to support the drafting of a policy paper on marijuana, based on which they could advocate for change both publically, as well as with politicians. In 2013 they applied for a follow-up grant that would enable their work to continue by hosting a conference on cannabis reform for the region. While our seed grant successfully surfaced new connections and opportunities in the region, we had to end our connection with the grantee. The first grant was completed according to our expectations, but as we started working on the implementation of the second phase which was the national conference, we experienced internal conflicts in the leadership of the grantee and other issues that affected the leadership of the organization. We immediately took steps to cancel our grant and requested the return of the unspent amount. Despite this setback, it was worthwhile to fund GLRC at this level as our initial connection with them has led us to new connections with Jamaican MPs and academics that we continue to collaborate with up until today.

    - Taking advantage of a political opportunity

There are rare opportunities when people of stature show interest and willingness to advocate in favor of drug policy reform. Given their public position, their actions and statements are followed with significant interest. We have such connections among our Advisory Board as well as a number of our grantees. We recognize that these grants are unusual in nature as they are aimed at supporting the activities of high profile individuals, rather than developing an organization. Active politicians rarely speak out on drug policy reform due to the highly controversial nature of the subject, but when some of them do, it can be a very powerful tool in quickly gaining the attention of large audiences and generating debate. Supporting the voices of engaged politicians, these grants are meant to mobilize the public at large. At the same time, the All Party Parliamentary Group, under the leadership of Baroness Molly Meacher, seemed a suitable mechanism to generate high-level discussions among politicians and further the debate of viable policy alternatives. In Italy, our long-time partner, Marco Perduca, a former senator working initially within the Comitato Promotore Referendum (project transferred to Luca Coscioni Association - LCA), was engaged in multiple campaigns aimed at the public to rally support for drug policy reform including one targeted at nationwide acceptance of medical cannabis.

Both of these projects contributed positively to European drug policy reform discussions. Encouraging a group of parliamentarians to speak out on drug policy reform and advocate for change at such a high level was an important milestone for GDPP. The seed grant mechanism was a great way to get to know each other and explore the potential for scaling up our support. It is strategic to have the voices of a few reform minded public figures strengthened while being aware of how they fit into our portfolio of grants and keeping our support at a modest level. We were aware that these seed grants were not meant to build the institutional capacity of these organizations, but were primarily mechanisms for engaging with particular individuals who we think are effective advocates. It remains a question whether supporting these initiatives on the longer term would contribute effectively to strengthening institutions or would continue to be purely a conduit for OSF to support these key actors. For now, the availability of our funding seems to be playing a critical role in the existence of these projects.

  - Enabling collaboration on international campaigns

In 2014, GDPP applied to the reserve fund with a proposal for a day of action, to be organized on June 26th, World Drug Day, to call for alternative drug policies. The International Drug Policy Consortium (IDPC) mobilized its network and numerous groups became involved and applied for our support. $150,000 was made available to us from the reserve fund to support particular actions. We hoped paid media would boost turnout, increase media coverage, and broaden participation. Time was a factor. We only had four weeks to identify strong actions and provide technical support (planning, press, etc.). In addition to financial support, GDPP worked with partner organizations to write and disseminate press releases and media outreach. Staff worked with a number of outlets and was able to book interviews and in-studio appearances for several grant recipients in advance of June 26.

The efforts resulted in hundreds of stories in The Guardian, BBC, The Telegraph, Al Jazeera, and many news sources. In addition to earned media, the funds were critical to engaging the public through paid media.

In Nepal, for instance, Coalition H3 issued a press release and organized a peaceful march on June 26th in Kathmandu and other major cities. Street demonstrations were also held in Dar es Salaam, Tanzania, where our partner, Tanzanian People who Use Drugs, prepared video spots that were aired on several national TV channels challenging negative stereotypes around drug users. Accion Tecnica Social (ATS) in Bogota also used video spots as a tool to reach a broader audience. On June 26th, with support from the city government and the presence of elected officials from Colombia’s capital, department of health, and office of security, they presented evidence of successful drug policies that respect human rights, public health, and civil liberties. The event was followed by a press conference and the day culminated with a cultural event in the center of the city. Carusel, in collaboration with a local comic artist, presented visual messages in 10 of Bucharest’s busiest pubs. These remained on display after the event. A public exhibition was also organized in which children, aged 10-15, presented their community with the use of photographs.

In addition to these grantees, several of the others in this portfolio review also participated in the campaign, including the Polish Drug Policy Network, Espolea, and the Luca Coscioni Association. In Poland, the Polish Drug Policy Network placed subway ads throughout Warsaw calling for an end to the criminalization of minor offenses. In Mexico City, Espolea developed compelling infographics to highlight the damage of the war on drugs. Luca Coscioni Association in Italy launched an e-petition to encourage national debate utilizing the digital platform of Change.org.

The particular materials used varied. In some cases, groups adopted the advertisements developed by the Global Commission quite faithfully (Italy, Mexico) that GDPP offered as a tool. In other cases, organizations preferred to create original materials that they felt would be more context-appropriate. Ultimately, the slogan, “Support. Don’t Punish.,” became more resonant and we helped to facilitate its use. We also coordinated social media activities with each participating group and, despite the World Cup, which made it extremely competitive for news, the hashtag #SupportDontPunish was a trending topic around the world.

While successful in the context of the campaign and in generating international attention, with the small contributions that were largely towards presence in the media and visibility on other platforms, these grants may not have contributed significantly to the strengthening of these organizations. We remain in consultations with several of these until today about more substantial ways of collaboration on national reform.

- The Role of GDPP/OSF and Other Actors in these Developments and the Significance of these Developments

As this account suggests, the role of GDPP and OSF partner programs is critical because there are few other actors supporting drug policy reform, particularly organizations endeavoring to affect decisions on a regional level.  We would summarize the significance of these developments and of GDPP’s role as follows:

Our grantees within this portfolio are working to identify potential opportunities to advocate for reforms nationally and within their domestic environment. In Poland, the presence of GDPP enabled local NGOs to benefit from frequent consultations and, as a result, sharpen their strategies. This is a country where possession of even a small amount of an illegal substance for personal consumption initiated criminal proceedings and a trial. The Polish Drug Policy Network and others inspired policy change. The process required relentless consultations and campaigning that raised public awareness. The result was an amendment to the national drug law that gives a degree of freedom to judges to divert drug users to treatment instead of prosecution.

A common aspect of these seed grants is the increased engagement required from GDPP staff. Organizations with a national focus usually have access to high-ranking officials domestically, but lack international connections that our program can provide. An example of this is our collaboration with Marco Perduca in Italy, via the Luca Coscioni Association. A former senator (from 2008 to 2013), currently a member of the Foreign Affairs and Justice committees, and secretary of the Senate's Special Commission on Human Rights, he has the authority to engage with UN missions with a credible voice. However, it was only after personal consultations with GDPP in Budapest, that he started this work. Marco Perduca is our ally, an active promoter of human rights and international criminal law. With our support, he is currently engaged in efforts aimed at the greater acceptance of medical cannabis nationwide in addition to his ongoing work on reforming drug policy in Italy.

Our collaboration with Espolea initially showed great promise. They appeared to be a capable representative of the voice of youth at international discussions as their iconic and young Executive Director, Aram Barra, networked very intensively with all the significant actors in the field. Espolea quickly became an organization enjoying joint support from the Latin America Program, the Youth Initiative, and GDPP. We continued to monitor the progress of the organization closely and discovered that the Executive Director has a tendency to put his personal development agenda ahead of the development of the organization as a whole. We have been concerned about this approach as it can hinder the growth of the organization as well as prevent other talents in the Espolea from thriving. In fact, Aram quickly outgrew Espolea and now is working with a prestigious drug policy institution in the UK. The person left in charge of the organization is Ceci Garcia, and we have been informed as we were developing this review, that the organization is to close down this year. This immediately raised several questions in us regarding what could we have done differently to avoid this. At some point most organizations are founder-driven and Aram’s dominant role itself was not a strong reason that would have raised flags for us. Eligibility assessments now provide a tool for keeping track of institutional developments and lead us to think more about our role with grantee organizations.

GDPP’s engagement and strategic advice was important for these organizations, but we recognized the need to create peer-to-peer learning opportunities as well. In order to promote networking and the exchange of ideas, GDPP provides scholarships to representatives of seed grantees to attend international conferences and present current issues and challenges that they are working on. Feedback about these opportunities has been positive as they created a setting in which grantees could identify their role and function within the context of an international movement.

- Lessons Learned and Conclusions

The following section highlights some examples of advances and setbacks/challenges that our program has identified.

- Seed grants without close engagement from the program, for the most part, failed to meet expectations. These grantees are organizations that require frequent consultation and which actively seek GDPP’s advice.

- We found that establishing personal contact with an OSF staff member was important for relationship building. A supportive lead officer from OSF is an important asset for emerging organizations.

- Staff capacity continues to be a limiting factor. Our seed portfolio is approximately 5% of our annual budget in the form of 10 grants per year. Our staff effort with these grants that amount to less than $250,000 per year, is significantly more than with some of the larger grants in our portfolio. Supporting the seed grantees is very labor intensive.

- Sustainability remains a key issue in many of the seed projects. While some have made progress and are on their way of becoming diversified, they still heavily rely on OSF’s support. While some grantees manage to stay at or under the 1/3rd (Espolea, Luca Coscioni Association, the Polish Drug Policy Network, Diogenis), others, like the All Party Parliamentary Group for Drug Policy Reform and the Canadian Drug Policy Coalition remain more dependent and they have requested approval for grants that are slightly over 1/3rd of our support.

- Some examples mentioned may suggest the conclusion that we should increase seed funding in Europe and American regions as projects here had better potential to be successful. We stress the importance of funding in Asia and Africa despite limited results. The point of our seed grants is risk taking and the field badly needs our support in those regions.

- With appropriate coordination from the program, a relatively small amount of funds can have a significant impact. The “Support. Don’t Punish.” campaign demonstrated GDPP’s ability to rally its grantees and unite them in a common cause. While the campaign was a huge success generating dozens of appearances in leading news outlets, it also exposed tension with IDPC about ownership of an action and what our role is in the movement.

- There is a need for us to be more strategic about our seed grants and to improve the criteria for identifying where, and in what situations, this is a useful mechanism. Understanding our own limitations and setting clear parameters is important.

- OSF has to be in the position to take risk. At the same time we need to be more careful with selecting partners to work with. Seed projects rarely fulfill the expected results without the right leadership in place. We have experienced with grantees like Espolea and the Canadian Drug Policy Coalition that, though the organization is on the right track, because of diverging agendas held by the organization’s leadership, the organizations did not develop as expected. In Espolea’s case, the leader’s self-focus, while in some sense making him a strong entrepreneur seems to have led to the collapse of the organization once his ambition moved elsewhere. Finding the best ways of expressing our views to them is often an issue.

- Experience shows (e.g. with ICW, Espolea) that pondering about the future direction of  organizations we support  and their own institutional developmental needs is a worthwhile step early in our collaboration; rather than focusing only on the expected outcomes of the proposed projects.

- The Advisory Board of GDPP discussed a draft version of this review at its meeting on April 9, 2015. They greatly appreciated seed grants as a tool to explore potential with groups that we have not worked with before. This was seen as an integral part of OSF’s way of interacting with the field and strong positions were formed about what success and failure of these grants mean. Given that these are the grants that open doors to future opportunities, it was seen that a greater commitment to this part of our work would have positive implications, for us, down the line.

Espolea, International Community of Women Living with HIV/AIDS – Asia Pacific, German Hemp Association, Polish Academy of Sciences and the Ganja Law Reform Coalition are the organizations GDPP does not intend to continue collaborating with at this point.