OSIEA -Health and Rights Program – Access to Essential Medicines Initiative (AEMI)

July, 2012

Name of Organization:            Center for Health, Human Rights Development (CEHURD)

Year of Founding:                    2009

Grant Title:  	Intellectual property, access to medicines and health information in Uganda

Person to Sign Grant Letter:   Mulumba Moses

+256-712-657974

Contact Information:   	Plot 614, Tufnell Drive, Kamwokya

P. O. Box 16617, Wandegeya, Kampala

Tel: +256-414-532283

info@cehurd.org; cehurd.uganda@gmail.com

www.cehurd.org

Grant Period:   	September 01, 2012 – September 01, 2014

Other Support:    	None

Past OSF Support:   	2011: Research and advocacy on intellectual property, access to medicines and knowledge in Uganda (OSIEA/LAHI/AEMI/HMI/Info: 95,630)

2011: Advocacy on access to medicines and intellectual property (OSIEA: $27,000)

2010: Constitutional case on maternal mortality (OSIEA:$8,000)

Organization Budget:  	$362,000

Amount Requested:     		         $ 360,000

Amount Recommended:      	$280,000

Program/Dept:   	OSIEA (37%) - $105,000; LAHI (23%) - $65,000; AEMI (18%) - $50,000; HMI (11%) - $30,000; Info Program (11%) - $30,000

Disbursement(s):   	4

Description of Organization:

The Center for Health, Human Rights and Development (CEHURD) is a non-profit research and advocacy organization promoting the right to health in East Africa. CEHURD was founded in 2009 to ensure that public health laws are used as tools for the promotion and protection of the right to health for vulnerable populations in Uganda and in the East African region. CEHURD is positioning itself as a litigation center on the right to health in the region.

Description of Project for which funding is sought:

Although CEHURD is a relatively young organization, it has emerged as a leading institution in the region with expert knowledge on trade related aspects of intellectual property (TRIPS) and its implications, including on access to essential and affordable medicines. The executive director is one of the few experts in the field of intellectual property (IP) in the East Africa region and one of the few engaged in advocacy on right to health in Uganda. This is a co-funded grant by OSIEA and four projects within OSF’s Public Health Program (PHP) are seeking to fund CEHURD for the next two years. OSIEA’s contribution is $105,000 and the budget indicates the activities will be supported by the OSIEA contribution.

This grant is to support various program activities as well as institutional support. The project will advocate for access to medicines and health information by doing the following:

- Challenging harmful legislation at national and regional level;

- Strengthening the capacity of civil society to understand and engage on issues of intellectual property and access to medicines and right to health;

- Advocating for needed policies and  recognition of traditional medicine and indigenous knowledge as a source of alternative and affordable health care;

- Challenging harmful laws and policies that prevent fulfillment and achievement of right to health through litigation as well as right to clean environment as an underlying determinant of health;

- Advocating for and promoting the realization of sexual and reproductive and maternal health rights of women in Uganda; and

- Holding a regional workshop on litigating the right to health in the East African countries to build the capacity of legal practitioners.

For CEHURD to continue to grow into a strong organization they will need organizational development support, hence a component to support this is included in the grant.

Concerns and Caveats:

None

Sustainability (Exit) Strategy:

The constitutional petition filed by CEHURD in Uganda on maternal mortality thrust them into international limelight.  This has created a huge demand on this small organization to grow quickly, but also has exposed them to possible support by other donors. OSIEA’s support to develop the organizational and staff capacity will help them manage this rapid growth successfully.

Rationale for Recommendation:

Uganda’s bill of rights does not contain the right to health and some of the public health related laws are archaic and discriminatory. In addition, civil society lacks sufficient capacity to engage on issues of right to health and particularly on intellectual property and its impact on health. The idea of framing health rights as constitutional obligations that are justifiable through public interest litigation is still new in Uganda. The ongoing constitutional petition filed by CEHURD on maternal mortality is part of this effort to impact the realization of access to health as a fundamental right.

A number of  IP related bills and policies such as the anti-counterfeit goods bill, the industrial property bill as well as the IP policy are before the Uganda parliament in draft form. The two bills and policy have significant gaps to guarantee access to medicines. These bills classify generics medicines as counterfeit drugs under the guise of fighting anti counterfeit goods. The banning of generic drugs as counterfeits would have serious implications for the cost of HIV medication for example. The draft laws also seek longer periods of enforcement of intellectual property rights for drug manufacturers through extension of patent periods, another attempt by international pharmaceutical companies to make it harder to access generic versions of medication.

Despite these gaps, there is pressure to pass the bills before 2016 so that Uganda becomes compliant with World Trade Organization (WTO) rules on intellectual property. There is likely to be a rush to pass these bills and policies without comprehensive national consultation and scrutiny as 2016 draws closer. Although the Uganda Counterfeit Goods Bill had been significantly revised to favor access to medicines (with support from OSIEA and PHP), it was not passed in the eighth parliament; there is high possibility of these gains being eroded by the new parliament because most of the parliamentarians who had been sensitized were not re-elected. Based on all these developments, there is need to step up advocacy to ensure any new legislation that is passed does not undermine access and affordability of public goods.

The areas of work proposed by CEHURD in this project are consistent with OSIEA and PHP’s goals of promoting increased access to essential medicine and strengthening the capacity of civil society organizations to demand transparency and hold governments accountable in health policy and practice.

_________________________________

Approved by the OSIEA Regional Board

- during 8th OSIEA Regional Board Meeting

- July 26th - 28th 2012, Naivasha, Kenya

Grant and Payment Details

| Date Requested (mm/dd/yyyy) |  | Begin Date (mm/dd/yyyy) |  | End Date (mm/dd/yyyy) |  |
| --- | --- | --- | --- | --- | --- |
| 06/01/2011 |  | 09/01/2012 |  | 09/01/2014 |  |
| Program (%) |  | Amount $ | Budget | T1 | T0 |
| OSIEA (37%) |  | 105,000 | 5 | 47003 | B7444 |
| LAHI (23%) |  | 65,000 | 3 | 14849 | B7437 |
| AEMI (18%) |  | 50,000 | 3 | 14816 | B7445 |
| HMI (11%) |  | 30,000 | 3 | 18855 | B7449 |
| Information Program (11%) |  | 30,000 | 3 | 18571 | --- |
| Monitoring Schedule |  |  | Number of Disbursement(s): |  |  |
| Report | Date (mm/dd/yyyy) |  | Date (mm/dd/yyyy) |  | Amount $ |
| Interim | 02/15/2013 |  | 09/01/2012 |  | 70,000 |
| Interim | 08/15/2013 |  | 03/01/2013 |  | 70,000 |
| Interim | 02/15/2014 |  | 09/01/2013 |  | 70,000 |
| Final | 09/30/2014 |  | 03/01/2014 |  | 70,000 |

BUDGET

Name of Organization:	Center for Health, Human Rights and Development (CEHURD)

Project title:			Intellectual property, access to medicines and health information in Uganda

Grant Period:			September 01, 2012 - September 01, 2014

Amount:			280,000

| Line Item | Total Project Amount ($US) | Proposed OSIEA Contribution ($US) | OSF Public Health Program Contribution ($US) |
| --- | --- | --- | --- |
| Staff Salaries and Benefits (% of time that salary represents, amount and duration) |  |  |  |
| Staff Salaries |  |  |  |
| 2 Program Officers (100%) $550 x 2 pax x 24 months | 26,400 | 26,400 |  |
| 1 Program Assistant (100%) $400 x 1 pax x 24 months | 9,600 | 9,600 |  |
| Executive Director (100%) $1,125 x 24 months | 27,000 | 27,000 |  |
| Communications Officer (100% ) $270 x 24 months | 6,480 | 6,480 |  |
| Administrative Assistant (100%) $410 x 24 months | 9,840 | 9,840 |  |
| Accountant (100%) $410 x 24 months | 9,840 | 9,840 |  |
| Subtotal | 89,160 | 89,160 |  |
| Program Activities (including travel and meetings - number of participants or items, days and amount) |  |  |  |
| Objective 1: Promote access to medicines through advocacy for enabling legislation at domestic and regional levels and communicate mobilization |  |  |  |
| Sub objective I: Challenge harmful legislation that impacts access to medicines in Uganda and regionally |  |  |  |
| (a) The Uganda Anti-Counterfeit Goods Bill 2010 and the Industrial Properties Bill |  |  |  |
| Hold 2 lobby meetings with key Parliamentarians over needed reforms in the bills |  |  |  |
| - Mobilization (Fuel and airtime expenses) x 2 @ $35 | 70 |  | 70 |
| - Lunch meeting x 10 pax x 2 @ $22 | 440 |  | 440 |
| - Transport Refund x 10 pax x 2 @ $44 | 880 |  | 880 |
| Subtotal | 1,390 |  | 1,390 |
| Hold a CSO meetings on strategy and advocacy activities in the two years |  |  |  |
| - Conference package x 40 pax x 1 meetings @ $35 | 1,400 |  | 1,400 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $60 | 60 |  | 60 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 3 x 1 @ $31 | 93 |  | 93 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 40 pax x 1 @ $22 | 880 |  | 880 |
| Subtotal | 2,683 |  | 2,683 |
| (b) The Competition Bill |  |  |  |
| Hold lobby meetings with policy makers over inclusion of the provisions that favor and support access to medicines |  |  |  |
| - Mobilization (Fuel and airtime expenses) x 2 @ $35 | 70 |  | 70 |
| - Lunch meeting x 10 pax x 2 @ $22 | 440 |  | 440 |
| - Transport Refund x 10 pax x 2 @ $44 | 880 |  | 880 |
| Subtotal | 1,390 |  | 1,390 |
| Hold one CSO workshop to sensitize activists on issues for reform in the Competition Law |  |  |  |
| - Conference package x 30 pax x 1 meeting @ $35 | 1,050 |  | 1,050 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $60 | 60 |  | 60 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 4 x 1 @ $31 | 124 |  | 124 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 30 pax x 1 @ $20 | 600 |  | 600 |
| Subtotal | 2,084 |  | 2,084 |
| (c) The Common Market Protocol |  |  |  |
| Hold a breakfast meeting with Uganda EALA members over access to medicine issues in the Common Market Protocol |  |  |  |
| - Mobilization (Fuel and airtime expenses) x 1 @ $35 | 35 |  | 35 |
| - Breakfast meeting x 10 pax x 1 @ $11 | 110 |  | 110 |
| - Transport Refund x 10 pax x 1 @ $44 | 440 |  | 440 |
| Subtotal | 585 |  | 585 |
| Conduct a media workshop on issues of access to medicine in the Common Market Protocol |  |  |  |
| - Conference package x 25 pax x 1 @ $35 | 875 |  | 875 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $90 | 90 |  | 90 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 4 x 1 @ $31 | 124 |  | 124 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 25 pax x 1 @ $22 | 550 |  | 550 |
| Subtotal | 1,889 |  | 1,889 |
| (d) The Draft EAC Anti-Counterfeit Goods Bill |  |  |  |
| Hold 2 breakfast meeting with Uganda EALA members over access to medicine issues in the Draft EAC Anti-Counterfeit Goods Bill |  |  |  |
| - Mobilization (Fuel and airtime expenses) x 2 @ $35 | 70 |  | 70 |
| - Breakfast meeting x 10 pax x 2 @ $11 | 110 |  | 110 |
| - Transport Refund x 10 pax x 2 @ $44 | 880 |  | 880 |
| Subtotal | 1,060 |  | 1,060 |
| Hold a CSO meeting on the EAC process on access to medicines |  |  |  |
| - Conference package x 30 pax x 1 meeting @ $35 | 1,050 |  | 1,050 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $60 | 60 |  | 60 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 4 x 1 @ $31 | 124 |  | 124 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 30 pax x 1 @ $22 | 660 |  | 660 |
| Subtotal | 2,144 |  | 2,144 |
| Sub - objective II: Strengthen regional and domestic civil society capacity to understand, appreciate and use Intellectual Property and trade policies to increase access to medicines |  |  |  |
| Hold 1 non-residential workshop to bring CSOs and stakeholders together to discuss IP in areas of trade and development |  |  |  |
| - Conference package x 30 pax x 1 meetings @ $35 | 1,050 |  | 1,050 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $60 | 60 |  | 60 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 3 x 1 @ $31 | 93 |  | 93 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 30 pax x 1 @ $22 | 660 |  | 660 |
| Subtotal | 2,113 |  | 2,113 |
| Sub-objective III: Propose and advocate for needed policies, regulations, laws, and practices on Intellectual Property and Traditional Medicines |  |  |  |
| Hold 1 meeting with policy makers aimed at discussing the development of a policy on traditional knowledge and medicinal |  |  |  |
| - Conference package x 20 pax x 1 meeting @ $35 | 700 |  | 700 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $60 | 60 |  | 60 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 3 x 1 @ $50 | 150 |  | 150 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 20 pax x 1 @ $44 | 880 |  | 880 |
| Subtotal | 2,040 |  | 2,040 |
| Objective 2: To strengthen the recognition, protection and fulfillment of health and human rights in Uganda at regional level |  |  |  |
| Hold a workshop to sensitize CSOs on legal implications of harmful legislation on access to medicines. |  |  |  |
| - Conference package x 30 pax x 1 meeting @ $35 | 1,050 | 1,050 |  |
| - Mobilization (Fuel and airtime expenses) x 1 @ $60 | 60 | 60 |  |
| - Projector (LCD) x 1 @ $100 | 100 | 100 |  |
| - Key Facilitators allowances x 4 x 1 @ $50 | 200 | 200 |  |
| - Stationery x 1 @ $150 | 150 | 150 |  |
| - Transport Refund for participants x 30 pax x 1 @ $25.6 | 770 | 770 |  |
| Subtotal | 2,330 | 2,330 |  |
| Sub-objective I: To conduct research and litigation to challenge unconstitutional provisions in health and human rights related legislation. |  |  |  |
| Institute and conduct 4 strategic health rights cases in courts @ $3,500 | 14,000 |  | 14,000 |
| File and represent 8 pro-bono cases as legal services to individuals who have suffered health rights violations @ $2,000 | 16,000 |  | 16,000 |
| Carry out 10 field visits to interview health workers and victims of health rights violations |  |  |  |
| - Car hire (1 x 20 days @ $87) | 1,740 |  | 1,740 |
| - Fuel for the car (1 x 20days @ $52) | 1,040 |  | 1,040 |
| Subtotal | 32,780 |  | 32,780 |
| Sub-Objective II: To promote the aspect of justifiability of the right to health into the judiciary, legal fraternity and health service providers |  |  |  |
| Conduct a non-residential workshop for the judiciary on the practical aspects of the justifiability of the right to health in Uganda |  |  |  |
| - Conference package x 20 pax x 1 day @ $47 | 940 |  | 940 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $174 | 174 |  | 174 |
| - Projector (LCD) x 2 @ $100 | 200 |  | 200 |
| - Key Facilitators allowances x 4 x 1 @ $100 | 400 |  | 400 |
| - Stationery x 1 @ $265 | 265 |  | 265 |
| - Transport Refund for participants x 20 pax x 1 @ $75 | 1,500 |  | 1,500 |
| Subtotal | 3,479 |  | 3,479 |
| 3-day residential regional lawyers’ meeting on information, experiences and best practices in litigating health related issues in the EAC | 25,000 |  | 25,000 |
| Sub-objective III: Undertake work on other underlying determinants of the right to health |  |  |  |
| Hold 2 meetings with parliamentarians especially the social services committee on the best practices to enhance provision and accesses to social services |  |  |  |
| - Mobilization (Fuel and airtime expenses) x 2 @ $35 | 70 |  | 70 |
| - Lunch meeting x 6 pax x 2 @ $25 | 300 |  | 300 |
| - Transport Refund x 6 pax x 2 @ $50 | 600 |  | 600 |
| Hold an advocacy meeting with district health inspectors from selected districts |  |  |  |
| - Mobilization (per diem, transport, accommodation, airtime while mobilizing) x 2 x 5 days @ $ 100 | 1,000 |  | 1,000 |
| - Conference package x 15 pax x 1 meeting @ $35 | 525 |  | 525 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 4 x 1 @ $31 | 124 |  | 124 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 12 pax x 1 @ $50 | 600 |  | 600 |
| - Car hire (for transporting CEHURD staff) x 1 x 3 @ $87 | 261 |  | 261 |
| - Fuel for the car x 1 x 2 @ $87 | 174 |  | 174 |
| - Accommodation & per diem x 3 people x 2 @ $ 100 | 600 |  | 600 |
| Subtotal | 4,504 |  | 4,504 |
| Sub-Objective IV: To promote the realization of reproductive and maternal health rights including ensuring access to youth friendly reproductive health services |  |  |  |
| Hold a 1-day workshop with policy makers to ensure provision of friendly reproductive health services at all centers |  |  |  |
| - Conference package x 40 pax x 1 meeting @ $35 | 1,400 |  | 1,400 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $60 | 60 |  | 60 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 4 x 1 @ $31 | 124 |  | 124 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 40 pax x 1 @ $44 | 1,760 |  | 1,760 |
| Subtotal | 3,594 |  | 3,594 |
| Sub-objective V: Follow up on the maternal health case: constitutional petition No.16 of 2011 |  |  |  |
| Mobilizing relevant stakeholders to attend court hearings of the appeal |  |  |  |
| - Mobilization x 4 @ $100 | 400 |  | 400 |
| - Transport allowances x 50 x 4 @ $4 | 800 |  | 800 |
| Hold 1 press conference on the effect of the ruling given by court regarding the petition x 1 @ $1,000 | 1,000 |  | 1,000 |
| Hold 8 coalition meetings to discuss advocacy activities and the way forward on the petition and the appeal @ $150 | 1,200 |  | 1,200 |
| Carry out research on appeals to the Supreme Court, draft and file an appeal arising out of the court’s ruling on the objection x 1 @ $3,000 | 3,000 |  | 3,000 |
| Working on the appeal process and continuous follow ups x 1 @ $5,000 | 5,000 |  | 5,000 |
| Hold a one-day legal expert advisory meetings x 1 @ $700 | 700 |  | 700 |
| Subtotal | 12,100 |  | 12,100 |
| Follow up and support to Uganda Human Rights Complaint |  |  |  |
| Popularize the complaint through media engagements | 2,500 |  | 2,500 |
| Hold public dialogues protesting power cuts in public health facilities. | 3,000 |  | 3,000 |
| Meetings with UMEME, ERA, MoH and government policy officials involved. | 2,000 |  | 2,000 |
| Subtotal | 7,500 |  | 7,500 |
| Objective 3: To ensure policy change on intellectual property and human rights at national, regional and international levels |  |  |  |
| Hold 1 parliamentary meeting on the access to knowledge issues in the copyright and counterfeit legislation |  |  |  |
| - Conference package x 30 pax x 1 meeting @ $35 | 1,050 |  | 1,050 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $60 | 60 |  | 60 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 4 x 1 @ $31 | 124 |  | 124 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 30 pax x 1 @ $44 | 1,320 |  | 1,320 |
| Subtotal | 2,804 |  | 2,804 |
| Support 2 core group meetings working on the creative commons process in Uganda to work towards finalizing the import license and another on copyright reform |  |  |  |
| - Conference package x 30 pax x 1 meeting @ $35 | 1,050 |  | 1,050 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $60 | 60 |  | 60 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 4 x 1 @ $2031 | 8,124 |  | 8,124 |
| - Stationery x 1 @ $100 | 100 |  | 100 |
| - Transport Refund for participants x 30 pax x 1 @ $22 | 660 |  | 660 |
| Subtotal | 10,094 |  | 10,094 |
| Hold a meeting with government officials from Ministry of Trade, Justice, President's office, Parliament, Uganda Registration Services Bureau to discuss issues on the copyright reforms. |  |  |  |
| - Conference package x 40 pax x 1 meeting @ $35 | 1,400 |  | 1,400 |
| - Mobilization (Fuel and airtime expenses) x 1 @ $100 | 100 |  | 100 |
| - Projector (LCD) x 1 @ $100 | 100 |  | 100 |
| - Key Facilitators allowances x 4 x 1 @ $31 | 124 |  | 124 |
| - Stationery x 1 @ $150 | 150 |  | 150 |
| - Transport Refund for participants x 40 pax x 1 @ $44 | 1,760 |  | 1,760 |
| Subtotal | 3,634 |  | 3,634 |
| Objective 4: Strengthen the institutional capacity of CEHURD through ensuring effective and efficient systems and structures |  |  |  |
| Establish an effective accounting system - purchasing a computerized Accounting package x 1 @ $1,000 | 1,000 |  | 1,000 |
| Develop an M&E framework to monitor organization's activities x 1 @ $800 | 800 |  | 800 |
| Carry out one training for CEHURD directors and managers to develop their management capacity | 800 |  | 800 |
| Carry out at least one staff training in advocacy and networking x 1 @ $890 | 890 |  | 890 |
| Organize one exchange visit per year to assimilate better work practices x 2 @ $1500 | 3,000 |  | 3,000 |
| Hold at least 2 board meeting per year (4 @ $350) | 1,400 |  | 1,400 |
| Carry out a two-days fundraising training for the staff x 1 @ $450 | 450 |  | 450 |
| Developing a five-year fundraising strategy and work plan for the organization x 1 @ $870 | 870 |  | 870 |
| Fundraising towards acquisition of office premises and a training center x 2 @ $4000 | 8,000 |  | 8,000 |
| Subtotal | 17,210 |  | 17,210 |
| Publications |  |  |  |
| Publish 1 press release in a national daily newspaper on issues for reforming the Bill x 1 @ $1,800 | 1,800 | 1,800 |  |
| 1 policy brief on the key issues of concern in the Bills x 400 @ $2 | 800 | 800 |  |
| Publish a press release over the necessity of the Bill in promoting access to medicines x 1 @ $1,800 | 1,800 | 1,800 |  |
| Publish a press release in a regional newspaper on issues of access to medicines of the Common Market Protocol x 1 @ $1,800 | 1,800 | 1,800 |  |
| Publish 1 press release in a regional newspaper on issues of access to medicines of the draft EAC Anti-Counterfeit Goods Bill x 1 @ $1,800 | 1,800 | 1,800 |  |
| Develop a popular write up to answer the question: what are the best practices on litigating the right to health x 1 @ $1,000 | 1,000 | 1,000 |  |
| Develop a popular write-ups addressing elements to consider in determining the right to health violation cases to magistrates. | 1,800 | 1,800 |  |
| Subtotal | 10,800 | 10,800 |  |
| Monitoring and Evaluation |  |  |  |
| Annual Financial auditing x 2 @ $1,250 | 2,500 | 2,500 |  |
| Subtotal | 2,500 | 2,500 |  |
| TOTAL PROJECT COSTS | 244,867 | 104,790 | 140,077 |
| Contribution to administrative overhead costs (13 of total grant) | 35,133 | 210 | 34,923 |
| GRAND TOTAL | 280,000 | 105,000 | 175,000 |