OSIEA North Sudan Program – Human Rights and Justice

July, 2012

Name of Organization:		Sudanese Plastic Artists General Union (SPAGU)

Year of Founding:         		1956

Grant Title:  		North Sudan: Promotion of human rights through arts and culture

Person to Sign Grant Letter:  	 	Ali Al Amin Mohamed

Project Manager

Email: alialamin86@yahoo.com

Tel: +249 912 213 341

Contact Information:   		South of Ozone Park

Khartoum 2, Sudan

Tel: +249 912 213 341

Project Manager: Ali Al Amin Mohamed

alialamin86@yahoo.com

Tel: +249 912 213 341

Grant Period:   	        September 01, 2012 – September 01, 2013

Other Support:    		SPAGU membership ($15,000)

Past OSF Support:   	2011: North Sudan: Promotion of Human Rights through

Arts and Culture (OSIEA $50,000)

Organization Budget:   	        $65,000

Amount Requested:     		                  $110,000

Amount Recommended:      	        $100,000

Program/Dept:   	        OSIEA (100%)

Disbursement(s):   	        2

Description of organization:

The Sudanese Plastic Artists General Union (SPAGU) was established in 1956. It has an office in Khartoum and is registered with the Registrar of Cultural Organizations. It has a membership of 219 artists. SPAGU aims to unify the efforts of Sudanese plastic artists and advocate for their interests; to strengthen their technical skills; to protect the national heritage; to promote the multicultural identity of Sudan; and to spread understanding of fine art. SPAGU is a democratic organization, holding elections biannually. The union received its first-ever donor funding in 2009 under the European Union’s Human Rights and Democracy Project.

Description of project for which funding is sought:

SPAGU aims to promote the role of culture and arts in enhancing human rights awareness in Sudan and advocating for cultural freedom through a series of activities in Khartoum and Al-Jazeera States implemented in collaboration with the Sudanese Sculptors Society and the Sudanese Plastic Arts Women’s Society. Depending on the security situation some activities may be implemented with the University of Diling, South Kordofan. The activities will consist of a series of seminars focused on freedom of cultural and political expression; two exhibitions of artistic works promoting human rights; and workshops to enhance the skills of artists in human rights education, focusing on photography, sculpture, textiles, portraiture and graphic design.

Funds are sought for administrative costs and covering the salaries of three current staff members. Support for the creation of three part-time assistant positions is requested in order to transfer staff’s skills and knowledge to younger people through mentorship.

Concerns and caveats:

Although SPAGU has successfully implemented two projects, it recognizes that its decision-making and management procedures are cumbersome.  This grant will enable SPAGU to organize four organizational development workshops for members of the Executive Committee, staff and volunteers to find ways to make work flow more smoothly. OSIEA will separately also try to identify Arabic-speaking arts administration courses which SPAGU leadership or staff could attend.

OSIEA requested SPAGU to submit a two-year proposal. However, its Executive Committee would like to request one-year funding because it does not want to bind a newly elected Executive Committee to a long-term commitment.

Sustainability strategy:

Despite successful implementation of two projects, SPAGU has found it difficult to raise funds for its activities. This is partly because SPAGU leadership and staff do not speak English and the group has limited experience in fundraising. Once SPAGU’s elections for a new executive committee have taken place later in the  year, OSIEA will engage SPAGU to explore if there is interest in developing a fundraising strategy for the union and leveraging more on the contributions of its members.

Rationale for recommendation:

The tools used by civil society to promote human rights tend to be text-based rather than image-based, even though Sudan is a country with low literacy levels. Support to SPAGU will highlight other more creative means to promote human rights and will, on the one hand, sensitize artists on human rights so that they can convey human rights messages effectively and, on the other hand, sensitize civil society on how it can convey human rights messages through images. Further, OSIEA’s grant will also support a union which is progressive and practices democracy through regular selection of its leadership in competitive elections.  Support for this project advances two objectives of OSIEA’s strategy to promote cultural diversity and freedom of expression in Sudan; it will have a multiplier effect as SPAGU cooperates with other sectors which are a priority for OSIEA, in particular journalists.

_________________________________

Approved by the OSIEA Regional Board

- during 8th OSIEA Regional Board Meeting

July 26th - 28th 2012, Naivasha, Kenya

Grant and Payment Details

| Date Requested |  | Begin Date |  | End Date |  |
| --- | --- | --- | --- | --- | --- |
| July 6, 2012 |  | September 01, 2012 |  | September 01, 2013 |  |
| Program (%) |  | Amount $ | Budget | T1 | T0 |
| OSIEA |  | $100,000 | 5 | 47040 | B7430 |
| Monitoring Schedule |  |  | Number of Disbursement(s): |  |  |
| Report | Date (mm/dd/yyyy) |  | Date (mm/dd/yyyy) |  | Amount $ |
| Interim report | 02/15/2013 |  | 09/01/2012 |  | $50,000 |
| Final report | 10/15/2013 |  | 03/01/2013 |  | $50,000 |

PROJECT BUDGET:

Organization:	 		Sudanese Plastic Artists General Union (SPAGU)

Project Title:                 	North Sudan: Promotion of human rights through arts and culture

Grant period:   		09/01/2012 – 09/01/2013

Grant Amount ($US): 		$100,000

| Line Item | Total Project Amount ($US) | Amount Requested from OSIEA ($US) | OSIEA Recommendation ($US) | Other Sources of Support ($US) |
| --- | --- | --- | --- | --- |
| Contribution to staff salaries (% of time dedicated towards project) |  |  |  |  |
| Director (100% of time) 12 months @$1,000 | 12,000 | 12,000 | 12,000 |  |
| Accountant (100% of time) 12 months @$1,000 | 12,000 | 12,000 | 12,000 |  |
| Administrative Assistant (100% of time) 12 months @$1,000 | 12,000 | 12,000 | 12,000 |  |
| 3 Administrative Assistants (50% of time) 3 x 12 months @$400 | 14,400 | 14,400 | 14,400 |  |
| Subtotal | 50,400 | 50,400 | 50,400 |  |
| Events |  |  |  |  |
| 3D production with computer-aided design |  |  |  |  |
| Rent for hall (7 days @$100) | 700 | 700 | 700 |  |
| Meals (7 days x 20 persons @$10) | 1,400 | 1,400 | 1,400 |  |
| Facilitator (1 x 7 days @$100) | 700 | 700 | 700 |  |
| Instructor (1 x 7 days @$100) | 700 | 700 | 700 |  |
| Subtotal | 3,500 | 3,500 | 3,500 |  |

| Line Item | Total Project Amount ($US) | Amount Requested from OSIEA ($US) | OSIEA Recommendation ($US) | Other Sources of Support ($US) |
| --- | --- | --- | --- | --- |
| Sculptors’ dilemmas in Islamic context |  |  |  |  |
| Rent for hall (2 days @$100) | 200 | 200 | 200 |  |
| Meals (2 days x 20 persons @$10) | 400 | 400 | 400 |  |
| Facilitator (1 x 2 days @$100) | 200 | 200 | 200 |  |
| Speakers (4 x 2 days @$100) | 800 | 800 | 800 |  |
| Subtotal | 1,600 | 1,600 | 1,600 |  |
| Sculptural works on the topic of human rights |  |  |  |  |
| Rent for studio (5 days @$100) | 500 | 500 | 500 |  |
| Meals (5 days x 20 persons@$10) | 1,000 | 1,000 | 1,000 |  |
| Facilitator (1 x 5 days @$100) | 500 | 500 | 500 |  |
| Instructor (1 x 3 days @$100) | 300 | 300 | 300 |  |
| Materials and stationery (lump sum) | 1,200 | 1,200 | 1,200 |  |
| Subtotal | 3,500 | 3,500 | 3,500 |  |
| Role of plastic art in human rights and democracy |  |  |  |  |
| Rent for hall (2 days @$100) | 200 | 200 | 200 |  |
| Meals (2 days x 20 persons @$10) | 400 | 400 | 400 |  |
| Facilitator (1 x 2 days @$100) | 200 | 200 | 200 |  |
| Speakers (2 x 2 days @$100) | 400 | 400 | 400 |  |
| Subtotal | 1,200 | 1,200 | 1,200 |  |
| Women’s rights and gender issues |  |  |  |  |
| Rent for hall (3 days @$100) | 300 | 300 | 300 |  |
| Meals (3 days x 20 persons @$10) | 600 | 600 | 600 |  |
| Facilitator (1 x 3 days @$100) | 300 | 300 | 300 |  |
| Speakers (6 x 3 days @$100) | 600 | 600 | 600 |  |
| Subtotal | 1,800 | 1,800 | 1,800 |  |
| Line Item | Total Project Amount ($US) | Amount Requested from OSIEA ($US) | OSIEA Recommendation ($US) | Other Sources of Support ($US) |
| Learning toys in preschool stage and human rights education |  |  |  |  |
| Transportation (visits to kindergartens (3 days x 15 persons @$5) | 225 | 225 |  |  |
| Meals (3 days x 15 persons @$10) | 450 | 450 |  |  |
| Facilitation (1 x 3 days @$100) | 300 | 300 |  |  |
| Instructor (1 x 3 days @$100) | 300 | 300 |  |  |
| Materials (lump sum) | 800 | 800 |  |  |
| Subtotal | 2,075 | 2,075 |  |  |
| Textile and T-shirt design for human rights messages |  |  |  |  |
| Rent for studio (3 days @$100) | 300 | 300 | 300 |  |
| Meals (3 days x 20 persons@$10) | 600 | 600 | 600 |  |
| Facilitation (1 x 3 days @$100) | 300 | 300 | 300 |  |
| Instructor (1 x 3 days @$100) | 300 | 300 | 300 |  |
| Materials (lump sum) | 600 | 600 | 400 |  |
| Exhibition | 400 | 400 | 400 |  |
| Subtotal | 2,500 | 2,500 | 2,300 |  |
| Artistic production and intellectual property rights |  |  |  |  |
| Rent for hall (3 days @$100) | 300 | 300 | 300 |  |
| Meals (3 days x 20 persons @$10) | 600 | 600 | 600 |  |
| Facilitator (1 x 3 days @$100) | 300 | 300 | 300 |  |
| Speakers (2 x 3 days @$100) | 600 | 600 | 600 |  |
| Subtotal | 1,800 | 1,800 | 1,800 |  |
| Photography as a tool for promoting human rights |  |  |  |  |
| Rent for hall (2 days @$100) | 200 | 200 | 200 |  |
| Meals (2 days x10 persons @$10) | 200 | 200 | 200 |  |
| Facilitation (1 x 2 days @$100) | 200 | 200 | 200 |  |
| Speakers (2 x 3 days @$100) | 600 | 600 | 600 |  |
| Exhibition | 400 | 400 | 400 |  |
| Subtotal | 1,600 | 1,600 | 1,600 |  |
| Line Item | Total Project Amount ($US) | Amount Requested from OSIEA ($US) | OSIEA Recommendation ($US) | Other Sources of Support ($US) |
| Portrait art techniques |  |  |  |  |
| Rent for studio (3 days @$100) | 300 | 300 | 300 |  |
| Meals (3 days x 10 persons @$10) | 300 | 300 | 300 |  |
| Facilitator (1x 3 days @$100) | 300 | 300 | 300 |  |
| Instructor (1 x 3 days @$100) | 300 | 300 | 300 |  |
| Materials (lump sum) | 300 | 300 | 300 |  |
| Exhibition | 400 | 400 | 400 |  |
| Subtotal | 1,900 | 1,900 | 1,900 |  |
| Freedom of expression and the Law on Press and Publications |  |  |  |  |
| Rent for hall (2 days @$100) | 200 | 200 | 200 |  |
| Meals (2 days x 20 persons @$10) | 400 | 400 | 400 |  |
| Facilitator (1 x 2 days @$100) | 200 | 200 | 200 |  |
| Speakers (4 x 2 days @$100) | 800 | 800 | 800 |  |
| Subtotal | 1,600 | 1,600 | 1,600 |  |
| Basics of graphic design for the press |  |  |  |  |
| Rent for hall (1 day @$100) | 100 | 100 | 100 |  |
| Meals (1 day x 10 persons @$20) | 200 | 200 | 100 |  |
| Facilitator(1 x 2 days @$100) | 100 | 100 | 100 |  |
| Instructor (1 x 2 days @$100) | 100 | 100 | 100 |  |
| Subtotal | 500 | 500 | 400 |  |
| Freedom of artistic expression |  |  |  |  |
| Rent for hall (2 days @$100) | 200 | 200 | 200 |  |
| Meals (2 days x 20 persons @$10) | 400 | 400 | 400 |  |
| Facilitator (1 x 2 days @$100) | 200 | 200 | 200 |  |
| Speakers (4 x 2 days @$100) | 800 | 800 | 800 |  |
| Subtotal | 1,600 | 1,600 | 1,600 |  |
| Graphics and advocacy in blogs and social networks |  |  |  |  |
| Rent for hall (2 days @$100) | 200 | 200 | 200 |  |
| Meals (2 days x 10 persons @$10) | 200 | 200 | 200 |  |
| Facilitator (1x 2 days @$100) | 200 | 200 | 200 |  |
| Line Item | Total Project Amount ($US) | Amount Requested from OSIEA ($US) | OSIEA Recommendation ($US) | Other Sources of Support ($US) |
| Speakers (2 x2 days @$100) | 400 | 400 | 400 |  |
| Subtotal | 1,000 | 1,000 | 1,000 |  |
| SPAGU organizational development courses |  |  |  |  |
| Meals (4 courses x 3 days x 20 persons @$10) | 2,400 | 2,400 | 2,400 |  |
| Resource persons (4 courses x 1 resource persons x 4 days @$400) inc. preparation time | 6,400 | 6,400 | 6,400 |  |
| Materials | 1,200 | 1,200 | 1,200 |  |
| Subtotal | 10,000 | 10,000 | 10,000 |  |
| Other expenses |  |  |  |  |
| Evaluation experts (2 x 5 days @$284) | 2,840 | 2,840 | 2,840 |  |
| Subtotal | 2,840 | 2,840 | 2,840 |  |
| TOTAL PROJECT COST | 89,415 | 89,415 | 87,040 |  |
| Contribution to administrative cost (13% of total grant)- 12 months @ $1,080 | 20,585 | 20,585 | 12,960 |  |
| Subtotal | 20,585 | 20,585 | 12,960 |  |
| GRAND TOTAL | 110,000 | 110,000 | 100,000 |  |