OSIEA South Sudan Program – Citizens’ Participation in Governance Debates

July, 2012

Name of Organization:			South Sudan Human Rights Society for Advocacy (SSHURSA)

Year of Founding:   			2007

Grant Title:  		South Sudan: Play your part in the constitution-making process

Person to Sign Grant Letter:  	 	Biel Boutros Biel, Executive Director

Contact Information:   	  		South Sudan Human Rights Society for Advocacy (SSHURSA)

Tonping Residential Area

Plot 41, Kololo Road

Juba, South Sudan

Email: sshursa2007@gmail.com / bboutrosb@yahoo.com

Tel: +211 955 300 382

Grant Period:   	  		September 01, 2012 – August 30, 2014

Other Support:    		OSIEA ($50,000); Members’ contributions ($2,500)

Past OSF Support:   			2011: Dissemination of the Transitional Constitution of South

Sudan using participatory and innovative methods (OSIEA

$50,000) (OSIEA)

Organization Budget:			$365,000

Amount Requested:     	            	$186,254

Amount Recommended:      	  	$150,000

Program/Dept:   	  		OSIEA (100%)

Disbursement(s):   	  	4

Description of organization:

The South Sudan Human Rights Society for Advocacy (SSHURSA) is a national human rights organization, founded in 2007 and legally registered as an NGO since 2010. It has conducted trainings on the transitional constitution, human rights and democracy with youth and women’s groups, members of legislative assemblies, civil society and local traditional authorities in various states in South Sudan. It has also exposed human rights violations committed by the Government of South Sudan.

Description of project for which funding is sought:

South Sudan Human Rights Society for Advocacy (SSHURSA) seeks support to disseminate information on the ongoing constitution-making process in Unity and Jonglei States and to gather the views of communities on the content of the Permanent Constitution for submission to the National Constitutional Review Commission and the National Assembly. SSHURSA also requests support for running costs, salaries and capacity-building for staff.

SSHURSA plans to organize 15 community dialogues in various counties of Unity and Jonglei States. It will also hold two lectures on constitutionalism and two consultative meetings with community and government leaders in the state capitals. It will also train 30 women and youth on the constitutional process so that they can transfer information to their communities. These activities will be supported by dissemination of Information Education Communication (IEC) materials.

SSHURSA also seeks institutional support to cover salaries for five staff members for the entire project period, as well as purchase of laptops, a satellite phone, two motorbikes and a scanner/printer unit. SSHURSA also seeks funding to develop a strategic plan and to undertake staff training.

Concerns and caveats:

The major risk to SSHURSA is the volatile security situation in Jonglei and Unity States due to inter-communal conflict and the presence of rebel groups. SSHURSA staff members are drawn from the two states and have successfully implemented activities there. They are therefore capable of assessing the risks and adapting their plans to avoid unnecessary exposure. SSHURSA also risks being subject to harassment due to its vocal human rights work. At least one SSHURSA staff member has received security training. OSIEA will undertake national and regional advocacy in case of any threat to SSHURSA. SSHURSA believes that its engagement in civic education work give it a degree of protection for its human rights work.

Sustainability strategy:

SSHURSA’s public profile has increased over the past 18 months as a result of its human rights advocacy. It has attracted the interest of several donors, including the European Union’s Human Rights and Democracy Fund, Diakonia and the National Endowment for Democracy. It is therefore anticipated that it will be able to diversify its sources of funding during the duration of this grant.

Rationale for recommendation:

There is widespread concern that the Sudan People’s Liberation Movement will try to further consolidate its grip on power through the current constitution-making process. The Transitional Constitution has already created a centralized state with a very powerful presidency. Support to SSHURSA, based on consultation with the grassroots, adopts a people-centred approach to the constitutional process. SSHURSA is one of the few groups which has been able to undertake work on the constitution in Jonglei and Unity States.  This grant application is complementary to other grants given by OSIEA to organizations working at the national and state level on the process.

Core support for SSHURSA is justified as it has conducted effective advocacy in South Sudan and has taken courageous and principled positions on human rights issues.

This project fits OSIEA’s objective to support efforts to ensure that the Permanent Constitution of South Sudan promotes decentralization and is consistent with international human rights standards.

_________________________________

Approved by the OSIEA Regional Board

- during 8th OSIEA Regional Board Meeting

- July 26th - 28th 2012, Naivasha, Kenya

Grant and Payment Details

| Date Requested |  | Begin Date |  | End Date |  |
| --- | --- | --- | --- | --- | --- |
| May 01, 2012 |  | September 01, 2012 |  | August 30, 2014 |  |
| Program (%) |  | Amount $ | Budget | T1 | T0 |
| OSIEA (100%) |  | $150,000 | 5 | 47020 | B7426 |
| Monitoring Schedule |  |  | Number of Disbursement(s): 1 |  |  |
| Report | Date (mm/dd/yyyy) |  | Date (mm/dd/yyyy) |  | Amount $ |
| Interim Report | 02/01/2013 |  | 09/01/2012 |  | $45,000 |
| Interim Report | 08/01/2013 |  | 02/15/2013 |  | $35,000 |
| Interim Report | 02/01/2014 |  | 08/15/2013 |  | $35,000 |
| Final Report | 09/30/2014 |  | 02/15/2014 |  | $35,000 |

PROJECT BUDGET:

Organization: 		South Sudan Human Rights Society for Advocacy (SSHURSA)

Project Title: 			South Sudan: Play your part in the constitution-making process

Grant Period:  		September 01, 2012 – August 30, 2014

Grant Amount ($US): 	$150,000

| Line Item | Total project amount ($US) | Amount requested from OSIEA ($US) | OSIEA recommendation ($US) |
| --- | --- | --- | --- |
| Staff salaries |  |  |  |
| Programme Officer@100% x $700 x 24 months | 16,800 | 14,800 | 14,800 |
| Project Director@100% x $800 x 24 months | 19,200 | 15,200 | 15,200 |
| Project Officer@100% x $600 x 24 months | 14,400 | 12,400 | 12,400 |
| Finance Manager@100% x $500 x 24 months | 12,000 | 10,000 | 10,000 |
| Administrative Assistant@100% x $400 x 24 months | 9,600 | 7,600 | 7,600 |
| Subtotal | 72,000 | 60,000 | 60,000 |
| Production of IEC materials |  |  |  |
| 400 posters@$10 | 4,000 | 4,000 | 4,000 |
| 15 banners@$150 | 2,250 | 2,250 | 2,250 |
| Production of 250 copies of abridged transitional constitution@$15 | 3,750 | 3,750 | 3,750 |
| Subtotal | 10,000 | 10,000 | 10,000 |
| Forum theatre trainings |  |  |  |
| Training 15 forum theatre Trainers of Trainees (ToTs) for 5 days@$300 | 1,500 | 1,500 |  |
| Consultancy fees for forum theatre ToTs training@$100 x 5 days) | 500 | 500 |  |
| Full board accommodation for consultant ($50 x 5 nights) | 250 | 250 |  |
| Training 300 pax for two forum theatre groups (@$500 x 5 days) | 2,500 | 2,500 |  |
| Training materials@$500 x 2 trainings | 1,000 | 1,000 |  |
| Forum theatre performance@$650 x 1 x 15 counties | 9,750 | 9,750 |  |
| Incentives for forum theatre ToTs@$25 x 15 x 12 months | 4,500 | 4,500 |  |
| Transport(car hire for participants during trainings)@$200 x 2 trainings x 2 days | 800 | 800 |  |
| Transport(car hire for participants during performance)@200 x 1 x 15 counties | 3,000 | 3,000 |  |
| 6 UNHAS return air tickets@$400 | 2,400 | 2,400 |  |
| Hall hire for trainings@$100 x 14 days | 1,400 | 1,400 |  |
| Production of 1 documentary@$600 | 600 | 600 |  |
| Multiplication of documentary@$5 x 15 copies | 75 | 75 |  |
| Hire of PA system for forum theatre performance@$50 x 1 x 15 counties | 750 | 750 |  |
| Subtotal | 29,025 | 29,025 |  |
| Community outreach activities in Unity and Jonglei States |  |  |  |
| Refreshments during community dialogues@$100 x 15 counties x 1 | 1,500 | 1,500 | 1,500 |
| Subtotal | 1,500 | 1,500 | 1,500 |
| Public Convenings and Lectures in Unity and Jonglei States |  |  |  |
| 2 public convenings with local leaders and state government officials@$15 x 25 pax x 2 states | 750 | 750 | 750 |
| 4 UNHAS return air tickets@$400 x 2 x 2 states | 1,600 | 1,600 | 1,600 |
| Full board accommodation for participants from Juba@$100 x 5 nights x 4 persons | 2,000 | 2,000 | 2,000 |
| Hall hire@$100 x 5 days x 2 states | 1,000 | 1,000 | 1,000 |
| Lunch@$15 x 25 pax x 2 states | 750 | 750 | 750 |
| Tea and breakfast@$5 x 25 pax x 2 states | 250 | 250 | 250 |
| Water@$3 x 25 pax x 2 states | 150 | 150 | 150 |
| Hall hire@$100 x 2 states | 200 | 200 | 200 |
| Transport(car hire)@$200 x 2 days x 2 states | 800 | 800 | 800 |
| Refreshments during public lectures in state capitals, Bentiu and Bor @$250 x 2 states | 500 | 500 | 500 |
| Subtotal | 8,000 | 8,000 | 8,000 |
| Youth and women groups training |  |  |  |
| Refreshments for Training of Trainers (ToTs) on interim constitution dissemination for 5 days@$400 x 2 states | 4,000 | 4,000 | 4,000 |
| Consultancy fees for ToTs training@$100 x 5 days x 2 states | 1,000 | 1,000 | 1,000 |
| Full board accommodation for consultant@$100 x 5 nights x 2 states | 1,000 | 1,000 | 1,000 |
| Incentives for ToTs@$25 x 30 x 12 months | 9,000 | 9,000 | 9,000 |
| Training materials@$300 x 2 trainings | 600 | 600 | 600 |
| Transport (car hire for participants during training) @$200 x 2 days x 2 trainings | 800 | 800 | 800 |
| Hall hire for trainings@$100 x 5 days x 2 trainings | 1,000 | 1,000 | 1,000 |
| Subtotal | 17,400 | 17,400 | 17,400 |
| Organizational development and staff training |  |  |  |
| Trainers@$200 x 3 days x 2 trainers x 2 events | 2,400 | 2,400 | 2,400 |
| Training materials (stationery) @$100 x 2 trainings | 200 | 200 | 200 |
| Food and refreshments @$20 x 10 persons x 2 trainings | 400 | 400 | 400 |
| Internal transport reimbursement @$50 x 10 x 2 trainings | 1,000 | 1,000 | 1,000 |
| Organizational audit cost @$5000 x 1 | 5,000 | 5,000 | 4,500 |
| Internal project monitoring and evaluation costs@$500 x 2 times | 1,000 | 1,000 |  |
| Subtotal | 10,000 | 10,000 | 8,500 |
| Strategic planning |  |  |  |
| Lunch@$10 x 10 persons x 4 days | 400 | 400 | 400 |
| Soda@$1 x 10 persons x 4 days | 40 | 40 | 40 |
| Refreshments@$3 x 10 persons x 8 times | 240 | 240 | 240 |
| Water@$1.5 x 10 persons x 12 times | 180 | 180 | 180 |
| Hall hire@$300 x 4 days | 1,200 | 1,200 | 1,200 |
| Transport (car hire)@$200 x 4 days | 800 | 800 | 800 |
| 4 UNHAS return air tickets@$400 | 1,600 | 1,600 | 1,600 |
| Full board accommodation (4 persons x $100 x 5 nights) | 2,000 | 2,000 | 2,000 |
| Facilitator local consultancy fees@$200 x 6 days | 1,200 | 1,200 | 1,200 |
| Subtotal | 7,660 | 7,660 | 7,660 |
| Equipment and supplies |  |  |  |
| 2 motorbikes DT-125 Yamaha@$6000 | 12,000 | 12,000 | 12,000 |
| 3 laptop computers@$1000 | 3,000 | 3,000 | 3,000 |
| Communication equipment (2 thuraya phones) @$1000 | 2,000 | 2,000 | 1,000 |
| 1 printing and photocopying machine@$1375x 1pc | 1,375 | 1,375 | 1,375 |
| Subtotal | 18,375 | 18,375 | 17,375 |
| TOTAL PROJECT COST | 173,960 | 161,960 | 130,435 |
| Contribution to SSHURSA overhead cost and administration 15% (24months @ $1,087.25) | 26,094 | 24,294 | 19,565 |
| GRAND TOTAL | 200,054 | 186,254 | 150,000 |