OSIEA South Sudan Program – Governance & Accountability

July, 2012

- Name of Organization:	South Sudan Women’s Empowerment Network (SSWEN)

Year of Founding:   			2005

Grant Title:  	South Sudan: Safeguarding women’s rights in the South Sudan constitution-making process

Person to Sign Grant Letter:  	Lilian Riziq

Director

lilian.riziq@sswen.org

Contact Information:   	  		Hai Buluk 77, Block 1

P.O Box 247, Juba

South Sudan

+211 955 490009

lilian.riziq@sswen.org

Grant Period:   	  		September 01, 2012 – August 30, 2014

- Other Support:    			Norwegian People’s Aid ($50,000)

- Past OSF Support:   			None

Organization Budget:			$430,000

Amount Requested:     	            	$180,140

Amount Recommended:      	  	$180,140

Program/Dept:   	  		OSIEA (32%)- $57,680; IWP (68%)- $122,460

Disbursement(s):   	  	4

- Description of organization:

- Founded in 2005, the South Sudan Women’s Empowerment Network (SSWEN) aims to achieve women’s economic independence, to alleviate poverty, to increase access to information, and to enhance social inclusion and gender equality. It is registered with the Ministry of Justice as an NGO.

- Description of project for which funding is sought:

- South Sudan is currently undergoing a constitutional review process for a permanent constitution. The project aims to promote women’s participation in the constitution-making process. SSWEN seeks to capture the views of women from inside the country and the diaspora and submit them to the National Constitution Review Commission (NCRC). It will advocate for the new constitution to enhance accountability, respect for the rule of law and citizens’ participation in decision-making.

- Most activities will focus on information dissemination. SSWEN will train three groups to translate information on the constitutional process into theatre pieces. During performances, SSWEN will record the discussions generated. SSWEN will also liaise with the media to provide constitution-based content for inserts in local dailies and to broadcast radio talk shows. SSWEN will also promote the participation of South Sudanese women in the Diaspora using social media. An overarching activity will be the production of context-specific information, education and communication (IEC) materials for use in all the above activities.

- In addition, SSWEN will hold three workshops with other advocacy groups to build a strategy for engagement in the constitution-making process. It will also hold three public convenings for experts to discuss specific constitutional issues and the discussions will inform the position papers that SSWEN will submit to the NCRC or the next tier in the constitution-making process.

- SSWEN will also use funds to hold three board meetings and will strengthen its institutional capacity by holding two trainings for its board and enabling two staff members to attend trainings.

- Concerns and caveats:

- SSWEN is a fairly young organization operating in a complex political and social environment for women in the nascent state of South Sudan. The project may look overly ambitious for such a young organization. IWP and OSIEA will maintain close contact with SSWEN over the entire grant period to preempt any concerns that would arise in the project implementation.

- Sustainability strategy:

- SSWEN’s inclusion of project beneficiaries in project monitoring and evaluation should ensure ownership not only of the project but also of the principles which SSWEN seeks to promote in the new constitution. This would ensure that women are able to identify with and claim their rights in the constitution once it is passed and this will certainly outlive the project period.

- The work with theatre groups and communities also broadens the reach of the project. Of particular relevance is the training of the members of the community focal points as this creates localized resources that remain with the communities long after the project comes to an end. SSWEN also works in collaboration with other organizations and this broadens the reach of its initiatives.

- Rationale for recommendation:

The transitional constitution adopted before South Sudan’s independence was done with little or no consultation with the population of South Sudan. The framework for the review process is short of practical approaches for obtaining the views of women. Given women’s marginalization, there is a risk that political parties and other interest groups will dominate the constitution-making process. This project will promote women’s participation in the process and allow for the consolidated views of women from the grassroots to be submitted to the NCRC and the higher tiers of constitutional review. It will also seek to safeguard progressive provisions in the transitional constitution, such as the 25 percent representation of women in leadership.

This project fits OSIEA’s objective to support efforts to ensure that the Permanent Constitution of South Sudan promotes respect for diversity and human rights and that the process is people-centered.

_________________________________

Approved by the OSIEA Regional Board

- during 8th OSIEA Regional Board Meeting

- July 26th - 28th 2012, Naivasha, Kenya

- Grant and Payment Details

| Date Requested |  | Begin Date |  | End Date |  |
| --- | --- | --- | --- | --- | --- |
| February 2012 |  | 09/01/2012 |  | 08/30/2014 |  |
| Program (%) |  | Amount $ | Budget | T1 | T0 |
| OSIEA (32%) |  | 57,680 | 5 | 47020 | B7426 |
| IWP (68%) |  | 122,460 |  |  |  |
| Monitoring Schedule |  |  | Number of Disbursement(s): |  |  |
| Report | Date (mm/dd/yyyy) |  | Date (mm/dd/yyyy) |  | Amount $ |
| Interim | 02/01/2013 |  | 09/01/2012 |  | $60,140 |
| Interim | 08/01/2013 |  | 02/15/2013 |  | $40,000 |
| Interim | 02/01/2014 |  | 08/15/2013 |  | $40,000 |
| Final | 09/30/2014 |  | 02/15/2014 |  | $40,000 |

- PROJECT BUDGET:

Organization: 		South Sudan Women’s Empowerment Network (SSWEN)

Project Title: 		South Sudan: Safeguarding women’s rights in the South Sudan constitution-making process

Grant Period: 		September 01, 2012 – August 30, 2014

- Grant Amount: (USD): $180,140

| Line items | Total project amount ($US) | Amount requested from OSIEA ($US) | OSIEA recommendation ($US) | Network program co-funding - IWP ($US) | Total OSIEA/IWP funding ($US) |
| --- | --- | --- | --- | --- | --- |
| Staff salaries |  |  |  |  |  |
| Program Director@$1400 x 24 months ($100%) | 33,600 | 33,600 | 33,600 |  | 33,600 |
| Program and Communication Coordinator@$1000 x 24 months ($100%) | 24,000 | 24,000 | 3,680 | 20,320 | 24,000 |
| Finance and Admin Officer@$500 x 24 months ($100%) | 12,000 | 12,000 | 12,000 |  | 12,000 |
| Monitoring and Evaluation Officer@$350 x 24 months ($100%) | 8,400 | 8,400 | 8,400 |  | 8,400 |
| Subtotal | 78,000 | 78,000 | 57,680 | 20,320 | 78,000 |
| Events - forum theatre training & performance |  |  |  |  |  |
| Food and refreshments, forum theatre training@$1500 x 3 days x 1 training | 4,500 | 4,500 |  | 4,500 | 4,500 |
| Forum theatre trainer@$400 x 3 days x 1 trainer | 1,200 | 1,200 |  | 1,200 | 1,200 |
| Training materials@$300 x 1 training | 300 | 300 |  | 300 | 300 |
| Food and refreshment - forum theatre performance@$450 x 3 days x 3 events | 4,050 | 4,050 |  | 4,050 | 4,050 |
| Transport (car hire for participants during performance@$150 x 3 events x 3 times | 1,350 | 1,350 |  | 1,350 | 1,350 |
| Hall hire for trainings@$200 x 3 days | 600 | 600 |  | 600 | 600 |
| Subtotal | 12,000 | 12,000 |  | 12,000 | 12,000 |
| Public and television debates and radio talk shows |  |  |  |  |  |
| Food and refreshments during public debates@$500 x 3 days x 3 events | 4,500 | 4,500 |  | 4,500 | 4,500 |
| Facilitator's fees, public debates@$200 x 3 days x 3 events | 1,800 | 1,800 |  | 1,800 | 1,800 |
| Participants’ transport@$200 x 3 days x 3 events | 1,800 | 1,800 |  | 1,800 | 1,800 |
| Air time for radio talk shows@$170 x 3 days x 3 events | 1,530 | 1,530 |  | 1,530 | 1,530 |
| Air time for television debates@$130 x 3 days x 3 events | 1,170 | 1,170 |  | 1,170 | 1,170 |
| Subtotal | 10,800 | 10,800 |  | 10,800 | 10,800 |
| Public convenings on selected thematic areas of the constitution |  |  |  |  |  |
| 3 public convenings with local leaders, women, youth and government representatives@$300 x 5 days x 3 events | 4,500 | 4,500 |  | 4,500 | 4,500 |
| Full board accommodation for participants@$100 x 5 days x 3 events | 1,500 | 1,500 |  | 1,500 | 1,500 |
| Hall hire@$100 x 5 days x 3 events | 1,500 | 1,500 |  | 1,500 | 1,500 |
| Transport reimbursement@$166.66 x 5 days x 3 events | 2,500 | 2,500 |  | 2,500 | 2,500 |
| Subtotal | 10,000 | 10,000 |  | 10,000 | 10,000 |
| Workshops |  |  |  |  |  |
| Lunch@$220 x 5 days x 3 workshops | 3,300 | 3,300 |  | 3,300 | 3,300 |
| Soda@$50 x 5 days x 3 workshops | 750 | 750 |  | 750 | 750 |
| Tea@$50 x 5 days x 3 workshops | 750 | 750 |  | 750 | 750 |
| Water@$46.66 x 5 days x 3 workshops | 700 | 700 |  | 700 | 700 |
| Hall hire@$100 x 5 days x 3 workshops | 1,500 | 1,500 |  | 1,500 | 1,500 |
| Transport reimbursements@$100 x 5 days x 3 workshops | 1,500 | 1,500 |  | 1,500 | 1,500 |
| Fees for local facilitator@$100x 5 days x 3 workshops | 1,500 | 1,500 |  | 1,500 | 1,500 |
| Subtotal | 10,000 | 10,000 |  | 10,000 | 10,000 |
| IEC materials |  |  |  |  |  |
| 1000 t-shirts@$11 each | 11,000 | 11,000 |  | 11,000 | 11,000 |
| 550 bags@$10 | 5,500 | 5,500 |  | 5,500 | 5,500 |
| 1000 flyers@$5 | 5,000 | 5,000 |  | 5,000 | 5,000 |
| 8 songs related to the constitution development process@$1000 | 8,000 | 8,000 |  | 8,000 | 8,000 |
| Poetry, 15 poems@$500 | 7,500 | 7,500 |  | 7,500 | 7,500 |
| 10 newspaper inserts on constitutional development process@$366 | 3,660 | 3,660 |  | 3,660 | 3,660 |
| Subtotal | 40,660 | 40,660 |  | 40,660 | 40,660 |
| Institutional strengthening |  |  |  |  |  |
| Support to board meetings@$800 x 3 meetings x 2 years | 4,800 | 4,800 |  | 4,800 | 4,800 |
| Management trainings to board members@$1200 x 2 trainings | 2,400 | 2,400 |  | 2,400 | 2,400 |
| Staff trainings at MS TCDC@$1000 x 2 trainings | 2,000 | 2,000 |  | 2,000 | 2,000 |
| Laptop computers@$1000 x 3 pcs | 3,000 | 3,000 |  | 3,000 | 3,000 |
| Subtotal | 12,200 | 12,200 |  | 12,200 | 12,200 |
| Total Project Cost | 173,660 | 173,660 | 57,680 | 115,980 | 173660 |
| Administrative Costs (3.73%) | 6,480 | 6,481 |  | 6,480 | 6,480 |
| Subtotal | 6,480 | 6,481 |  | 6,480 | 6,480 |
| GRAND TOTAL | 180,140 | 180,141 | 57,680 | 122,460 | 180,140 |