Christian Health Association of Kenya (CHAK) –

Summary of Data Analysis

During the November 2010 OSIEA regional board meeting, the grant to the Christian Health Association of Kenya (CHAK) was approved on the condition that a program review would be undertaken to assess the quality of service delivery and establish the impact that the project (now entering the fifth year of support) has had among the targeted beneficiaries. Below is the excerpt evaluating CHAK. This section is part of a larger evaluation of all of OSIEA Health and Rights projects which seek to integrate legal services in HIV/AIDS health care centres.

- Methods

        - Resource Assessment Questionnaire

Structure data on the financial, human, technical, and information resources needed to carry out integration was collected using a brief questionnaire handed out to program coordinators or relevant staff.  The questionnaire was distributed to Christian Health Association of Kenya (CHAK) program staff to be filled out independently. An incomplete questionnaire was returned to the research team and should be followed-up on by the research team in the next phase of data collection.

The information collected through the resource assessment questionnaire will help reveal how resources are driving - or limiting - program success, as well as implications for scale-up of future integration efforts.

        - Quantitative Indicators of On-Site Legal Service Provision and Referral

Quantitative indicators for on-site legal service provision were calculated by collecting and tabulating existing CHAK records using the Baseline Evaluation Instruments as guidance. CHAK was able to provide copies of 18 case records for their community health center in Naivasha, one of the two evaluation sites (the other being Zion).These records dated from June 2009 to February of 2010, though a number of records did not have dates. Indicators were calculated as proportions of clients receiving a particular service or referral overall. Given the missing information dates, no specific reporting periods could be identified so proportions were calculated for the entire known time frame.

c. Methods- Client Satisfaction Forms

On Tuesday, July 20, 2010, a visit was made to the site of Zion to administer the Client Satisfaction Card. Fifteen clients were available, and all completed a survey with the assistance of a translator. These clients were relatively new to CHAK and had not received training in human rights or legal assistance from CHAK. The client satisfaction form – as presented in the Baseline Evaluation Instruments – was in English. The form asked clients which services they received that day and to rate eight categories related to their experience at Zion on a four-point scale (1=weak, 2=fair, 3=good, 4=excellent). The various categories included: attitude, time, information, service, expertise, confidentiality, action, and benefit.

Two translators, both affiliates of Zion Community Clinic, were provided to verbally administer the survey in Kiswahili or the local indigenous language of Giryama, based on the client’s comfort level. The research team administered surveys to those comfortable with English.

The research team recorded all responses on the client satisfaction form, as translated by the translators. Demographic information was also collected for each client. With the exception of one client, ages were verified by the client, his/her identification card, or Zion personnel. The information recorded on the forms was then entered and sorted in a data spreadsheet so that results could be analyzed. Ratings were totaled and calculated as a proportion of the highest possible scoring.

The clients surveyed were new to CHAK’s legal integration program and therefore represent a control group of those who are not receiving legal aid or human rights trainings from CHAK. The client satisfaction form was not administered to clients who have accessed integrated services, or the ‘intervention group’ as these clients were unavailable during the baseline data collection visits made by the research team.

d. Methods- Qualitative Key Informant, Group Interviews and Focus Groups

Key informant interviews, group interviews, and focus groups were used to understand the qualitative dimensions of integrating legal and health services. Eight interviews and focus group discussions were carried out for CHAK and are summarized in the table below. Four of these interviews took place in the Naivasha site, while three took place in the Zion site. One key informant interview with CHAK’s legal officer took place at CHAK headquarters in Nairobi. This interview provides reflection across the organization’s sites.  Interview protocols from the Baseline Evaluation Instruments designed to focus on individual process and outcome components were used in combination during CHAK interviews for logistical purposes.

Interviews were carried out in English or Swahili and then transcribed. Swahili transcripts were then translated into English by the team of interviewers. Transcripts were then coded and analyzed using qualitative analysis software based on a detailed baseline analysis plan. The summary of findings below presents the results of this coding and analysis.

      - Summary of Findings

a. Understanding the Process of Integrating Legal and Health Services- Mixed Methods

This section presents data on the evaluation processes of interest from quantitative indicators and qualitative interviews and FGDs carried out with CHAK staff and clients. The results are organized using the process components from the evaluation’s conceptual-logical framework. Key findings are summarized and followed by analysis of indicators or supporting quotes from interviews and FGDs as appropriate. The section concludes with a list of issues for consideration relevant to legal integration processes for CHAK and other organizations and for the follow-up evaluation.

i . Quantitative Indicators of On-site Legal Service Provision and Referrals-Naivasha Site

- CHAK’s Naivasha site was able to provide records of 18 client cases which were tabulated into indicators. Note that these are not exhaustive- they do not represent all the cases CHAK has worked on in Naivasha, but only the documented ones. Figure 3 below summarizes each case. While they do not provide time trends, the 18 cases do give an overview of the different types of legal services and referrals that are provided by CHAK between February and June of 2010.

| Case Number | Date | Indicator Classification | Case Description | Action Taken | Health Facility |
| --- | --- | --- | --- | --- | --- |
| i | Feb-10 | 1,4 | Abuse of wife by husband | Negotiation meeting between client, relatives, and religious leaders | Naivasha |
| ii | Feb-10 | 1,7 (Kijabe Hospital) | Enrolled HIV+ girl in Kijabe AIDS Relief Program to ensure her health | N/A | Naivasha |
| iii | Apr-10 | 1,4 | A sensitive issue at Logonut | Settled (no further details given) | Naivasha |
| iv | Apr-10 | 1,4 | Plot/sale issues | Settled (no further details given) | Naivasha |
| v | 4/28/10 | 1 | Several violations surrounding inheritance issues | On going with the help of Lawyer | Naivasha |
| vi | 4/28/10 | 1 | Issues surrounding violations of minors' rights | Reported to the police and to the Chief | Naivasha |
| vii | 4/29/10 | 1,2,4 | Disinheritance of property | Reported to Assistant Chief, who will meet with client and give her letter to acquire spouse's belongings | Naivasha |
| viii | 4/29/10 | 1,4 | Child stigmatization and denied rights | Spoke with wife about getting child treatment and disclosing status to her husband | Naivasha |
| ix | 6/15-16/2010 | 1,2, 5 | Disinheritance of property (an IDP lady from Jikzao IDP Camp) | Being handled by CHAK Legal Advisor; and also referred to Amani Communities Africa in June 2010 for IDP support | Naivasha |
| x | 6/15-16/2010 | 1,4,7 | Discrimination based on status (child unable to attend preferred high school due to status) | School sued for discrimination but local administration (chief and Dos office) intervened before case concluded to have child admitted | Naivasha |
| xi | 6/15-16/2010 | 1,4,7 | Verbal abuse on PLWAs | Referred to local administration (chief and Dos office) | Naivasha |
| xii | 6/15-16/2010 | 1,2 | HIV/AIDS funds not reaching targeted people (PLWAs) | PLWAs advised on how to draft/forward proposals so as to access funds from CAAC | Naivasha |
| xiii | 6/2,27/2009 | 1,4 | Child denied education | Reported to Assistant Chief; child taken back to school | Naivasha |
| xiv | 02 - 03/year? | 1, 7 | Case of sexual violence of minor | Referred client to Nairobi Women's Hospital and police station for P-3 form | Naivasha |
| xv | 02 - 03/year? | 1 | Mistreatment of child | Referred to Chief ; advised to remove child when school closes and allow court to decide | Naivasha |
| xvi | N/A | 1 | Discrimination based on status | N/A | Naivasha |
| xvii | N/A | 1,4 | Discrimination based on status | Arranged negotiation meeting between parties; reported to chief | Naivasha |
| xviii | N/A | 1,7 | Client wouldn't get tested despite partner's positive status | Advice given; has now accepted testing and is under treatment | Naivasha |

Figure 3- CHAK-Naivasha, Summary of Quantitative Case Review

Figure 3: Indicator Key

Proportion of clients seen receiving: 1: Legal information or advice 2: Assistance with legal documents 3: Formal legal representation in or out of court 4: Access to informal conflict resolution mechanisms 5: Off-site referral to legal services 6: Off-site referral to economic empowerment services 7: Off-site referral to non-legal services

- Twelve of the eighteen cases took place between February and June of 2010. One case took place in 2009, while the five remaining cases did not specify a date.

- All 18 clients (100%) received legal information or advice (Indicator 1).

- Fourteen of the eighteen (~78%) of clients – the majority - received more than one legal service or referral.

  - Six of the eighteen (~33%) clients received legal services or advice (Indicator 1) and access to informal conflict resolution mechanisms (Indicator 4).

  - Three of the eighteen clients (~17%) received legal services or advice (Indicator 1) and were referred to non-legal services (Indicator 7) such as hospitals or local district offices.

  - Two of the eighteen clients (~11%) received legal services or advice (Indicator 3), access to formal conflict resolution mechanisms (Indicator 4), and were referred to non-legal services (Indicator 7).

  - One client received legal services or advice (Indicator 1) and help with legal documents (Indicator 2).

  - One client received legal services or advice (Indicator 1) help with legal documents (Indicator 2), and access to informal conflict resolution mechanisms (Indicator 4).

  - One client received legal services or advice (Indicator 1) help with legal documents (Indicator 2), and was referred to off-site legal services (Indicator 5).

- Two of the eighteen cases records reviewed were reported by CHAK as settled, with no further details given. More data on settled cases would be useful for documenting the outcome Increased Protection and Redress.

- Assuming these records are representative of the kinds of legal services CHAK-Naivasha clients receive, access to informal conflict resolution appears to be a primary approach for helping resolve client cases.

Issues for Consideration- Quantifying Legal Service Provision and Referral For CHAK: - CHAK should consider monitoring trends in access to justice by sex, age, and other categories as determined relevant by program staff. This could potentially be done with attention to traditional factors of discrimination such as socio-economic status, sex, age, religion, ethnicity, geographic region, etc. It is worth noting here that even simple age and demographic information for clients was not always documented on the client case forms. - CHAK should consider more consistent recording of case outcomes in client case files as they occur. For Follow-up Evaluation: - The research team should follow-up yet again with Zion site to see if any records exist as it was verified in the qualitative interviews that they do exist. - The research team should update the analysis of CHAK-Naivasha client case records for missing dates in order to quantify time trends in legal service provision and referral

ii. Process: On-Site Legal Service Provision

-CHAK has integrated a human rights program under its larger HIV/AIDS program at 15 health facilities. The human rights program is overseen by CHAK’s legal officer who provides information and support on rights issues to the various health facilities. Two facilities- Zion Community Health Center and Naivasha Hospital- were selected as sites for this evaluation. CHAK’s patients and clients are predominantly people living with HIV/AIDS (PLWA).

-While the program originally focused on training of service providers and patients/clients on human rights, it has more recently expanded to provide legal aid through legal clinics which are held on-site at all 15 health facilities. The legal aid is provided by CHAK’s legal officer and teams of pro-bono lawyers often from nearby communities.

[BC: Legal Officer]: …apart from the training component we also give legal advice and services to people living with HIV and AIDS through the clinic though it is something which started very recently. I actually started doing that when I joined CHAK when my predecessor didn’t do that by the time she was here, so we hold legal clinics, we are able to give a brief sensitization first off all on the human rights and after that they are able to see me or the pro bono lawyers present, we have managed to bring a team together to mobilize a team of pro bono lawyers in all the sites, the 15 sites and in some sites you will realize that maybe the lawyers in that area,,, you are not able to get a lawyer so we mobilize lawyers…as nearer as possible to those people in the 15 sites. So we are able to give one legal advice and for some of those cases which need to be taken up after the legal clinic the pro bono lawyers are able to take them up then they give us feedback we are able to follow up with them and we monitor them to see how far the cases have gone…

-The Zion site project manager describes the reasons for bringing in legal services to the Zion site. The focus on fighting stigma and discrimination has been a clear driving force in CHAK’s integration efforts and relates to conceptually incorporating the human rights principle of non-discrimination into their project’s objectives.

[PL: Zion Project Manager]: I think when it comes to human rights and since we are concentrating much and why we started this project to begin with as from the faith-based, was because we wanted to help people living with HIV/AIDS and to try to reduce the stigma that is there not just within the church but the whole society and why we also got involved as the church is because we believe that it is important for us, with the values that we have in the word of God, to come in and help people that are infected because according to our faith everybody has a value, everybody should be respected and be given the same opportunity. Many times when somebody is essentially positive it is more than just having the virus in the body.  It includes so much more, the whole social setup around them, the family, the relations kind of change when someone knows their fate and it is positive.  That is something that we have been working much with here, stigma reduction and especially through our support groups, trying to get our clients here to believe in themselves, believe that they have a future, believe that they are still worth something, that life has not come to an end and they are not hopeless. : What we are seeing among many of our patients especially single mothers is that they have been thrown out from homes, from their relatives, maybe from devastation they have been dying and the relatives are throwing them out saying they are cursed, a lot of traditional beliefs involved, and, of course, they feel hopeless and helpless. Many of them are illiterate therefore they also do not know that they have rights.  Maybe they do not have the opportunity to go and get some written legal aid somewhere to know that these are my rights, but they are just listening to the abuse from outside and they have been left on their own.

… That is why I thought that this programme was very good because many of these women have no clue of their rights especially when they are coming from a background of being rejected, maybe feeling that they are outcasts or cursed.  They need somebody to stand up and say, actually, you have some rights here, even if diseased, you still have some rights, so that they do not like give up and die and leave orphan children behind because that is also another thing.

-According to Zion’s Project manager, their clients predominantly seek legal aid for issues related to property, inheritance, sexual assault, and abuse.

Help with Legal Documents

-CHAK’s legal officer noted that the organization provides assistance with legal documents, mentioning land and succession documents as the main types.

INT: in terms of the services that people seek other than just seeking legal advice, do people seek help with legal documents and of what kinds?

[BC: Legal Officer]: yeah, from the legal clinics that I have attended people seek help with legal documents and the main ones I have seen are documents to do with land and documents to do with succession..

Formal Legal Representation

-CHAK assists clients in obtaining formal legal representation most often through networks of pro-bono lawyers. In some cases, pro-bono lawyers are present at the health facility as part of the legal aid clinics. In others, clients are referred to pro-bono lawyers located off-site. The legal officer describes one case that used pro-bono assistance (note this example is not from Zion or Naivasha evaluation sites).

[BC: Legal Officer]: In Maua we have one, during the clinic an old woman came to the clinic and her case was already in court. Initially she had engaged a lawyer but she was not able to pay him so the lawyer abandoned her case she heard we were coming she came to present her case. It was a succession case where her brothers in law had obntained letters of administration for her late husband’s estate without her knowledge. A probono lawyer took up the case during the legal clinic and has filed the case. Two hearings have taken place and we await the conclusion of the case.

Informal Conflict Resolution Mechanisms

- Both CHAK’s legal officer and Zion Project Manager described the kinds of informal resolution options clients receive at the family and community levels. Chiefs as well as local and religious leaders are seen as the first point of reference for basic mediation and are seen to play a key and often successful role in resolving certain disputes.

Successes and Persistent Challenges in Providing Legal Aid

-CHAK’s legal officer describes how the legal aid clinics have been successful in helping clients access legal services in general.

[BC: Legal Officer]: … there is some quite good progress which has been reported from the legal clinics I can also say that there is a lot of successes, because people have had problems and they sit with them because they are not able to afford legal fees or legal services even the consultations with the lawyers but through the legal clinics we are able to give them the opportunity to access these legal services for free and for some of those cases which are really burning the pro bono lawyers are ready to take them up.

-CHAK has support groups ,made up and led by patients and clients living with HIV/AIDS, across its sites. These groups are often the recipients of legal aid and human rights sensitization trainings. The structure of these support groups embodies the human rights principles of participation and non-discrimination. Support groups are run by CHAK’s patients and clients who are actively involved in making decisions about group activities. Moreover, CHAK’s focus on inclusion of people living with HIV/AIDS (PLWA) as support group members stems from their awareness about PLWA in Kenya and the stigma and discrimination they often face.

One major challenge with the support groups, according to CHAK’s legal officer, has been leadership among these groups, and this may be affecting the effectiveness of the legal integration efforts.

The financial capacity and commitment of pro-bono lawyers has been a major obstacle, as observed by CHAK’s legal officer.

[BC: Legal Officer]: The main challenge is with most this pro bono lawyers, most of them are people who are in private practice. So they really don’t have the motivation to offer services that and even during the legal clinics we have to give them incentives like transport or lunch.  When it comes to taking up cases and there are those filing fees and all, they are really not willing to go to that extent and we do not expect them to use their money to pay for filing fees. They can only provide legal aid to a client to a certain level because they also have their own clients to attend to. So they cannot do much pro bono work but they are trying, they are really trying.

In terms of informal conflict resolution, a major obstacle has been corruption and the refusal of local leaders to take up their presumed responsibilities to help community members who approach them with legal or formal documentation issues, for example, obtaining signatures for pension documents. Both CHAK’s Legal Officer and one trained client expressed the need to strengthen capacity of duty-bearers in the community.

Resources for Future Scale-up of Legal Integration

CHAK’s legal officer explained that much more financial and human resources are needed to scale-up the integration to additional sites. In particular, financial resources are needed to support the costs and time and effort that go into litigation. In addition, the legal officer noted that more resources are needed for information, education, and communication (IEC) materials. Human resources is also a big constraint and needs to be addressed if the project is to scale up.

INT: I understand there those, so in terms of scaling up and lessons learnt, what additional resources do you see yourself needing to continue providing legal services?

BC: of course we need financial resources, we will need additional financial resources, since as I said the legal clinics that we are doing now is a pilot, it’s not something which had been done in the previous two years and they have turned out to be very useful to the people of course we need more of those like even more than one clinic in an area within a certain period of time. As it is now we only do one clinic in a site, so like we will need more financial support to be able to roll out to more sites and also have more clinics. And then in light of these cases coming up the legal clinics, some of those cases need legal intervention in terms of them now going to court and we really don’t have funds to support that some of these people by virtue of their status they are not able to afford the legal fees, maybe the pro bono lawyers are not able to go an extra mile to pay for the filling fees. If we are able to get support, to get financial support for a few test cases, the few public interest litigation cases that would also be good.

iii. Process: Legal and/or Human Rights Trainings for Clients and Rights-Holders

-CHAK provides human rights sensitization trainings for patients at its various health facilities and for PLWA support groups. In training PLWA support groups, CHAK often conducts a training of trainers (TOT) for support group leaders who then are responsible for educating and sensitizing their fellow group members.

[BC: Legal Officer]: …all is training to build capacity on human rights, what human rights are, they are able to understand the kinds of human rights especially as people living with HIV and AIDS and we are also able to train them on the laws that protect their rights in the event that someone’s rights have been violated what law can they fall back on,

-One trainer from Zion site generally described a human rights training of community members, mostly recruited from PLWA support groups, that took place as part of a legal clinic in November 2009. This trainer works for a legal aid organization KITUO, which works with CHAK to run its human rights trainings and legal aid centers. The training focused on marriage law, succession law, gender, and its impact on HIV/AIDS.

After the training, feedback was obtained from trainees about what they learned from training, what was missing, as well as broader concerns relayed to CHAK. This is related to the human rights principle of participation though it is unclear whether trainees had

Combining Sensitization/Training with Legal Aid Provision

This training led to at least three cases being referred to various legal and community resolution mechanisms. This shows the model of combining legal aid clinic with trainings helps in getting legal challenges addressed. Zion’s (one of CHAKS project sites)  Project Manager also noted the importance of immediate follow-up after training to ensure clients have access to effective remedies. He made a case for combining trainings and sensitizations with legal aid provision or providing legal aid very shortly afterwards. One approach is to integrate legal aid into VCT days where individuals come for counseling and to pick up medications. In this manner, legal aid follow-up would be tied directly into the clinical follow-up process.

Client and Rights-Holder Training: Challenges for Scale-up

One trainer from Zion noted three challenges for future training: 1) that there was not enough time to provide all the information in the trainings;  2) trainings should be held in a more geographically accessible area; and 3) lawyers need to be given more notice in order to participate in the trainings. Perhaps the participation of trainees in the design of training can help address these and other challengers from the outset.

iv. Process: Legal and/or Human Rights Trainings for Service Providers

-CHAK provides human rights sensitization trainings to staff in its HIV/AIDS division, as well as in the malaria and TB divisions. It has carried out TOTs among health staff who then share this information with fellow service providers.

  - Additional Program Processes

Referral Systems

CHAK provides referrals to local authorities and supports the handling of cases at the community level where suitable as pursuing cases through the courts can be quite costly for clients.

In some cases, CHAK also refers clients to hospitals to deal with non-legal health issues.

Issues for Consideration- Legal Integration Processes For CHAK: -CHAK should consider strategies for strengthening the capacity community leaders in terms of knowledge and awareness of legal issues, rights and their roles as duty-bearers, as poor awareness could be posing a major obstacle to informal conflict resolution given observations local leaders have dismissed individuals approaching them for help with legal issues. The research team should keep in mind strategies to help do so. For Follow-up Evaluation: -Some of the interviews carried out diverged significantly from the protocols in the Baseline Evaluation Instruments. Follow-up data collection should aim to adhere more strictly to the semi-structured interview protocols and use follow-up and probing techniques to get a deeper understanding of relevant issues as they arise. -Follow-up evaluation should address IEC and Referrals as originally planned -The research team should further investigate the importance of combining training/sensitization with legal services or providing legal aid very shortly afterwards as an effective model for legal integration. Are clients more likely to act on information they just learned because a lawyer is immediately available versus having to retain that information and act in the long run?

d. Understanding Program Outcomes

This section presents data on the evaluation outcomes of interest from the qualitative interviews and FGDs carried out with CHAK staff and clients. The results are organized using the outcome components from the evaluation’s conceptual-logical framework (Annex II). Key findings are summarized and followed by supporting quotes from interviews and FGDs. The section concludes with a list of issues for consideration relevant to outcomes for CHAK and for the follow-up evaluation.

i. Changes in Knowledge of Clients/Rights-Holders About Human Rights

CHAK’s legal officer, while acknowledging that there is still a lot of work to be done, observed an increase in awareness about the human rights of PLWA among both CHAK clients and the community at large since the onset of legal integration.

She also observed an increase in demand of legal services. This is likely to be indicative of a broader increase in knowledge about rights and where to access legal services in the community.

Comparisons between Trained and Untrained Clients/Patients- Zion Site

- A number of PLWA who accessed Zion for medical care but were not part of support groups nor received legal training or aid (untrained) expressed some knowledge about rights presumably from other sources. However, there is no comparative data from Zion as there were no trained clients interviewed. Note that in this FGD many of the women did not speak and there was commotion regarding this which may have led to even less openness.

Comparisons between Trained and Untrained Clients/Patients- Naivasha Site

-When asked about their experience with rights, four Naivasha untrained clients/patients expressed basic understanding of rights violations faced by PLWA, with specific reference to stigma and discrimination encountered. In particular, stigma related to the misconception that the virus can be spread through sharing food and utensils was emphasized by two of the untrained client interviewees. [Note that these clients are part of CHAK support groups at the Naivasha site but have not received any human rights training or sensitization from CHAK.]

In the same interview, untrained clients were asked about their experiences with accessing redress or support after experiencing rights violations. The clients did not discuss seeking legal or other services but rather discussed more of their experiences living with HIV/AIDS. [Note more probing should have been done here.]. It appears that they have not had significant experiences accessing legal aid.

Interestingly, two of the interviewed untrained clients expressed a distrust of organizations using their stories to receive donor funds and then not providing them with services or support. This may contribute to apprehension in seeking redress for rights violations.

In comparison to untrained clients, trained clients from Naivasha, when asked about their experiences with human rights after training, described more detailed experiences with accessing rights and helping others learn about their rights seek redress.

[EW: Naivasha Trained Client]: The next issue came up, since my husband met me and then he looked for somebody else then he decided that the plot on which we are residing at Mai Mahiu should be up for sale and I had personally contributed to the purchase of that plot and I had to block the sale of the plot.  I did not have the documents, I did not have the title deeds they had been taken away but I was assisted by the local office of administration at Mai Mahiu, I called in the Assistant Chief, I consulted the Office of the Chief, they showed me the way forward and I blocked the sale of my plot.

[MN: Naivasha Trained Client] One day as I was coming from the training, one of my neighbours told me about a neighbor who was molesting her children. I was eager to know more, I was told that she had been married together with those children. I was also told that for three days she had tied the children in the house and they were in real pain. I did not hesitate and therefore decided to take action. I informed the community who later came and confirmed what was happening, I never informed the Chief because of his inertia. She was later imprisoned for three months but was released on finding that she was pregnant. Then her mother took the children in her custody.

-One trained client discussed the importance of spreading what they learned in CHAK trainings to other clients in support groups. This is a good  example of knowledge diffusion.

There is another problem in Maua whereby when they find out that you are positive, its not easy to get employment and if you are employed and they find out, there is a possibility of being sacked. During our support group meeting, I informed them that they had a right to work and therefore anyone who may be sacked due to being positive, need to take action. I also took the training on human rights to churches where I told them of my story and hoped that such a thing will not happen to them after undergoing the training.  Most of them appreciated the training for they were now aware of their rights.

ii . Changes in Knowledge of Service Providers About Human Rights

Comparisons between Trained and Untrained Service Providers- Naivasha Site

-All three interviewed untrained service providers working at Naivasha hospital expressed basic knowledge of rights and stigmatization faced by PLWHA, but counseling or other application of rights to their day to day work appears limited. One mentioned the “right to choose whether to take medication”, which although not a human right in and of itself, can be closely related to the right to health. The same interviewee also recognized the rights to confidentiality and information for patients. Another interviewee specifically mentioned the “right to dignity”.

[JL: Naivasha Untrained Service Provider]:  I have not had any official training or session on this, but my own understanding is just like every other human being has rights and this is now trying to bring it to the context of HIV/AIDS in which people brought here are stigmatized or segregated against on the grounds of their HIV status which really should not be the case, so I really do not know to what extent I would explain that as in regards to my patients because I never relate to them in the context of are your rights being respected, except for the few extreme cases that come in and say, since I came here probably we get to diagnose them here and they come back sometimes and say I have heard some new things happening at home because since I knew my HIV status I am being looked at in a different way or I am being treated differently either at work and at home.  So except those few cases most of which we do not have much to do other than to counsel them and maybe refer them to seek legal assistance, I have not related with them in a much bigger sense in the area of human rights.

Overall the untrained providers recognize that patients have rights and that they face a range of legal and social problems which need to be addressed. In terms of being able to help patients with legal needs and human rights issues, one untrained service provider noted that referral guidelines for those who need legal aid beyond were unclear and seem to be a limiting factor in terms of service provision. They also perceived the legal system to be difficult to work with because the process is lengthy.

-Much of the trained service provider interview recording was inaudible so the information is limited for this reason. Two trained service providers expressed knowledge about specific rights- the right to confidentiality, right to non -discrimination in employment, in education, in marriage, the right to found a family and bear children.

[PM: Naivasha Trained Service Provider]:(inaudible).  We told them whether they are HIV positive or not they have their own rights and have the right to have children, to get married. Before it was like HIV positive patients or clients are not supposed to bear children.  Now we are telling them they have that right. We tell them they have the right to education and so on.

Trained service providers also seemed to recognize the different formal and informal avenues for referring patients, depending on the case while one trained service provider from Naivasha observed that ultimately not very many health workers or patients are getting information on human rights.

iii. Additional Program Outcomes

Improved Service Provision

-CHAK’s legal officer observed a synergy between providing medical and legal services that could be leading to better information and advice provided at health facilities and as a result empowering patients/clients. Presumably this is a result of health workers now being able to provide legal and other non-medical advice to help patients/clients deal with legal and social problems thereby leading to their empowerment.

Changes in Protection and Redress for Human Rights Violations

Zion’s community trainer alluded to examples of where individuals pursued legal cases with the help of CHAK’s integration program. However, details in terms of the final outcome of the case are still unclear. A qualitative case review should be considered.

Improved Satisfaction With Services: Client Satisfaction Forms, Zion Site

-Client satisfaction forms from the Baseline Evaluation Instruments were administered to 15 relatively new clients at CHAK’s Zion site with the help of two translators. The form asked clients which services they received that day and to rate eight categories related to their experience at Zion on a four-point scale (1=weak, 2=fair, 3=good, 4=excellent). The various categories included: attitude, time, information, service, expertise, confidentiality, action, and benefit.

- Two-thirds of clients surveyed were female (10), while the remaining five clients were male. The clients ranged between 25 years old and 70 years old, although one client expressed uncertainty about her age. Eighty percent of clients were present to pick up medication and 73% of clients attended an informational empowerment meeting, which takes place each Tuesday. A few clients also received some other services; two clients received a CD4 test, one picked up test results, and one other client followed up with a clinical officer.

The results are inconclusive because the client satisfaction form has not yet been administered to clients accessing integrated services. This task should be pursued during the follow-up phase. According to CHAK staff, long-term or established clients access the site on Saturdays- the research team should consider carrying out the survey with these persons as they would provide a good comparison group to these baseline results.

Issues for Consideration- Program Outcomes CHAK should consider building in follow-up case data into its routine records to quantify case outcomes, settled and resolved disputes etc. This will help improve future M&E. For Follow-up Evaluation: Some of the interviews carried out diverged significantly from the protocols in the Baseline Evaluation Instruments. Follow-up data collection should aim to adhere more strictly to the interview protocols and use follow-up and probing techniques to get a deeper understanding of relevant issues as they arise. The research team should consider carrying separate follow-up interviews and FGDs for men and women at the community level as gender dynamics seemed to prevent the women in one group from speaking. The follow-up evaluation should assess the outcomes Improved Service Provision, Improved Satisfaction with Services as originally planned. The evidence for change in knowledge and awareness among trained clients has been collected for Naivasha. A trained client interview should be carried out in the Zion site to compare with the baseline control group. The evidence for change in knowledge and awareness among trained service providers has been collected for Naivasha. The research team should attempt to recover missing pieces of the trained provider interview transcript. The research team should carry put trained and untrained service provider interviews for Zion as was done in Naivasha. The research team should administer the client satisfaction forms at Zion site on a Saturday, when long-term clients attending support groups and pick up their medication, so that the differences in ratings between those trained and untrained could be identified within Zion. This could reveal the impact that human rights training has on the client’s satisfaction with the clinic as well as his/her awareness. In particular, ratings for the “Information,” “Service,” and “Expertise” categories should be monitored, since an awareness of human rights could impact a client’s perception of Zion’s ability to respond to these services. The research team should further explore the issue of clients distrust of organizations using their stories to receive donor funds and then not providing them with services or support. The research team should re-explore the feasibility of carrying out the client satisfaction forms at the Naivasha site as well as other organizations in this evaluation. -CHAK has very limited records of improved protection and redress that could be quantified to show how many cases were resolved or settled. The follow-up evaluation should undertake a qualitative case review where a few select cases are explored in great detail to provide case evidence of how cases are ultimately dealt with.

## e. CHAK- Summary of Issues for Consideration

This section summarizes all of the issues for consideration emerging from the above analysis of CHAK data.

Issues for Consideration- Quantifying Legal Service Provision and Referral For CHAK: -CHAK should consider monitoring trends in access to justice by sex, age, and other categories as determined relevant by program staff. This could potentially be done with attention to traditional factors of discrimination such as socio-economic status, sex, age, religion, ethnicity, geographic region, etc. It is worth noting here that even simple age and demographic information for clients was not always documented on the client case forms. -CHAK should consider more consistent recording of case outcomes in client case files as they occur. For Follow-up Evaluation: -The research team should follow-up yet again with Zion site to see if any records exist as it was verified in the qualitative interviews that they do exist. -The research team should update the analysis of CHAK-Naivasha client case records for missing dates in order to quantify time trends in legal service provision and referral Issues for Consideration- Legal Integration Processes For CHAK: -CHAK should consider strategies for strengthening the capacity community leaders in terms of knowledge and awareness of legal issues, rights and their roles as duty-bearers, as poor awareness could be posing a major obstacle to informal conflict resolution given observations local leaders have dismissed individuals approaching them for help with legal issues. The research team should keep in mind strategies to help do so. For Follow-up Evaluation: -Some of the interviews carried out diverged significantly from the protocols in the Baseline Evaluation Instruments. Follow-up data collection should aim to adhere more strictly to the semi-structured interview protocols and use follow-up and probing techniques to get a deeper understanding of relevant issues as they arise. -Follow-up evaluation should address IEC and Referrals as originally planned -The research team should further investigate the importance of combining training/sensitization with legal services or providing legal aid very shortly afterwards as an effective model for legal integration. Are clients more likely to act on information they just learned because a lawyer is immediately available versus having to retain that information and act in the long run? Issues for Consideration- Program Outcomes For CHAK: --CHAK should consider building in follow-up case data into its routine records to quantify case outcomes, settled and resolved disputes etc. This will help improve future M&E. For Follow-up Evaluation: - Some of the interviews carried out diverged significantly from the protocols in the Baseline Evaluation Instruments. Follow-up data collection should aim to adhere more strictly to the interview protocols and use follow-up and probing techniques to get a deeper understanding of relevant issues as they arise. - The research team should consider carrying separate follow-up interviews and FGDs for men and women at the community level as gender dynamics seemed to prevent the women in one group from speaking. -The follow-up evaluation should assess the outcomes Improved Service Provision, Improved Satisfaction with Services as originally planned. -The evidence for change in knowledge and awareness among trained clients has been collected for Naivasha. A trained client interview should be carried out in the Zion site to compare with the baseline control group. - The evidence for change in knowledge and awareness among trained service providers has been collected for Naivasha. The research team should attempt to recover missing pieces of the trained provider interview transcript. -The research team should carry put trained and untrained service provider interviews for Zion as was done in Naivasha. -The research team should administer the client satisfaction forms at Zion site on a Saturday, when long-term clients attending support groups and pick up their medication, so that the differences in ratings between those trained and untrained could be identified within Zion. This could reveal the impact that human rights training has on the client’s satisfaction with the clinic as well as his/her awareness. In particular, ratings for the “Information,” “Service,” and “Expertise” categories should be monitored, since an awareness of human rights could impact a client’s perception of Zion’s ability to respond to these services. -The research team should further explore the issue of clients distrust of organizations using their stories to receive donor funds and then not providing them with services or support. -The research team should re-explore the feasibility of carrying out the client satisfaction forms at the Naivasha site as well as other organizations in this evaluation. -CHAK has very limited records of improved protection and redress that could be quantified to show how many cases were resolved or settled. The follow-up evaluation should undertake a qualitative case review where a few select cases are explored in great detail to provide case evidence of how cases are ultimately dealt with.