## Instructions
GLOBAL PARTNERSHIP FOR SOCIAL ACCOUNTABILITY (GPSA) Grantee Application: Results Framework and Monitoring
Instructions:
Please read these instructions before filling out your proposal’s Results Framework (RF) included under Tab 2. You should also review Tab 3, which includes GPSA’s Results Framework. Please note that you are NOT required to use any of the specific outcomes or indicators as defined in the GPSA's Results Framework [see Tab 3: GPSA RF]. The latter is provided for guidance purposes only insofar as the proposal should reflect GPSA's pillars of good governance.
If you need additional guidance, you can find more information about designing a results framework in the GPSA’s website under Resources.
For the Proposal's Results Framework, you must provide the following information:
--Project-level outcomes and outcomes indicators
--For each Component included in your proposal, intermediate outcomes, outcomes indicators, outputs and outputs indicators.
--Based on the RF proposed, you will have to describe the proposal's Monitoring and Evaluation (M&E) Plan in Section 4 of the e-application, which includes the following questions [please note that these questions must be answered IN the e-application, NOT here]:
Please describe the proposal’s monitoring system, including the specific methods and tools that will be used. Justify how the proposed methods and tools are adequate to the problem(s) being addressed by the project. What resources will be needed to rollout and implement the monitoring system? E.g. financial, human, technical, use of ICTs, etc. Will external support be needed? If yes, please explain. Please make sure to address all these questions.
Describe the intervention’s evaluation methods. Why are these adequate to evaluate the intervention’s expected intermediate and final outcomes? What resources will be needed to design and implement the proposed evaluation(s) Will external support be needed? If yes, explain. Please make sure to address all these questions.
The numbers below correspond to the references included in the Results Framework tables [see Tab 2: Proposal RF] that you must fill out:
[1] Insert Project Strategic Objectives as defined in question 2.1 of the online application. For each Component, insert the component’s title as defined in the online application.
[2] Insert the definition of the Project Level Outcomes. These outcomes should derive from the definition of your Project’s strategic objectives. Please focus on key outcomes only, which will reflect the Project’s overall achievements. Outcomes are the specific changes in project participants’ behavior, knowledge, skills, status and level of functioning; they should be defined in a SMART way: strategic, measurable, action-oriented, realistic, and timed.
For each Component, insert the definition of Intermediate Outcomes: these outcomes are attributable to each component, and would contribute to the achievement of intermediate and final outcomes at the Project level. An intermediate outcome specifies a result proximate to an intended final outcome, but likely more measurable and achievable in the lifetime of a project to an intended final outcome. To ensure the accuracy of assigned intermediate outcomes, the consideration of each proposed outcome should include reviewing who is best situated to achieve the outcome (that is, is this within or outside the scope of this intervention?) and how the outcome might be effectively measured. Example: Teachers use the new teaching methods (output/intermediate outcome) to improve learning among students (final outcome).
[3] Project-level Outcome Indicators and Component-Level Outcome Indicators. Strategic objective(s) and intermediate outcomes reflect constructs that need further definition to be measured. These outcomes need to be translated into a set of measurable indicators to establish whether progress is being achieved. Indicators are tied to results by focusing on one or more characteristics of the outcome. A measure then expresses an indicator’s value quantitatively or qualitatively using SMART criteria:
Specific. Indicators should reflect simple information that is communicable and easily understood.
Measurable. Are changes objectively verifiable?
Students’ learning achievement
Percentage of customers who are satisfied with the availability of potable water or electricity
Achievable. Indicators and their measurement units must be achievable and sensitive to change during the life of the project.
Relevant. Indicators should reflect information that is important and likely to be used for management or immediate analytical purposes.
Time bound. Progress can be tracked at a desired frequency for a set period of time.
Where possible, measurement strategies should be based on existing data sources or tested data collection methodologies. Relevant information for analysis and aggregation could already be available through administrative databases or through sample or census-based surveys. Before specific indicators are defined for desired outcomes, practitioners should identify data sources that could be used to measure desired changes.
The following considerations will help guide this process:
An objective or intermediate outcome could need more than one indicator to measure both its qualitative and quantitative aspects.
A minimal number of indicators should be selected. More information is not necessarily better. A common problem with results frameworks and performance measurement systems is that they are tied to a large set of indicators that are burdensome to track.
There is no correct number of indicators to assign per outcome, but the following are useful questions to ask:
Is this indicator absolutely necessary to measure whether progress toward the strategic objective is being achieved?
Will it create additional burdens on the respondents or on the staff collecting the data?
How will this indicator help with monitoring, management, and evaluation?
Having multiple stakeholder opinions on the design of the results framework provides an opportunity for discussion and eventual consensus on what good indicators and measures are and what number of indicators will suffice.
Proxy indicators can be used as indirect measures of achievement when direct measures are difficult to assign. For example, where tests of student achievement have not been systematically applied to assess education quality, a proxy measure might focus on student completion rates. Such proxy indicators must be assigned carefully; a common threat to the validity of results measurement is the use of inadequate proxy indicators (for example, students’ self-reported levels of achievement in mathematics).
Indicators assigned in the design of a results framework might be modified during implementation, as data capacity increases and new data elements become available.
[3. A] Component-level Outputs and Output Indicators. For each Component, follow the above guidance to define outputs and output indicators. Outputs are the direct products of project activities and may include types, levels and targets of services to be delivered by the project. The key distinction between an output (a specific good or service) and an outcome is that an output typically is a change in the supply of goods and services (supply side), while an outcome reflects changes in the utilization of goods and services (demand side)
[4] – [10] Project Monitoring Plan
The next step in designing a results framework is to plan how it will be operationalized to monitor progress and assess the effects of interventions. The plan for monitoring performance typically lists the following elements in a complementary tool, the monitoring plan:
[5] & [6] Baseline and target values for selected measures to provide the means for verification to measure changes in the indicators. It is important to remember that the construction of baseline values can be based on available secondary data sources, which can be improved or sharpened through subsequent work. Delaying the preparation of an intervention until a “perfect” baseline is available is rarely feasible or desirable. At the same time, the absence of a baseline too often indicates that the problem definition stage of intervention design is being conducted on the basis of either conventional wisdom or untested assumptions.
For [6] Target values should be entered for the years data will be available, not necessarily annually.
[7] Frequency or designated intervals at which the data will be collected or provided.
[8] Data sources or methods for data collection.
[9] The agent(s) responsible for collecting or providing the data (for example, independent evaluation team, project staff, and so forth).
[10] Assumptions and risks associated with the indicators or information being collected (such as the assumption that data will be available from a second party).
[11] Core: please mark if any of the outcome indicators are the same as any of those included in the list of outcome indicators used by the GPSA’s Results Framework to measure results at the Program Level. This information is useful for analysis purposes only by the GPSA. Leave blank if not applicable.

## 2. Proposal RF
Global Partnership for Social Accountability (GPSA)
Proposal Results Framework
PROJECT LEVEL RESULTS
Project Title | Transformation of Unions for Equality (TRUE)
Project's Strategic Objectives [1] | To enhance social accountability at UP level to promote transformative governance practices.
Project Level Outcomes [2] | Project level Outcome Indicators [3] | Unit of Measure [4] | Baseline [5] | Cumulative Target Values [6] |  |  |  |  | Frequency [7] | Data Source/ Methodology [8] | Responsibility for Data Collection [9] | Assumptions and Risks [10] | Core [11]
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Outcome 1: 20 UPs accelerate their open budget processes through citizen-led collective initiative. | Increase in open budget index (open budget survey) of UPs | Score | not available [to be determine during B/L Survey] | B/L | 15% increase from the B/L | 40% increase from the B/L | 60% increase from the B/L | 75% increase from the B/L | annually | Open budget index (open budget survey based on UP operation manual) of UPs will be designed and assessed during B/L, which will be measered and compared annually. | Project M&E | 1. Local government reforms remain in place and UP authorities are empowered to liaise with citizens' groups.
Outcome 2: Poor and vulnerable women & men in target UPs increased their resiliency through greater access to livelihood information, entitlements to natural resources and safety nets | % of women & men are aware and exercise their rights within the RTI framework | % | not available [to be determine during B/L Survey] | B/L | 20% increase from the B/L | 35% increase from the B/L | 50% increase from the B/L | 60% increase from the B/L | annually | sample survey | Project M&E | 1. Appellate authority & Information Commission continued effective at the local level
Outcome 3: UTTARAN developed effective knowledge management and learning system for contineous transformation of transperency and accountability in UP planning | Increase in SAcc related organisat'nal capacity scores of Uttaran | Score | 50% available | 50% increase from the B/L | 100% increase from the B/L | 100% increase from the B/L | 100% increase from the B/L | 100% increase from the B/L | annually | Org. capacity of SAcc Score of Uttaran will be designed and measured during B/L, which will be annually assessed and compared. | Project M&E | 1. Uttaran retains capable staff and assistance with operational/HR resource planning 2. donors remain cooperative
RESULTS BY COMPONENTS
COMPONENT 1 [1]: Community Social Accountability (SAcc) Mechanism
Intermediate Outcomes [2] | Outcome Indicators [3] | Unit of Measure [4] | Baseline [5] | Cumulative Target Values [6] |  |  |  |  | Frequency [7] | Data Source/ Methodology [8] | Responsibility for Data Collection [9] | Assumptions and Risks [10]
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Citizens able to effectively engage in UP budget processes | Increase in SAcc Index scores of the UPs | Score | not available [to be determine during B/L Survey] | B/L | 25% increase from the B/L | 50% increase from the B/L | 70% increase from the B/L | 85% increase from the B/L | annually | SAcc index combining transparency, participation & accountability of UPs will be designed and assessed during B/L, which will be measered and compared annually. | Project M&E | Govt. continued UP chairperson and members capacity building through various project
IO 2: Increased demand by the citizens' for pro-poor and gender equitable UP annual budget planning and implementation | numbers of interventions at the Upa-zila, district and national level made for change | number of interventions | to be determined at B/L and project implementation plan | at least five interventions | at least fifteen interventions | at least thirty interventions | at least forty interventions | at least fifty interventions | annually | media reports, monitoring systems, intervention report, impact study | Project M&E | government remains tolerant of civil society/citizens' activity
Add more
Planned Outputs [3.A] | Output Indicators [3.A] | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: 25 Citizens’ Committees (CC) and their 3 upward Apex Federartions (AF) formed and enhance awarness & engagement in 25 UPs in the project areas. | ## of CC & AF formed, ## of trainings & awarness activities, | number | not available | 25 CC | 28 CC & AF; | 28 CC & AF; | 28 CC & AF; | 28 CC & AF; | Continuous | project monitoring system, | Project M&E | local government reforms remain in place and UP officials are empowered to liaise with citizens'/cvil society groups
Output 2: Advice and Information Centres (AIC) provide information, training and advisory services on governance-related issues resilience livelihood information to citizen groups to CC and AF: act as a conduit for information from the community/citizens groups and UPs. | ## of AICs functioning, information from AICs used in challenges to UP/GoB officials at the local level. | number | not available | 3 AICs | 3 AICs | 3 AICs | 3 AICs | 3 AICs | Continuous | AIC report, FGD with users | Project M&E
Output 3: Multi-stakeholder dialogue and collaboration by linking CCs & AFs with governments, academics, media and practitioners | ## of dialogues, collaboration & linkage established | numbers | not available | 28 | 84 | 140 | 196 | 252 | Continuous | reports on dialogues, collaboration and linkage building events, FGD/interview with users | Project M&E
Add more
COMPONENT 2: Promote Citizens' rights to information (RTI)
Intermediate Outcomes | Outcome Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Citizens in the project areas are aware about their rights to information | % of population can articulate the basic RTI issues | % of population | not available [to be determine during B/L Survey] | 20% increase from the B/L | 80% increase from the B/L | 100% increase from the B/L | 100% increase from the B/L | 100% increase from the B/L | annually | sample survey | Project M&E
IO 2: Citizens in the project areas use ICT to get information on their entitelments and services | % of population use ICT to access information | % of population | not available [to be determine during B/L Survey] | 25% increase from the B/L | 75% increase from the B/L | 100% increase from the B/L | 100% increase from the B/L | 100% increase from the B/L | annually | sample survey | Project M&E
Add more
Planned Outputs | Output Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: UPs and citizen groups developed greater awareness on RTI framework | ## of RTI awarness informations | number | not available | 450 | 900 | 1350 | 1800 | 2250 | Continuous | intervention report | Project M&E
Output 2: 50 Community Information Volunteers (CIV) provide information assistance to the community people | ## of Information volunteers & their service | number | not available | 50 | 50 | 50 | 50 | 50 | Continuous | Volunteers services | Project M&E
Output 3: Citizens demand information and services from the respective duty bearers under the framework of RTI | ## of claimed submited | number | not available [to be determine during B/L Survey] | 20% increase from the B/L | 75% increase from the B/L | 100% increase from the B/L | 120% increase from the B/L | 150% increase from the B/L | Continuous | information officers of the services providers/duty bearers | Project M&E
Add more
COMPONENT 3: Knowledge & themetic capacity building of Uttaran on SAcc
Intermediate Outcomes | Outcome Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Uttaran build RTI compliance capacity. | increase in organisational capacity score | score | 20% available | 25% increase from the B/L | 75% increase from the B/L | 100% increase from the B/L | 120% increase from the B/L | 150% increase from the B/L | annually | org. capacity score on RTI for Uttaran will be designed and assessed during B/L, which will be measered and compared annually. | Project M&E | Uttaran will be able to hire and retain competent staff.
IO 2: Uttaran mainstream SAcc across its project/programme portfolio | ## of mgt. decision made & implemented by Uttaran ensuring SAcc at various level. | number | not available [to be determine during B/L Survey] | 2 | 5 | 8 | 12 | 15 | annually | SAcc indicators to achieve by Uttaran will be determined during Project implementation planning which will be subsequently monitored. | Project M&E | Donors will provide required fund for establishing SAcc mechanisam
Planned Outputs | Output Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: Uttaran develop short and long term plan and strategis to establish SAcc mechanisam both at the org. and community level. | process & output of Uttaran's short & long term plan & strategis for SAcc | plan & strategy - quality, output & implementation | not available | plan & strategies with target developed through a process | achieve the target made in the plan & strategy | achieve the target made in the plan & strategy | achieve the target made in the plan & strategy | achieve the target made in the plan & strategy | six-monthly | monitoring indicators and targets as agreed on the plan and strategy. Organisational data | Project M&E
Output 2: A technology based information communication & sharing system establish in Uttaran | plan & implementation of system establishment | progress of plan implemenntation | not available | plan with target developed. | target achievement against plan | target achievement against plan | target achievement against plan | target achievement against plan | six-monthly | monitoring indicators and targets as agreed on the plan. Organisational data | Project M&E
Output 3: Staff capacity enhanced in SAcc and RTI | Staff participated in capacity enhancement initiatives (SCHI) | quality & number of staff capacity enhancement initiatives (SCEI) | not available [to be determine during B/L Survey] | staff : 25, SCEI : 3 | staff : 35, SCEI : 6 | staff : 35, SCEI : 8 | staff : 35, SCEI : 10 | staff : 35, CEI : 12 | reguler | CEI reports, FGD/interview with staff, staff performance apprial. | Project M&E
COMPONENT: KNOWLEDGE & LEARNING
Intermediate Outcomes | Outcome Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Organisational, national and internationally SAcc intervantion strategies influenced have been by the project experience, learnings and knowledge. | MoLG&C & other national/inernational policy makers recognise issues emerges from the intervention | number of knowledge products developed, experience & learnings sharing events | not available | 1 | 3 | 5 | 8 | 11 | annually | project/event report, interviews, national/ inernational policy docs | project M&E | policy makers are willing to value/recognise grassroots’ knowledge/experience
IO 2: Project adopt from and contributed to GPSA KP learnings and knowledge | participated/ jointly undertaken GPSA KP activities | ### of participated/ jointly undertaken GPSA KP activities | not available | 2 | 5 | 7 | 10 | 13 | annually | project/event report, interviews, GPSA reports/docs | project M&E | GPSA KA effectively implemented as designed
Planned Outputs | Output Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: research, studies and other knowledge mateial on SAcc | peer reviewed research studies and knowledge materials | ### of peer reviewed research studies and knowledge materials | not available |  | 1 |  | 2 |  | annually | project reports, research, studies and knowledge materials | project M&E
Output 2: Functional linkage and network established with GPSA KP | GPSA KP recognise and value relationship, linkage & network with Uttaran | qualitative assessment | not available | relationship, network & linkage esablished with GPSA KP | continued effective relationship, network & linkage with GPSA KP | continued effective relationship, network & linkage with GPSA KP | continued effective relationship, network & linkage with GPSA KP | continued effective relationship, network & linkage with GPSA KP | annually | project report, evaluation, interview and communications, | project M&E | GPSA KA effectively implemented as designed
Note on A8: These outcomes should derive from the definition of your Project’s strategic objectives. Please focus on key outcomes only, which will reflect the Project’s overall achievements. Outcomes are the specific changes in project participants’ behavior, knowledge, skills, status and level of functioning; they should be defined in a SMART way: strategic, measurable, action-oriented, realistic, and timed.
Note on A16: For each Component, insert the component’s title as defined in the online application.
Note on A59: Required Component for all Application

## 3. GPSA RF
GPSA: Results Areas, Indicators and Sources of Information
A. Results Areas
GPSA is structured in four “results areas”, which correspond to its “governance pillars”.
1) Transparency: people able to access and use information on government activities
2) Representation and voice: people have mechanisms and/or policies through which they can engage in government processes.
3) Accountability: governments are more accountable to beneficiaries in service delivery and in management of public resources.
4) Learning for Improved Results: improved knowledge and practice of social accountability.
The first three areas can be considered as a menu from which GPSA might want to draw from without having to cover each area in every country. The specific results will need to be tailored to each country context.
These results areas are presented in GPSA’s “theory of change” as (intermediate) outcomes. The diagram also shows critical assumptions and the pathways from resources to impacts, including development results to which GPSA may contribute but that cannot be attributed only to it. The critical assumptions can also be used as a key input for risk management.
In order to operationalize the results framework it is necessary to identify a set of indicators corresponding to the different levels of the “results chain” (except the higher level corresponding to development results) included in the “theory of change” (TOC). This is done below, making use as much as possible of existing indicators and available data sources, as well as those that can be constructed using data that will be generated by GPSA’s operations. It should be noted that whereas the indicated outputs are fully dependent on GPSA (and therefore GPSA is accountable for achieving them), the outcomes and impact depend crucially on the role of other interventions and exogenous factors. Furthermore, the links between outputs and outcomes, as well as between outcomes and impact, are covered by other WB initiatives (such as those under the Governance & Anticorruption -GAC -strategy), as well as by research projects.
Finally, complementing the general key assumptions included in the TOC diagram, the following are additional assumptions concerning what leads from one stage to another:
from activities to outputs: the knowledge component activities (1-3) will help to establish a global platform for knowledge exchange and research (output 1), assuming that CSOs would be interested to participate in such a platform; knowledge on effective SAcc interventions for different contexts would result from the implementation of activities (1-3) assuming that a M&E system (along the lines further described in the GPSA Results Framework, Draft Concept Note, see GPSA website) is fully functional.
from outputs to outcomes: activities supporting the enabling environment for SAcc (4) combined with capacity building activities (2) and outputs (1), (2) and (3) would lead to outcomes (1-4) assuming that the knowledge generated and disseminated is relevant, that governments would be willing, or sufficiently pressured, to undertake governance reforms and to become more accountable; it is also assumed that SAcc capacity building activities will be effective.
from outcomes to impact: outcomes (1-4) would contribute to improved service delivery and development effectiveness assuming that demand pressure on government services resulting from the achievement of those outcomes would lead to enhanced quality of government services and to greater development effectiveness.
On this last set of links, there is evidence from research and ongoing work by (among others) the World Bank GAC strategy, as well as on the work leading to (and spawned by) the 2004 World Development Report (“Making Services Work for Poor People”). On ii), the evidence is thin, and GPSA can and should contribute to it.
B. Indicators and sources of information
Given that GPSA will operate at the global, country and project level, the results framework includes indicators corresponding to these three levels. The indicators are focused on quantitative aspects, which would be complemented by the qualitative information to be provided by the activities indicated in the section on M&E.
Global level
This level is basically related to the fourth results area, i.e., “Learning for improved results”, which at the global level boils down to the generation of the global public good of knowledge on social accountability. Furthermore, aspects related to GPSA as a whole are also included in this level.
Country level
There is an abundance of data sources corresponding to different aspects of SAcc at the country level, such as Governance-at-a-Glance and Demand for Good Governance indicators (AGI Data Portal), WBI’s CDR, the Open Budget Index, Afrobarometer, Latinobarometro, for IDA countries the last of the CPIA criteria, i.e., “Transparency, Accountability, and Corruption in the Public Sector”, IEG (World Bank Independent Evaluation Group) GAC country data , World Bank indicators developed for GAC-II on government openness; CPARs (Country Procurement Assessment Reviews), WBI Worldwide Governance Indicators and the Open Transparency Index.
The tables presented further below select among these sources those which are more adequate given their periodicity and coverage. However, in specific country cases, some of the other sources mentioned above may also be suitable. Furthermore, there are countries where local sources of data on transparency are available. These sources can be tapped particularly in the elaboration of country or thematic case studies, as indicated in the section on M&E.
Project level
Each project/ grant funded by GPSA should indicate in their applications the result area(s) to which it expects to contribute, targets for its outputs specifying their timeframe, the set of activities in which they plan to use the resources provided by GPSA, the links between activities' outputs and outcomes, the current levels of these variables (which will be the baselines) and their implementation strategy. GPSA could develop a web based application that projects/grants could (and should) utilize for their own management and monitoring as well as to feed GPSA’s monitoring and reporting. This would be a sort of self-organizing system, minimizing the time needed from GPSA’s Secretariat.
An important source of information will be the records of activities supported by GPSA. Therefore, it is necessary to ensure that the designs of grants/activities to be funded by GPSA indicate clearly their output and outcome indicators before they are approved, as indicated in the preceding paragraph, and that they complete the collection of baseline data (complementing the data presented in the application form, if need be) during their first 6 months of operations. During the first three months of operations, formats for reporting results and data should be established, and to assure the quality of self-reported data the reports will be systematically reviewed by peer organizations and/or GPSA staff.
GPSA Program-Level Outputs and Outcomes Indicators (Sample Draft - under revision):
C. Outcome indicators and case studies
As indicated in the preceding tables, for some indicators the source of information will be case studies (country and thematic). These case studies could complement the information provided by indicators with an analysis and synthesis of a set of issues such as the following: the extent to which Civil Society (CS), government and other stakeholders have improved knowledge and capacity to harness social accountability for better development outcomes; the degree to which Citizens are engaged in monitoring of service delivery and public resource management; the extent to which Citizens’ priorities are reflected in policy and decision-making (looking at levels of engagement and where this has changed policy and practice), and the extent to which government authorities value the participation of citizens in achieving effective service delivery; participation of CS in public policy discussions; use by CS of grievances mechanisms and collective action behaviour induced by GPSA’s supported CSOs and development by CSOs supported by GPSA of associations representing CS.
D. Performance indicators
In addition to the indicators shown in the above tables, the following indicators are proposed (to be reported on annual bases, using GPSA’s records)to assess GPSA's performance:
1. number of partners involved;
2. number and amount (disbursed) of grants
3. number of mentoring grants,
4. number of countries that opted-in
5. number of grant applications
6. number of CSOs which GPSA supported
E. Dissemination Strategy and Knowledge Sharing to facilitate use and decision making
The results framework can be used to communicate the progress and problems in achieving results. One way of presenting results is through a “dashboard,” highlighting the key high-level objectives and outcomes/outputs achieved, using the framework for planning and review meetings (with the current status of the indicators highlighted), and using the change in the indicators from baseline to highlight the results.