## Instructions
GLOBAL PARTNERSHIP FOR SOCIAL ACCOUNTABILITY (GPSA) Grantee Application: Results Framework and Monitoring
Instructions:
Please read these instructions before filling out your proposal’s Results Framework (RF) included under Tab 2. You should also review Tab 3, which includes GPSA’s Results Framework. Please note that you are NOT required to use any of the specific outcomes or indicators as defined in the GPSA's Results Framework [see Tab 3: GPSA RF]. The latter is provided for guidance purposes only insofar as the proposal should reflect GPSA's pillars of good governance.
If you need additional guidance, you can find more information about designing a results framework in the GPSA’s website under Resources.
For the Proposal's Results Framework, you must provide the following information:
--Project-level outcomes and outcomes indicators
--For each Component included in your proposal, intermediate outcomes, outcomes indicators, outputs and outputs indicators.
--Based on the RF proposed, you will have to describe the proposal's Monitoring and Evaluation (M&E) Plan in Section 4 of the e-application, which includes the following questions [please note that these questions must be answered IN the e-application, NOT here]:
Please describe the proposal’s monitoring system, including the specific methods and tools that will be used. Justify how the proposed methods and tools are adequate to the problem(s) being addressed by the project. What resources will be needed to rollout and implement the monitoring system? E.g. financial, human, technical, use of ICTs, etc. Will external support be needed? If yes, please explain. Please make sure to address all these questions.
Describe the intervention’s evaluation methods. Why are these adequate to evaluate the intervention’s expected intermediate and final outcomes? What resources will be needed to design and implement the proposed evaluation(s) Will external support be needed? If yes, explain. Please make sure to address all these questions.
The numbers below correspond to the references included in the Results Framework tables [see Tab 2: Proposal RF] that you must fill out:
[1] Insert Project Strategic Objectives as defined in question 2.1 of the online application. For each Component, insert the component’s title as defined in the online application.
[2] Insert the definition of the Project Level Outcomes. These outcomes should derive from the definition of your Project’s strategic objectives. Please focus on key outcomes only, which will reflect the Project’s overall achievements. Outcomes are the specific changes in project participants’ behavior, knowledge, skills, status and level of functioning; they should be defined in a SMART way: strategic, measurable, action-oriented, realistic, and timed.
For each Component, insert the definition of Intermediate Outcomes: these outcomes are attributable to each component, and would contribute to the achievement of intermediate and final outcomes at the Project level. An intermediate outcome specifies a result proximate to an intended final outcome, but likely more measurable and achievable in the lifetime of a project to an intended final outcome. To ensure the accuracy of assigned intermediate outcomes, the consideration of each proposed outcome should include reviewing who is best situated to achieve the outcome (that is, is this within or outside the scope of this intervention?) and how the outcome might be effectively measured. Example: Teachers use the new teaching methods (output/intermediate outcome) to improve learning among students (final outcome).
[3] Project-level Outcome Indicators and Component-Level Outcome Indicators. Strategic objective(s) and intermediate outcomes reflect constructs that need further definition to be measured. These outcomes need to be translated into a set of measurable indicators to establish whether progress is being achieved. Indicators are tied to results by focusing on one or more characteristics of the outcome. A measure then expresses an indicator’s value quantitatively or qualitatively using SMART criteria:
Specific. Indicators should reflect simple information that is communicable and easily understood.
Measurable. Are changes objectively verifiable?
Students’ learning achievement
Percentage of customers who are satisfied with the availability of potable water or electricity
Achievable. Indicators and their measurement units must be achievable and sensitive to change during the life of the project.
Relevant. Indicators should reflect information that is important and likely to be used for management or immediate analytical purposes.
Time bound. Progress can be tracked at a desired frequency for a set period of time.
Where possible, measurement strategies should be based on existing data sources or tested data collection methodologies. Relevant information for analysis and aggregation could already be available through administrative databases or through sample or census-based surveys. Before specific indicators are defined for desired outcomes, practitioners should identify data sources that could be used to measure desired changes.
The following considerations will help guide this process:
An objective or intermediate outcome could need more than one indicator to measure both its qualitative and quantitative aspects.
A minimal number of indicators should be selected. More information is not necessarily better. A common problem with results frameworks and performance measurement systems is that they are tied to a large set of indicators that are burdensome to track.
There is no correct number of indicators to assign per outcome, but the following are useful questions to ask:
Is this indicator absolutely necessary to measure whether progress toward the strategic objective is being achieved?
Will it create additional burdens on the respondents or on the staff collecting the data?
How will this indicator help with monitoring, management, and evaluation?
Having multiple stakeholder opinions on the design of the results framework provides an opportunity for discussion and eventual consensus on what good indicators and measures are and what number of indicators will suffice.
Proxy indicators can be used as indirect measures of achievement when direct measures are difficult to assign. For example, where tests of student achievement have not been systematically applied to assess education quality, a proxy measure might focus on student completion rates. Such proxy indicators must be assigned carefully; a common threat to the validity of results measurement is the use of inadequate proxy indicators (for example, students’ self-reported levels of achievement in mathematics).
Indicators assigned in the design of a results framework might be modified during implementation, as data capacity increases and new data elements become available.
[3. A] Component-level Outputs and Output Indicators. For each Component, follow the above guidance to define outputs and output indicators. Outputs are the direct products of project activities and may include types, levels and targets of services to be delivered by the project. The key distinction between an output (a specific good or service) and an outcome is that an output typically is a change in the supply of goods and services (supply side), while an outcome reflects changes in the utilization of goods and services (demand side)
[4] – [10] Project Monitoring Plan
The next step in designing a results framework is to plan how it will be operationalized to monitor progress and assess the effects of interventions. The plan for monitoring performance typically lists the following elements in a complementary tool, the monitoring plan:
[5] & [6] Baseline and target values for selected measures to provide the means for verification to measure changes in the indicators. It is important to remember that the construction of baseline values can be based on available secondary data sources, which can be improved or sharpened through subsequent work. Delaying the preparation of an intervention until a “perfect” baseline is available is rarely feasible or desirable. At the same time, the absence of a baseline too often indicates that the problem definition stage of intervention design is being conducted on the basis of either conventional wisdom or untested assumptions.
For [6] Target values should be entered for the years data will be available, not necessarily annually.
[7] Frequency or designated intervals at which the data will be collected or provided.
[8] Data sources or methods for data collection.
[9] The agent(s) responsible for collecting or providing the data (for example, independent evaluation team, project staff, and so forth).
[10] Assumptions and risks associated with the indicators or information being collected (such as the assumption that data will be available from a second party).
[11] Core: please mark if any of the outcome indicators are the same as any of those included in the list of outcome indicators used by the GPSA’s Results Framework to measure results at the Program Level. This information is useful for analysis purposes only by the GPSA. Leave blank if not applicable.

## 2. Proposal RF
Global Partnership for Social Accountability (GPSA)
Proposal Results Framework
PROJECT LEVEL RESULTS
Project Title | Mozambican Social Accountability Network, MOSANET
Project's Strategic Objectives [1] | 1) To build capacity of civil society on social accountability in the Health and Education sectors 2) To increase constructive dialog between citizens and government in the Health and Education sectors governance. 3) The 1st and 2nd objectives will significantly contribute to improve the quality of service delivery in the Health and Education sectors
Project Level Outcomes [2] | Project level Outcome Indicators [3] | Unit of Measure [4] | Baseline [5] | Cumulative Target Values [6] |  |  |  |  | Frequency [7] | Data Source/ Methodology [8] | Responsibility for Data Collection [9] | Assumptions and Risks [10] | Core [11]
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Outcome 1: Strengthened capacity of civil society, including child led organizations on social accountability in the Health and Education sectors | Significant increase in number of COSs, and child led organizations, that engage in SA in the Health and Education sectors nationwide | # of CSOs and child led organizations holding government to account, actively participating in SA activities, # of SMS feedbacks, # community score cards submitted, # of expenditure trackings undertaken # of PDQ undertaken, # of workshops with CSO representatives, # child participants in workshops | Many CSOs in Mozambique have focused on direct service delivery, and have limited awareness about their right and mandate to actively participate in governance. Some CSOs have taken on SA, but not in a systematic way and with little coordination. Limited knowledge about PDQ, CESC have started piloting the SMS platform, but limited to the education sector, and in i limited # of provinces, the public lack awareness of the SMS channel, # lack of child participation | A startup workshop is organized, 11 CSOs, and child led organizations, identified and trained, 1st year of nation-wide survey undertaken, 1 round of annual workshops, comprenhensive SA programs established in the 3 focus provinces, SMS Quality Assessment System started | 2nd round of annual workshops, comprenhensive SA programs, with strong participation, further developed in the 3 focus provinces | 3rd year nation-wide survey undertaken, 3 round of annual workshops with strong participation from children, comprenhensive SA programs are sustainable in the 3 focus provinces |  |  | Quarterly, Annualy | Project reports from partners, Workshop reports, Rede de Crianca's publications, government publications, Open Budget Index, AGI Data Portal - Governance reports | All stakeholders, with SCIMoz responsible for coordinating and compiling | We assume that CSOs are willing to take on SA work it they receive support, and that they will be significantly strengthened on SA work if they receive training on community Score Cards, PDQ and SMS feedback platform. We assume that the CSO environment in Mozambique will be strengthened by creating a stronger network. We risk that civil society have limited capacity, knowledge and motivation to engage in SA activities given their previous focus on direct service delivery. We risk that the lack of awareness about children's right and abilities to participate on issues like this can limited the involvement of children. | X
Outcome 2: Increased constructive dialog between citizens, including child led organizations, and government in the Health and Education sectors governance | # of dissemination workshops with participation from government and civil society , including child led organizations, on district, province and national level, #, quality and multi-stakeholder participation in proposed actions to fill identified gaps | # of issues raised by civil soceity and childre responded to bt governments, # of workshops with CSO and government representatives, | School Councils and Health Community Committees exist today, but the work and result do not the potential. There are limited opportunities for citizens, including children to voice their concerns to governments, and limited communication from governments to a broader audience. | 1st annual workshops organized with strong participation of children, PDQ establised, SMS established, capacity building of government representatives undertaken | 2nd annual workshops organized with strong particiation on children, PDQ functioning, SMS functioning, capacity of government representatives increased | 3rd annual workshop organized with strong participation of children, PDQ functioning, SMS functioning, capacity of government representatives increased and sustainable |  |  | Quarterly, Annualy | Project reports from partners, Workshop reports, Rede de Crianca's publications, the Nation-wide Community Score Cards Survey, the SMS database, Open Budget Index, AGI Data Portal - Governance reports | All stakeholders, with SCIMoz responsible for coordinating and compiling | We assume that the dialog between CSOs, Citizens and government improves and becomes constructive if we create well functioning channels for direct communication, both though face to face meetings and though new technology. We risk that government are reluctant to participate in dialogues like this, with this degree of openness given the lack of experience with it. We risk that CSOs and citizens lack motivation and belief in this, given their previous experience. | X
Outcome 3: Improved quality of service delivery in the Health and Education sectors | Increased quality in service delivery as perceived by service beneficiaries, the funds received by the school do correspond with allocations | Perceived quality of Education and Health services reported by beneficiaries through the community score card system, the PDQ approach and though the SMS channel, # of complaints/complements on education and health services, the funds received by the school | To be developed | 1st round of nation-wide community score card survey undertaken as a baseline, SMS and PDQ established to monitor quality | SMS and PDQ functioning to monitor quality | 2nd round of nation-wide community score card survey undertaken and we expect a signifant improvement in the 3 target provinces, SMS and PDQ data indicate increase in quality |  |  | Following project cycle, but with national community score card surveys in year 1 and 3 | Quality score card reports, on individual level and compiled on project, region and national level, SMS data collection, workshop reports, Rede de Crianca's publications | All CSO stakeholders, with SCIMoz responsible for coordinating and compiling | We assume that we will identify gaps through the SA activities, including the national community score card survey that we will disseminate and discuss with government representatives in the workshops to plan how to solve the problems. We assume that some of the problems identified can be solved though better communication and better practices within the financial frame given. We risk that the problems and issues identified are caused by lack of funding or other reasons outside this project reach.
RESULTS BY COMPONENTS
COMPONENT 1 [1]: Civil Society Capacity Building
Intermediate Outcomes [2] | Outcome Indicators [3] | Unit of Measure [4] | Baseline [5] | Cumulative Target Values [6] |  |  |  |  | Frequency [7] | Data Source/ Methodology [8] | Responsibility for Data Collection [9] | Assumptions and Risks [10]
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Well functioning SA programs in Maputo, Tete and Nampula, involving all stakeholders, including children | # of CSOs implementing a quality SA activities in the 3 regions of Mozambique | # and quality of programs | Many CSOs in Mozambique have focused on direct service delivery, and have limited awareness about their right and mandate to actively participate in governance. Some CSOs have taken on SA, but not in a systematic way and with little coordination. Limited knowledge about PDQ, CESC have started piloting the SMS platform, but limited to the education sector, and in i limited # of provinces, | Comprenhensive SA programs established in the 3 focus provinces | Comprenhensive SA programs functioning in the 3 focus provinces | Comprenhensive SA programs are made sustainable in the 3 focus provinces |  |  | Quarterly | Project reports from partners, workshops reports | SCIMoz | We assume that CSOs are willing to take on SA work it they receive support, and that they will be significantly strengthened on SA work if they receive training on community Score Cards, PDQ and SMS feedback platform. We assume that the CSO environment in Mozambique will be strengthened by creating a stronger network. We risk that civil society have limited capacity, knowledge and motivation to engage in SA activities given their previous focus on direct service delivery. We risk that the lack of awareness about children's right and abilities to participate on issues like this can limited the involvement of children.
Nation-wide Score Card baseline and final survey on quality of Education and Health sectors perceived by service beneficiaries | Participatory performance monitoring of Health and Education services report produced with participation of 11 CSOs and child led organizations, covering all of the provinces in year 1 and 3 | Quality of report, # of CSOs and child led organizations involved and coverage of provinces. | To be developed | CSOs and child led organizations in 11 provinces collect community score cards, which lead to an national report |  | CSOs and child led organizations in 11 provinces collect community score cards, which lead to an national report |  |  | Year 1 and 3 | Project reports from partners, workshops reports, Participatory performance monitoring of Health and Education services report t | CSOs in the provinces, with SCIMoz reponsible for coordination and compilation. | We assume that we can identify CSOs in all provinces with motivation to collect data in sampled districts, and that they can perform a data collection of good quality with the right support and training. We risk that we cannot find motivated CSO in all districts, or those CSO fail to collect community score cards
Add more
Planned Outputs [3.A] | Output Indicators [3.A] | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Representatives from SCIMoz, CESC and Rede de Crianca in Maputo, Tete and Nampula trained on Score Cards, Expenditure Tracking, PDQ, SMS quality assessment and CSO mapping | # of participants from each of the 3 partners and child led organizations in a national project start up workshop and their perceived learning outcomes. # of participants in the mid-term project wokshop | # of participants and quality, # of child participants dissagregated by gender | To be developed | Key project staff and child led organizations receive initial training | Key project staff and child led organizations receive technical assistance | Key project staff and child led organizations receive technical assistance |  |  | 1st and | Workshop report, including simple evaluation | SCIMoz | We assume that each of the 3 partners will participate actively in delivering in the workshop, that we have access to external capacity on PDQ, and that each of the 3 partners indentify and send suitable participants. We risk that external capacity is not available
Mapping of CSOs ability, motivation and capacity to engage in SA activities in all provinces | # relevant CSOs and child led organizations in every province are identified | # of CSOs and child led organizations identified, and their geographical coverage | To be developed | Relevant CSOs and child led organizations in every province are identified |  |  |  |  | 1st year | CSO mapping as agreed on in the start-up workshop | All CSO stakeholders, with SCIMoz responsible for compilation. | We assume that the 3 partners of MOSANET will be able to do this mapping after agreeing on method. We risk that we are unable to cover all provinces
CSOs, including child led organizations, in Maputo, Nampula and Tete capacitated to implement SA programs that utilize and pilot the following context sensitive and adapted tools in Education and Health sectors: Score Cards, SMS quality assessment and PDQ | # of CSO initiating SA programs in the 3 focus areaes, # of SMS feedbacks, # community score cards submitted, # Expenidtures trackings undertaken, # of PDQ undertaken, # of workshops with CSO representatives | # of CSOs in the focus areas that implement programs utilizing the 3 tools | Many CSOs in Mozambique have focused on direct service delivery, and have limited awareness about their right and mandate to actively participate in governance. Some CSOs have taken on SA, but not in a systematic way and with little coordination. Limited knowledge about PDQ, CESC have started piloting the SMS platform, but limited to the education sector, and in i limited # of provinces. Some CSOs have limited understang of child particiation | The project organization is established and have started implementing the methods, in all the 3 areas | Well functioning SA programs, according to the checklist, established |  |  |  | Quarterly | Project reports from partners, workshops reports, and data collected with the tools | All CSO stakeholders, with SCIMoz responsible for compilation. | We assume that we have the capacity to establish strong SA programs in these provinces given the 3 partners current engagement in the areas, and that we can build on existing programs and institutions like School Councils and Health Community Committees. We risk that government and other existing actors are reluctant to participate in workshops and other dialog channels.
1 CSO in each of the remaining provinces trained on the use of score card | All provinces are covered by CSOs and child led organizations able to collect community score cards | # of CSO and child led organizations collecting community score cards, and geographical coverage | To be developed | Community score cards are collected in 11 provinces |  | Community score cards are collected in 11 provinces |  |  | 1st and 3rd year | Nation-wide data collection and report. | All CSO stakeholders, with SCIMoz responsible for compilation. | We assume we are able to train CSOs to cover all provinces in the data collection and that they are able to perform. We risk that we are not able to cover all 11 provinces.
Reader and child friendly and relevant training manual available for CSOs, child led organizations and other actors on the 3 different SA tools in Education and Health sectors | 1 project manual aimed at relevant actors covering all tools developed | Quality of project manual as perceived by audience, including children | Many different sources of training material available, but fragmented and not contextualized and translated into Portuguese, limited access to child friendly material | Project manual developed, and evaluated. | Project manual adjusted, and evaluated. | Shared natioanally and internationally |  |  | 1st and 2nd year | Light evaluation/assessment | SCIMoz | We assume that we can collect relevant guidance, tools and lessons learnt form other projects, and contextualize and translate to make the material relevant and easy accessible by relevant audience. We risk that audiences outside the project are not aware of the training material.
Available on-line training for CSO child led organizations,and other actors on the 3 different SA tools in Education and Health sectors | Training material uploaded and adapted to the MOSANET webpage | Function of online training materials | Limited available online resources on SA available in Portuguese, and lack of child friendly material | Online training manual adapted and uploaded on MOSANET | Actors from CSOs and child led organizations and government utilize the online training material | Actors from CSOs, child led organizations andgovernment utilize the online training material |  |  | Annualy | Online basic survey connected to the material | SCIMoz | We assume that MOSANET is functional, and that relevant audiences, including children, will use it. We risk that relevant audiences are not aware of MOSANET and its content.
COMPONENT 2: Building Awareness and Capaciy of Service Providers
Intermediate Outcomes | Outcome Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Increased awareness among service providers in 6 districts of Nampula (2), Tete (2) and Maputo city (2) provinces about SA with a focus on PDQ; | 6 service providing instutions have knowledge and awareness about PDQ | # of service providers and level of knowledge | to be developed | Service providers are trained in all target districts | The service providers are supported by project stakeholders | The service providers are supported by project stakeholders |  |  | Annually | Basic self assessment survey of knowledge | SCIMoz | We assume that the service providers are motivated and participate. We risk that representative lack motivation or capacity to participate in trainings.
IO 2: Functioning information and feedback mechanism for service providers | PDQ, Community Score Card, and SMS feedback program is operational with civil and governmental participation, MOSANET webpage is operational, project messages are broadcasted on radio | # of SMS assesment, # PDQs undertaken, # number of considated reports produced | SMS system, PDQ and the feedback mechanisms established | SMS system, PDQ and the feedback mechanisms funtions | SMS system, PDQ and the feedback mechanisms funtions |  |  |  | Annually | SMS database, PDQ reports, workshop reports | SCIMoz | We assume that the the PDQ program will be operational. We risk that government representatives are unwilling or unable to participate in the project.
Add more
Planned Outputs | Output Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: Awareness raising meetings with service providers in 6 districts of Nampula and Tete provinces, on SA with a focus on PDQ; | Government participants from all target areas have knowledge about PDQ | # of government participant and geographic coverage | to be developed | Service providers involved in awareness raising in all target districts |  |  |  |  | Quarterly | Project reports from partners, workshops reports, including self assessment of participants learning outcomes | All CSO stakeholders, with SCIMoz responsible for validation and compialtion | We assume that the service providers are motivated and participate. We risk that representative lack motivation or capacity to participate in trainings
Output 2: IEC materials for service providers on SA | Training material uploaded and adapted to MOSANET | Function of online training materials | Limited available online resources on SA available in Portuguese | Training material made available for service providers on webpage, the SMS database etsablished | Training material adjusted and available for service providers on webpage, the SMS database functions | Training material adjusted and available for service providers on webpage, the SMS database functions |  |  | Annually | Online survey connected to the material | SCIMoz | We assume that MOSANET is functional, and that relevant audiences will use it. We risk that relevant audiences are not aware of MOSANET and its content.
Output 3: Training members of the Provincial Assemblies in Nampula and Tete, 6 District Consultative Councils and 3 Municipal Assembly on SA in order to use the results from SA tools as evidence for the need of improvements in quality of Health and Education. | Provincial Assemblies in Nampula and Tete, 6 District Consultative Councils and 3 Municipal Assembly, use evidence from the SA tools to improve quality of service delivery | # of plans and policies to improve quality based on SA evidence | to be developed | 1st annual workshop resulting in concrete plans to bridge identified gaps with involvent of CSOs | 2nd annual workshop resulting in adjustment of concrete plans to bridge identified gaps with involvent of CSOs | 3rd annual workshop resulting in of concrete planss on how to continue the SA network with involvment of CSOs |  |  | Annually | Project reports from partners, workshops reports and minutes from assembly meetings on different levels | All CSO stakeholders, with SCIMoz responsible for validation and compialtion | We assume that assembly representative on different levels are motivated and participate, and that they are able to utilize SA evidence in policy development and planning. We risk that representative lack motivation or capacity to participate in trainings and to address problems in service delivery
Add more
COMPONENT 3 Constructive Dialog
Intermediate Outcomes | Outcome Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Improved communication channels between government and civil society in Health and Education sectors | Annual workshops with civil, child and governmental participation on different levels organized, operational MOSANET webpage and frequent radio broadcasts with project messages | # workshops with civil, child and governmental participation on different levels organized, # of visits on webpage, # of radiobroadcasts with project messages | Lack of communication channels | 1st annual workshop organized with broad participation, Webpage established, | 2nd annual workshop organized with broad participation, Webpage funtions and is used, SMS system funtion and in use | 3nd annual workshop organized with broad participation, Webpage funtions and is used, SMS system funtion and in use |  |  | Annually | Project reports from partners, workshops reports, webpage counter, media (radio) monitoring | All CSO stakeholders, with SCIMoz responsible for validation and compilation | underrepresented
Strengthened mechanisms through which citizens, including children, can voice their concerns to the government in Health and Education sectors (in Maputo City, Tete and Nampula) | Citizens report their concerns through the SMS channel and though the PDQ system | # of SMSs received and geographical coverage, # of community score cards submitted, # PDQ meetings organized with civil and governmental participation | [6 empty] | Quarterly | Project reports from partners, workshops reports, SMS database and PDQ reports. | All CSO stakeholders, with SCIMoz responsible for validation and compilation | We assume that we will able to add the Health sector as a part of the SMS channel, that we can widen the geographic coverage of this project item and we manage to broadcast the information about the SMS channel to the audience though radio and Rede de Crianca's representation in the different districts. We risk that the audience lack knowledge about the SMS channel, and that some beneficiaries have limited access to cellular phones.
Add more
Planned Outputs | Output Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: Partner defined quality exercises on annual basis involving both service providers and service users, including children, at community level in 6 districts of Maputo City, Tete and Nampula provinces; | 6 annual PDQ exercises at community level, geographic coverage in target areas | # of PDQ exercises at community level, and geographical coverage | To be developed | 1st annual workshop organized with broad participation | 2nd annual workshop organized with broad participation | 3nd annual workshop organized with broad participation |  |  | Annually | Project reports from partners, workshops reports, and PDQ reports. | All CSO stakeholders, with SCIMoz responsible for validation and compilation | We assume that both service providers and service users are motivated and capable to play a part in PDQ exercises after receiving training. We risk that the PDQ projects are not sustainable throughout the project period.
Output 2: Meetings at district and provincial levels to discuss and develop joint plan of action to address findings from PDQ,. | Meetings at district and provincial levels that leads to joint plan of action to address findings from PDQ organize | # of meetings at district and provincial levels, # of plans of action or policy changes to address findings from PDQ | To be developed | 1st annual worksop with participation from CSOs and government resulting in concrete plans | 2nd annual worksop with participation from CSOs and government resulting in concrete plans | 3rd annual worksop with participation from CSOs and government resulting in concrete plans for sustainability |  |  | Annually | Project reports from partners, workshops reports, PDQ reports, plans of action and policies. | All project stakeholders, with SCIMoz responsible for validation and compilation | We assume that project stakeholders are motivated and capable to contribute in meetings, and that those meeting will lead to action. We risk limited participation and obligation
Government actors
Add more
COMPONENT: KNOWLEDGE & LEARNING
Intermediate Outcomes | Outcome Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Improved knowledge of government, citizens and CSOs including child led organizations, on social accountability through strategic sharing of the MOSANET results and lessons learnt in Mozambique | Lessons learnt shared with all project stakeholders and external audiences, including the global GPSA knowledge sharing platform | # of and content of knowledge publication shared, and with which audience. | To be developed | Lessons learnt from inception phase produced and shared | Lessons learnt from implementation phase, and mid-term review, produced and shared | Lessons learnt from implementation phase, and final evaluation, produced and shared |  |  | Annually | Knowledge publications, GPSA plattforms, MOSANET webpage | All project stakeholders, with SCIMoz responsible for validation and compilation | We assume that project stakeholders are able to identify lessons learnt based on experience and training, and that we get access to publish this on the GPSA platform. We risk that project stakeholder are focusing on project performance with little sensitivity on knowledge production.
IO 2:
Add more
Planned Outputs | Output Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: A program webpage for dissemination of results and lessons learnt on social accountability in health and education sectors; | MOSANET webpage functional with a knowledge and learning section online | Assessment of MOSANET webpage | No such webpage exsist today | webpage is establised | webpage is regulary updated with relevant material, and is in use | webpage is regulary updated with relevant material, is in use, and linked to the GPSA knowledge plattform |  |  | Annually | MOSANET webpage, and visit tracker | SCIMoz | We assume we can establish a webpage within the SCIMoz web structure with limited costs and investments. We risk financial and technical complications.
Output 2: Mid-term review and final on evaluation project performance undertaken in program impact areas; | Internal midterm-review that identify needs for adjustments and final evaluation that documents or indicates impact produced | Quality of mid-term review and final evaluations | N/A |  | Mid-term review produced | Final evaluation produced |  |  | 2nd and 3rd year | Review and evaluation reports | SCIMoz | We assume that the stakeholders are capable of undertaking a mid-term review based on training in a basic methodology and we assume we get access to capacity to undertake the final evaluation. We risk that project stakeholders are not able to produce a mid-term review that can inform the continuation of the project and hat we lack the resources to engage with capacity actors on the final evaluation.
Output 3 :Lessons learnt and success stories, to be disseminated in formats and means for the different audiences, with a special focus of innovative elements like the SMS channel, through annual national meetings with broad participation from key stakeholders on social accountability in Mozambique or other countries implementing GPSA supported programs | Lessons learnt shared with all project stakeholders and external audiences, including the global GPSA knowledge sharing platform | # of and content of knowledge publication shared, and with which audience. | To be developed | Lessons learnt produced and shared | Lessons learnt produced and shared | Lessons learnt produced and shared |  |  | Annually | Knowledge publications, reports from national meeting, GPSA platforms, MOSANET webpage | SCIMoz | We assume that project stakeholders are able to identify lessons learnt based on experience and training, that we are able to communicate this in annual meetings and that we get access to publish this on the GPSA platform. We risk that project stakeholder are focusing on project performance with little sensitivity on knowledge production.
Note on A8: These outcomes should derive from the definition of your Project’s strategic objectives. Please focus on key outcomes only, which will reflect the Project’s overall achievements. Outcomes are the specific changes in project participants’ behavior, knowledge, skills, status and level of functioning; they should be defined in a SMART way: strategic, measurable, action-oriented, realistic, and timed.
Note on A16: For each Component, insert the component’s title as defined in the online application.
Note on A61: Required Component for all Application

## 3. GPSA RF
GPSA: Results Areas, Indicators and Sources of Information
A. Results Areas
GPSA is structured in four “results areas”, which correspond to its “governance pillars”.
1) Transparency: people able to access and use information on government activities
2) Representation and voice: people have mechanisms and/or policies through which they can engage in government processes.
3) Accountability: governments are more accountable to beneficiaries in service delivery and in management of public resources.
4) Learning for Improved Results: improved knowledge and practice of social accountability.
The first three areas can be considered as a menu from which GPSA might want to draw from without having to cover each area in every country. The specific results will need to be tailored to each country context.
These results areas are presented in GPSA’s “theory of change” as (intermediate) outcomes. The diagram also shows critical assumptions and the pathways from resources to impacts, including development results to which GPSA may contribute but that cannot be attributed only to it. The critical assumptions can also be used as a key input for risk management.
In order to operationalize the results framework it is necessary to identify a set of indicators corresponding to the different levels of the “results chain” (except the higher level corresponding to development results) included in the “theory of change” (TOC). This is done below, making use as much as possible of existing indicators and available data sources, as well as those that can be constructed using data that will be generated by GPSA’s operations. It should be noted that whereas the indicated outputs are fully dependent on GPSA (and therefore GPSA is accountable for achieving them), the outcomes and impact depend crucially on the role of other interventions and exogenous factors. Furthermore, the links between outputs and outcomes, as well as between outcomes and impact, are covered by other WB initiatives (such as those under the Governance & Anticorruption -GAC -strategy), as well as by research projects.
Finally, complementing the general key assumptions included in the TOC diagram, the following are additional assumptions concerning what leads from one stage to another:
from activities to outputs: the knowledge component activities (1-3) will help to establish a global platform for knowledge exchange and research (output 1), assuming that CSOs would be interested to participate in such a platform; knowledge on effective SAcc interventions for different contexts would result from the implementation of activities (1-3) assuming that a M&E system (along the lines further described in the GPSA Results Framework, Draft Concept Note, see GPSA website) is fully functional.
from outputs to outcomes: activities supporting the enabling environment for SAcc (4) combined with capacity building activities (2) and outputs (1), (2) and (3) would lead to outcomes (1-4) assuming that the knowledge generated and disseminated is relevant, that governments would be willing, or sufficiently pressured, to undertake governance reforms and to become more accountable; it is also assumed that SAcc capacity building activities will be effective.
from outcomes to impact: outcomes (1-4) would contribute to improved service delivery and development effectiveness assuming that demand pressure on government services resulting from the achievement of those outcomes would lead to enhanced quality of government services and to greater development effectiveness.
On this last set of links, there is evidence from research and ongoing work by (among others) the World Bank GAC strategy, as well as on the work leading to (and spawned by) the 2004 World Development Report (“Making Services Work for Poor People”). On ii), the evidence is thin, and GPSA can and should contribute to it.
B. Indicators and sources of information
Given that GPSA will operate at the global, country and project level, the results framework includes indicators corresponding to these three levels. The indicators are focused on quantitative aspects, which would be complemented by the qualitative information to be provided by the activities indicated in the section on M&E.
Global level
This level is basically related to the fourth results area, i.e., “Learning for improved results”, which at the global level boils down to the generation of the global public good of knowledge on social accountability. Furthermore, aspects related to GPSA as a whole are also included in this level.
Country level
There is an abundance of data sources corresponding to different aspects of SAcc at the country level, such as Governance-at-a-Glance and Demand for Good Governance indicators (AGI Data Portal), WBI’s CDR, the Open Budget Index, Afrobarometer, Latinobarometro, for IDA countries the last of the CPIA criteria, i.e., “Transparency, Accountability, and Corruption in the Public Sector”, IEG (World Bank Independent Evaluation Group) GAC country data , World Bank indicators developed for GAC-II on government openness; CPARs (Country Procurement Assessment Reviews), WBI Worldwide Governance Indicators and the Open Transparency Index.
The tables presented further below select among these sources those which are more adequate given their periodicity and coverage. However, in specific country cases, some of the other sources mentioned above may also be suitable. Furthermore, there are countries where local sources of data on transparency are available. These sources can be tapped particularly in the elaboration of country or thematic case studies, as indicated in the section on M&E.
Project level
Each project/ grant funded by GPSA should indicate in their applications the result area(s) to which it expects to contribute, targets for its outputs specifying their timeframe, the set of activities in which they plan to use the resources provided by GPSA, the links between activities' outputs and outcomes, the current levels of these variables (which will be the baselines) and their implementation strategy. GPSA could develop a web based application that projects/grants could (and should) utilize for their own management and monitoring as well as to feed GPSA’s monitoring and reporting. This would be a sort of self-organizing system, minimizing the time needed from GPSA’s Secretariat.
An important source of information will be the records of activities supported by GPSA. Therefore, it is necessary to ensure that the designs of grants/activities to be funded by GPSA indicate clearly their output and outcome indicators before they are approved, as indicated in the preceding paragraph, and that they complete the collection of baseline data (complementing the data presented in the application form, if need be) during their first 6 months of operations. During the first three months of operations, formats for reporting results and data should be established, and to assure the quality of self-reported data the reports will be systematically reviewed by peer organizations and/or GPSA staff.
GPSA Program-Level Outputs and Outcomes Indicators (Sample Draft - under revision):
C. Outcome indicators and case studies
As indicated in the preceding tables, for some indicators the source of information will be case studies (country and thematic). These case studies could complement the information provided by indicators with an analysis and synthesis of a set of issues such as the following: the extent to which Civil Society (CS), government and other stakeholders have improved knowledge and capacity to harness social accountability for better development outcomes; the degree to which Citizens are engaged in monitoring of service delivery and public resource management; the extent to which Citizens’ priorities are reflected in policy and decision-making (looking at levels of engagement and where this has changed policy and practice), and the extent to which government authorities value the participation of citizens in achieving effective service delivery; participation of CS in public policy discussions; use by CS of grievances mechanisms and collective action behaviour induced by GPSA’s supported CSOs and development by CSOs supported by GPSA of associations representing CS.
D. Performance indicators
In addition to the indicators shown in the above tables, the following indicators are proposed (to be reported on annual bases, using GPSA’s records)to assess GPSA's performance:
1. number of partners involved;
2. number and amount (disbursed) of grants
3. number of mentoring grants,
4. number of countries that opted-in
5. number of grant applications
6. number of CSOs which GPSA supported
E. Dissemination Strategy and Knowledge Sharing to facilitate use and decision making
The results framework can be used to communicate the progress and problems in achieving results. One way of presenting results is through a “dashboard,” highlighting the key high-level objectives and outcomes/outputs achieved, using the framework for planning and review meetings (with the current status of the indicators highlighted), and using the change in the indicators from baseline to highlight the results.