## Instructions
GLOBAL PARTNERSHIP FOR SOCIAL ACCOUNTABILITY (GPSA) Grantee Application: Results Framework and Monitoring
Instructions:
Please read these instructions before filling out your proposal’s Results Framework (RF) included under Tab 2. You should also review Tab 3, which includes GPSA’s Results Framework. Please note that you are NOT required to use any of the specific outcomes or indicators as defined in the GPSA's Results Framework [see Tab 3: GPSA RF]. The latter is provided for guidance purposes only insofar as the proposal should reflect GPSA's pillars of good governance.
If you need additional guidance, you can find more information about designing a results framework in the GPSA’s website under Resources.
For the Proposal's Results Framework, you must provide the following information:
--Project-level outcomes and outcomes indicators
--For each Component included in your proposal, intermediate outcomes, outcomes indicators, outputs and outputs indicators.
--Based on the RF proposed, you will have to describe the proposal's Monitoring and Evaluation (M&E) Plan in Section 4 of the e-application, which includes the following questions [please note that these questions must be answered IN the e-application, NOT here]:
Please describe the proposal’s monitoring system, including the specific methods and tools that will be used. Justify how the proposed methods and tools are adequate to the problem(s) being addressed by the project. What resources will be needed to rollout and implement the monitoring system? E.g. financial, human, technical, use of ICTs, etc. Will external support be needed? If yes, please explain. Please make sure to address all these questions.
Describe the intervention’s evaluation methods. Why are these adequate to evaluate the intervention’s expected intermediate and final outcomes? What resources will be needed to design and implement the proposed evaluation(s) Will external support be needed? If yes, explain. Please make sure to address all these questions.
The numbers below correspond to the references included in the Results Framework tables [see Tab 2: Proposal RF] that you must fill out:
[1] Insert Project Strategic Objectives as defined in question 2.1 of the online application. For each Component, insert the component’s title as defined in the online application.
[2] Insert the definition of the Project Level Outcomes. These outcomes should derive from the definition of your Project’s strategic objectives. Please focus on key outcomes only, which will reflect the Project’s overall achievements. Outcomes are the specific changes in project participants’ behavior, knowledge, skills, status and level of functioning; they should be defined in a SMART way: strategic, measurable, action-oriented, realistic, and timed.
For each Component, insert the definition of Intermediate Outcomes: these outcomes are attributable to each component, and would contribute to the achievement of intermediate and final outcomes at the Project level. An intermediate outcome specifies a result proximate to an intended final outcome, but likely more measurable and achievable in the lifetime of a project to an intended final outcome. To ensure the accuracy of assigned intermediate outcomes, the consideration of each proposed outcome should include reviewing who is best situated to achieve the outcome (that is, is this within or outside the scope of this intervention?) and how the outcome might be effectively measured. Example: Teachers use the new teaching methods (output/intermediate outcome) to improve learning among students (final outcome).
[3] Project-level Outcome Indicators and Component-Level Outcome Indicators. Strategic objective(s) and intermediate outcomes reflect constructs that need further definition to be measured. These outcomes need to be translated into a set of measurable indicators to establish whether progress is being achieved. Indicators are tied to results by focusing on one or more characteristics of the outcome. A measure then expresses an indicator’s value quantitatively or qualitatively using SMART criteria:
Specific. Indicators should reflect simple information that is communicable and easily understood.
Measurable. Are changes objectively verifiable?
Students’ learning achievement
Percentage of customers who are satisfied with the availability of potable water or electricity
Achievable. Indicators and their measurement units must be achievable and sensitive to change during the life of the project.
Relevant. Indicators should reflect information that is important and likely to be used for management or immediate analytical purposes.
Time bound. Progress can be tracked at a desired frequency for a set period of time.
Where possible, measurement strategies should be based on existing data sources or tested data collection methodologies. Relevant information for analysis and aggregation could already be available through administrative databases or through sample or census-based surveys. Before specific indicators are defined for desired outcomes, practitioners should identify data sources that could be used to measure desired changes.
The following considerations will help guide this process:
An objective or intermediate outcome could need more than one indicator to measure both its qualitative and quantitative aspects.
A minimal number of indicators should be selected. More information is not necessarily better. A common problem with results frameworks and performance measurement systems is that they are tied to a large set of indicators that are burdensome to track.
There is no correct number of indicators to assign per outcome, but the following are useful questions to ask:
Is this indicator absolutely necessary to measure whether progress toward the strategic objective is being achieved?
Will it create additional burdens on the respondents or on the staff collecting the data?
How will this indicator help with monitoring, management, and evaluation?
Having multiple stakeholder opinions on the design of the results framework provides an opportunity for discussion and eventual consensus on what good indicators and measures are and what number of indicators will suffice.
Proxy indicators can be used as indirect measures of achievement when direct measures are difficult to assign. For example, where tests of student achievement have not been systematically applied to assess education quality, a proxy measure might focus on student completion rates. Such proxy indicators must be assigned carefully; a common threat to the validity of results measurement is the use of inadequate proxy indicators (for example, students’ self-reported levels of achievement in mathematics).
Indicators assigned in the design of a results framework might be modified during implementation, as data capacity increases and new data elements become available.
[3. A] Component-level Outputs and Output Indicators. For each Component, follow the above guidance to define outputs and output indicators. Outputs are the direct products of project activities and may include types, levels and targets of services to be delivered by the project. The key distinction between an output (a specific good or service) and an outcome is that an output typically is a change in the supply of goods and services (supply side), while an outcome reflects changes in the utilization of goods and services (demand side)
[4] – [10] Project Monitoring Plan
The next step in designing a results framework is to plan how it will be operationalized to monitor progress and assess the effects of interventions. The plan for monitoring performance typically lists the following elements in a complementary tool, the monitoring plan:
[5] & [6] Baseline and target values for selected measures to provide the means for verification to measure changes in the indicators. It is important to remember that the construction of baseline values can be based on available secondary data sources, which can be improved or sharpened through subsequent work. Delaying the preparation of an intervention until a “perfect” baseline is available is rarely feasible or desirable. At the same time, the absence of a baseline too often indicates that the problem definition stage of intervention design is being conducted on the basis of either conventional wisdom or untested assumptions.
For [6] Target values should be entered for the years data will be available, not necessarily annually.
[7] Frequency or designated intervals at which the data will be collected or provided.
[8] Data sources or methods for data collection.
[9] The agent(s) responsible for collecting or providing the data (for example, independent evaluation team, project staff, and so forth).
[10] Assumptions and risks associated with the indicators or information being collected (such as the assumption that data will be available from a second party).
[11] Core: please mark if any of the outcome indicators are the same as any of those included in the list of outcome indicators used by the GPSA’s Results Framework to measure results at the Program Level. This information is useful for analysis purposes only by the GPSA. Leave blank if not applicable.

## 2. Proposal RF
Global Partnership for Social Accountability (GPSA)
Proposal Results Framework
PROJECT LEVEL RESULTS
Project Title | Citizens Engage to Monitor Bottlenecks in the Delivery of Quality Reproductive Health (RH) Services for Poor Women and Men
Project's Strategic Objectives [1] | Contribute to improved delivery of reproductive health (RH) services through Social Accountability (SAcc) approaches to identify and address supply side bottlenecks in access and quality
Project Level Outcomes [2] | Project level Outcome Indicators [3] | Unit of Measure [4] | Baseline [5] | Cumulative Target Values [6] |  |  |  |  | Frequency [7] | Data Source/ Methodology [8] | Responsibility for Data Collection [9] | Assumptions and Risks [10] | Core [11]
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Outcome 1: Enhanced capacities of citizen groups and community members in target sites to engage with local government units (LGUs) to monitor performance in RH service delivery, specifically to identify bottlenecks | No. of CSOs capable of participation and feedback in RH service delivery | Number | 0 |  |  | 6 |  |  | annually | capacity assessments | project staff | Willingness of the key partners and stakeholders to share experiences and adopt SAc tools | x
| No. of CSOs who are actually engaged in monitoring and feedback on RH service delivery (planning, budgeting, monitoring) | Number | 0 |  |  | 6 |  |  | annually | citizen reports/ community report cards | project staff | Commitment of the trained volunteers to sustain engagement in citizen monitoring. | x
| 400 community members engaged in information gathering and monitoring of RH service delivery | Number | 0 |  |  | 400 |  |  | annually | citizen reports/ community report cards | CSO partners
Outcome 2: Increased transparency and responsiveness of government agencies involved in delivery of RH programs and services | 1 policy institutionalizing mechanism for citizen participation in government RH programming | Number | 0 |  |  | 1 |  |  | annually | Guidelines/Memorandum/Policy | Government Partners | Commitment and Willingness of Government, CSO partners, private sector and civil society to collaborate for effective RH service delivery
| 1 Standards for Health service providers both public and private developed by DOH | Number | 0 |  |  | 1 |  |  | annually | copy of Standards/ Policy | Government Partners
Outcome 3: Strengthened learning network on SAcc in RH that generates knowledge on citizen monitoring and engagement with government on RH issues | 1 guidelines developed by network citizen group for citizen inputs to the annual legislative review of the RPRH law | Number | 0 |  |  | 1 |  |  | annually | copy of document | partner CSOs | Willingness of the key partners and stakeholders to share experiences and adopt SAc tools
| 1 online platform for exchange of ideas between key stakeholders, citizen groups and the public | Number | 0 |  | 1 |  |  |  | annually | actual online platform/ report on usage of the online platform | project staff | Online facility is accessible to target users – the general public who are in most need of RH services
RESULTS BY COMPONENTS
COMPONENT 1 [1]: Partnership Building and Communication
Intermediate Outcomes [2] | Outcome Indicators [3] | Unit of Measure [4] | Baseline [5] | Cumulative Target Values [6] |  |  |  |  | Frequency [7] | Data Source/ Methodology [8] | Responsibility for Data Collection [9] | Assumptions and Risks [10]
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Established partnership with CSOs and other key stakeholders on the implementation of the project | No. of memorandum of agreement signed with key stakeholders and partners | Number | 0 | 27 |  |  |  |  | monthly in 1st year, then annually | Memorandum of Agreement | project staff | CSOs and other key stakeholders agreed with project framework
IO 2: Established partnership with media in the dissemination of information relative to the project and delivery of RH services | No. of memorandum of agreement signed with media partners | Number | 0 | 1 |  |  |  |  | quarterly in 1st year, then annually | Memorandum of Agreement | project staff | media partners understood relevance of the project in RPRH law implementation
| 100% of activities supported by media | Percentage | 0 | 100 | 100 | 100 |  |  | quarterly | documentation of activities/ media articles and other materials | project staff
Planned Outputs [3.A] | Output Indicators [3.A] | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: Key stakeholders agreed with project framework and engage in project activities | No. of meetings and groundwork with DOH, PhilHealth, local health officials, service providers, communities and other stakeholders | number | 0 | 6 |  |  |  |  | monthly in first year, then annually | documentation of activity | project staff | Openness and readiness of the stakeholders, especially the public servants to provide relevant and useful information on RH plans, programs and budget
| 1 inception workshop per province | number | 0 | 1 |  |  |  |  | one time (first year) | documentation of activity | project staff | Openness of the service providers to engage the community members in identification of problems and solutions with citizens
| 1 draft MOA for partnership | number | 0 | 1 |  |  |  |  | one time (first year) | copy of MOA | project staff
Output 2: Signed MOA with key stakeholders and partners | 1 MOA signing conducted per municipality | number | 0 | 20 |  |  |  |  | one time (first year) | documentation of activity | project staff | Commitment and Willingness of Government, CSO partners, private sector and civil society to collaborate for effective service delivery
| 1 MOA signing with DOH, DILG and PhilHealth | number | 0 | 1 |  |  |  |  | one time (first year) | documentation of activity | project staff
| 1 MOA signing with partner CSOs | number | 0 | 1 |  |  |  |  | one time (first year) | documentation of activity | project staff
| 1 signed MOA with partners | number | 0 | 1 |  |  |  |  | one time (first year) | signed MOA | project staff
Output 3: Bridged community stakeholders with policymakers | Number of meetings conducted | number | 0 | 1 | 1 | 1 |  |  | annual | documentation of activity | project staff | Commitment and Willingness of Government, CSO partners, private sector and civil society to collaborate for effective service delivery
Output 4: Media partners understood project framework/RH service delivery and agree to support the implementation of the project | Number of consultation dialogue with media partners | number | 0 | 1 | 2 | 3 |  |  | annual | documentation of activity | project staff
COMPONENT 2: Capacity Building for Citizen engagement
Intermediate Outcomes | Outcome Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Competencies in use of SAc approaches and tools by CSOs in target sites (budget analysis, CSC, constructive engagement) | 100% of trained Sac facilitators and community volunteer monitors report confidence in the use of the Sac approaches and tools | Percentage | 0 |  | 100 | 100 |  |  | annual (after each round of mentoring and reflection sessions) | survey report/survey | project staff | Willingness and motivation of target groups to be trained on social accountability and government monitoring.
IO 2: Established collaborative practices and systems for addressing RH concerns between citizens and service providers | Presence of reporting and feedback mechanism between community and service providers | Number | 0 | 20 | 20 |  |  |  | annual | guidelines on reporting and feedback mechanism | project staff | Willingness of RH service providers and citizen groups to use the SAc tools in monitoring RH service delivery
IO 3: Established use of information and findings from SAc processes for advocacy | Conduct of consultations/ fora/ dialogue with LGUs and other key stakeholders | Number | 0 |  | 6 | 6 |  |  | annual starting on the second year | documentation of consultations/ fora/ dialogue with LGUs and key stakeholders | project staff | Commitment service providers to support and encourage constructive engagement with civil society in RH service delivery
Planned Outputs | Output Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: capacitated SAc facilitators and community volunteer monitors for RH budget monitoring and RH scorecard process | 60 SAc facilitators from 20 municipalities are trained on RH budget monitoring and RH scorecard process | Number | 0 | 30 | 30 |  |  |  | bi-annual | attendance sheets / training documentation | project staff | Willingness and motivation of target groups to be trained on social accountability and government monitoring.
| 400 community volunteer monitors are trained on the use of the community scorecard | Number | 0 | 200 | 200 |  |  |  | bi-annual | attendance sheets / training documentation | CSO partners
| 100% of Community Volunteers utilizing the scorecard in monitoring RH services | Percentage | 0 | 50 | 50 |  |  |  | annual | community report card | project staff
Output 2: Customized tools for citizen RH budget tracking and performance scorecard | one tool per year for each municipality for citizen RH budget tracking and performance scorecard | Number | 0 | 20 | 20 |  |  |  | annual | actual tool for citizen RH budget tracking | project staff | SAc Facilitators and community volunteer monitors understood the SAc tools and approaches
Output 3: Customized tools for service providers on RH performance scorecard | one tool per year for each municipality for service provider RH performance scorecard | Number | 0 | 20 | 20 |  |  |  | annual | actual tool for service provider RH performance scorecard | project staff | RH service providers have knowledge on SAc tools and approaches
Output 4: Mentoring through reflection sessions of citizen monitoring groups | 4 reflection sessions conducted in each municipality | Number | 0 | 40 | 40 |  |  |  | bi-annual | reflection session documentations | project staff
Output 5: Action plans between community and service providers reflecting the agreements reached during interface meetings | 4 interface meetings per municipality conducted between community volunteer monitors and service providers | Number | 0 | 40 | 40 |  |  |  | bi-annual | meeting documentations | project staff | Openness of the service providers to engage the community members in identification of problems and solutions with citizens
| 1 action plan per municipality | Number | 0 | 20 | 20 |  |  |  | annual | copy of action plan per municipality | project staff | Commitment of service providers to ensure implementation of actio plans
Output 6: Aggregated data on level of quality of RH services from citizen monitoring | one report per year from 20 municipalities on the quality of RH services | Number | 0 | 20 | 20 |  |  |  | annual | accomplishment report | project staff
Output 7: Identified problem areas in RH service delivery and proposed solutions with key partners and stakeholders | No. of problem areas identified from the community report card | Number | 0 | 1 | 1 |  |  |  | annual | accomplishment report | project staff | Openness of the service providers to engage the community members in identification of problems and solutions with citizens
| Proportion of solutions agreed between community and key partners/stakeholders over problems identified | Percentage | 0 | 100 | 100 |  |  |  | annual | accomplishment report | project staff
Output 8: Citizen Report to Legislative Committee | 1 report submitted to the Legislative Committee | Number | 0 |  | 1 | 1 |  |  | annual | copy of citizen report | project staff | Commitment of the government to support and encourage constructive engagement with civil society in RH service delivery
COMPONENT:
Intermediate Outcomes | Outcome Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Planned Outputs | Output Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Add more
COMPONENT: KNOWLEDGE & LEARNING
Intermediate Outcomes | Outcome Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
IO 1: Generated and packaged information coming from actual SAcc initiative into knowledge products | No. of promotional activities conducted | Number | 0 |  |  | 1 |  |  | final year | documentation of promotional activities | project staff
IO 2: Promoted the use of Sacc tools and approaches to other groups for the purposes of replication and sustaining efforts for social accountability in RH | Interactive feature of the online platform | Yes/No/ In progress | No | In progress | Yes |  |  |  | annual | Online Platform | external service provider | Online facility is accessible to target users – the general public who are in most need of RH services
| No. of citizen reports uploaded in the online platform | Number | 0 |  | 1 | 1 |  |  | monthly | report of online activities from website administrator | website administrator
| Proportion of action response from key stakeholders over citizen reports | percentage | 0 |  | 100 | 100 |  |  | monthly | report/updates from key stakeholders | project staff | Commitment of the government to support and encourage constructive engagement with civil society in RH service delivery through the utilization of the online platform
Planned Outputs | Output Indicators | Unit of Measure | Baseline | Cumulative Target Values |  |  |  |  | Frequency | Data Source/ Methodology | Responsibility for Data Collection | Assumptions and Risks
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
Output 1: Knowledge products (SAcc toolkits, video on SAcc-RH, brochures and CSC reports) produced and distributed | No. of SAc-RH toolkits developed | number | 0 |  |  | 1 |  |  | one time (third year) | copy of SAcc-RH toolkit | external service provider | Successful implementation of the project in target areas and Willingness of the key partners and stakeholders to share experiences and adopt SAc tools
| No. of SAc-RH toolkits distributed | number | 0 | [5 empty] | third year | distribution list | project staff
| 3 SAc-RH videos produced and uploaded to online platform | number | 0 | 1 | 2 | 3 |  |  | annual | copy of SAcc-RH videos | external service provider
| No. of SAc-RH brochures developed | number | 0 | 1 |  |  |  |  | annual | copy of SAcc-RH brochures | external service provider
| No. of Sac-RH brochures distributed | number | 0 | [5 empty] | annual | distribution list | project staff
| No. of SAc-RH CSC reports produced | number | 0 |  | 1 | 2 |  |  | annual starting on the second year | copy of SAc-RH CSC reports | project staff
| No. of SAc-RH CSC reports distributed | number | 0 | [5 empty] | annual starting on the second year | distribution list | project staff
Output 2: Knowledge sharing session involving local and international participants to showcase lessons from project experience | 1 knowledge sharing session conducted | number | 0 |  |  | 1 |  |  | one time (final year) | documentation of knowledge sharing session | project staff | Willingness of the key partners and stakeholders to share experiences and adopt SAc tools
Output 3: Social Marketing activities (cross learning activities, study tours, etc.) conducted to promote replication of Sac tools and approaches used | No. of social marketing activities conducted | number | 0 |  |  | 1 |  |  | quarterly (final year) | documentation of social marketing activities | project staff | Successful implementation of the project in target areas and Willingness of the key partners and stakeholders to share experiences and adopt SAc tools
Output 3: Online platform for information sharing, data gathering and aggregation and citizen feedback on RPRH Law implementation | 1 Online Platform developed | number | 0 |  | 1 |  |  |  | one time (second year) | actual online platform | external service provider | Online facility is accessible to target users – the general public who are in most need of RH services
Add more
Note on A8: These outcomes should derive from the definition of your Project’s strategic objectives. Please focus on key outcomes only, which will reflect the Project’s overall achievements. Outcomes are the specific changes in project participants’ behavior, knowledge, skills, status and level of functioning; they should be defined in a SMART way: strategic, measurable, action-oriented, realistic, and timed.
Note on A13: Author: Expressed needs of the citizens are considered in the planning, budgeting and implementing RH services
Note on A15: Author: Does this pertain to the K&L component? If this is the case, the strengthened network should pertain to the network of resources.
Note on A21: For each Component, insert the component’s title as defined in the online application.

## 3. GPSA RF
GPSA: Results Areas, Indicators and Sources of Information
A. Results Areas
GPSA is structured in four “results areas”, which correspond to its “governance pillars”.
1) Transparency: people able to access and use information on government activities
2) Representation and voice: people have mechanisms and/or policies through which they can engage in government processes.
3) Accountability: governments are more accountable to beneficiaries in service delivery and in management of public resources.
4) Learning for Improved Results: improved knowledge and practice of social accountability.
The first three areas can be considered as a menu from which GPSA might want to draw from without having to cover each area in every country. The specific results will need to be tailored to each country context.
These results areas are presented in GPSA’s “theory of change” as (intermediate) outcomes. The diagram also shows critical assumptions and the pathways from resources to impacts, including development results to which GPSA may contribute but that cannot be attributed only to it. The critical assumptions can also be used as a key input for risk management.
In order to operationalize the results framework it is necessary to identify a set of indicators corresponding to the different levels of the “results chain” (except the higher level corresponding to development results) included in the “theory of change” (TOC). This is done below, making use as much as possible of existing indicators and available data sources, as well as those that can be constructed using data that will be generated by GPSA’s operations. It should be noted that whereas the indicated outputs are fully dependent on GPSA (and therefore GPSA is accountable for achieving them), the outcomes and impact depend crucially on the role of other interventions and exogenous factors. Furthermore, the links between outputs and outcomes, as well as between outcomes and impact, are covered by other WB initiatives (such as those under the Governance & Anticorruption -GAC -strategy), as well as by research projects.
Finally, complementing the general key assumptions included in the TOC diagram, the following are additional assumptions concerning what leads from one stage to another:
from activities to outputs: the knowledge component activities (1-3) will help to establish a global platform for knowledge exchange and research (output 1), assuming that CSOs would be interested to participate in such a platform; knowledge on effective SAcc interventions for different contexts would result from the implementation of activities (1-3) assuming that a M&E system (along the lines further described in the GPSA Results Framework, Draft Concept Note, see GPSA website) is fully functional.
from outputs to outcomes: activities supporting the enabling environment for SAcc (4) combined with capacity building activities (2) and outputs (1), (2) and (3) would lead to outcomes (1-4) assuming that the knowledge generated and disseminated is relevant, that governments would be willing, or sufficiently pressured, to undertake governance reforms and to become more accountable; it is also assumed that SAcc capacity building activities will be effective.
from outcomes to impact: outcomes (1-4) would contribute to improved service delivery and development effectiveness assuming that demand pressure on government services resulting from the achievement of those outcomes would lead to enhanced quality of government services and to greater development effectiveness.
On this last set of links, there is evidence from research and ongoing work by (among others) the World Bank GAC strategy, as well as on the work leading to (and spawned by) the 2004 World Development Report (“Making Services Work for Poor People”). On ii), the evidence is thin, and GPSA can and should contribute to it.
B. Indicators and sources of information
Given that GPSA will operate at the global, country and project level, the results framework includes indicators corresponding to these three levels. The indicators are focused on quantitative aspects, which would be complemented by the qualitative information to be provided by the activities indicated in the section on M&E.
Global level
This level is basically related to the fourth results area, i.e., “Learning for improved results”, which at the global level boils down to the generation of the global public good of knowledge on social accountability. Furthermore, aspects related to GPSA as a whole are also included in this level.
Country level
There is an abundance of data sources corresponding to different aspects of SAcc at the country level, such as Governance-at-a-Glance and Demand for Good Governance indicators (AGI Data Portal), WBI’s CDR, the Open Budget Index, Afrobarometer, Latinobarometro, for IDA countries the last of the CPIA criteria, i.e., “Transparency, Accountability, and Corruption in the Public Sector”, IEG (World Bank Independent Evaluation Group) GAC country data , World Bank indicators developed for GAC-II on government openness; CPARs (Country Procurement Assessment Reviews), WBI Worldwide Governance Indicators and the Open Transparency Index.
The tables presented further below select among these sources those which are more adequate given their periodicity and coverage. However, in specific country cases, some of the other sources mentioned above may also be suitable. Furthermore, there are countries where local sources of data on transparency are available. These sources can be tapped particularly in the elaboration of country or thematic case studies, as indicated in the section on M&E.
Project level
Each project/ grant funded by GPSA should indicate in their applications the result area(s) to which it expects to contribute, targets for its outputs specifying their timeframe, the set of activities in which they plan to use the resources provided by GPSA, the links between activities' outputs and outcomes, the current levels of these variables (which will be the baselines) and their implementation strategy. GPSA could develop a web based application that projects/grants could (and should) utilize for their own management and monitoring as well as to feed GPSA’s monitoring and reporting. This would be a sort of self-organizing system, minimizing the time needed from GPSA’s Secretariat.
An important source of information will be the records of activities supported by GPSA. Therefore, it is necessary to ensure that the designs of grants/activities to be funded by GPSA indicate clearly their output and outcome indicators before they are approved, as indicated in the preceding paragraph, and that they complete the collection of baseline data (complementing the data presented in the application form, if need be) during their first 6 months of operations. During the first three months of operations, formats for reporting results and data should be established, and to assure the quality of self-reported data the reports will be systematically reviewed by peer organizations and/or GPSA staff.
GPSA Program-Level Outputs and Outcomes Indicators (Sample Draft - under revision):
C. Outcome indicators and case studies
As indicated in the preceding tables, for some indicators the source of information will be case studies (country and thematic). These case studies could complement the information provided by indicators with an analysis and synthesis of a set of issues such as the following: the extent to which Civil Society (CS), government and other stakeholders have improved knowledge and capacity to harness social accountability for better development outcomes; the degree to which Citizens are engaged in monitoring of service delivery and public resource management; the extent to which Citizens’ priorities are reflected in policy and decision-making (looking at levels of engagement and where this has changed policy and practice), and the extent to which government authorities value the participation of citizens in achieving effective service delivery; participation of CS in public policy discussions; use by CS of grievances mechanisms and collective action behaviour induced by GPSA’s supported CSOs and development by CSOs supported by GPSA of associations representing CS.
D. Performance indicators
In addition to the indicators shown in the above tables, the following indicators are proposed (to be reported on annual bases, using GPSA’s records)to assess GPSA's performance:
1. number of partners involved;
2. number and amount (disbursed) of grants
3. number of mentoring grants,
4. number of countries that opted-in
5. number of grant applications
6. number of CSOs which GPSA supported
E. Dissemination Strategy and Knowledge Sharing to facilitate use and decision making
The results framework can be used to communicate the progress and problems in achieving results. One way of presenting results is through a “dashboard,” highlighting the key high-level objectives and outcomes/outputs achieved, using the framework for planning and review meetings (with the current status of the indicators highlighted), and using the change in the indicators from baseline to highlight the results.